## Construction Project Timeline
Create professional Gantt charts in GanttPRO in a few clicks
Construction Project Timeline | [7 empty] | 2021-04-09 08:21
Color | WBS Number |  | Task name / Title | Assigned to | Planned start date | Planned end date | Deadline | Progress (%) | Duration (hours) | Estimated hours | Time log (minutes) | Status | Priority | Task description | Cost | Actual cost
| 1 | ZONING |  |  | 2021-07-10 08:21 | 2021-09-11 08:21 |  | 0 | 368 | 0 | 0 |  |  |  | 0 | 0
| 1.1 |  | Land Use |  | 2021-07-10 08:21 | 2021-09-10 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 1.2 |  | Easements, Set Backs |  | 2021-07-13 08:21 | 2021-09-11 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 1.3 |  | Access, Street Improvements |  | 2021-07-13 08:21 | 2021-09-11 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 1.4 |  | Utilities Available |  | 2021-07-13 08:21 | 2021-09-11 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 2 | HOUSE PLANS |  |  | 2021-07-15 08:21 | 2021-09-18 08:21 |  | 0 | 384 | 0 | 0 |  |  |  | 0 | 0
| 2.1 |  | Purchase Standard Plans |  | 2021-07-15 08:21 | 2021-09-15 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.2 |  | Architect Original Drawings |  | 2021-07-16 08:21 | 2021-09-16 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.3 |  | Specifications |  | 2021-07-17 08:21 | 2021-09-17 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.4 |  | Architect Manage Job |  | 2021-07-20 08:21 | 2021-09-18 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.5 |  | Engineer-Loads & Spans |  | 2021-07-20 08:21 | 2021-09-18 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.6 |  | Draftsman |  | 2021-07-20 08:21 | 2021-09-18 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 3 | LOT SURVEY |  |  | 2021-07-22 08:21 | 2021-09-25 08:21 |  | 0 | 384 | 0 | 0 |  |  |  | 0 | 0
| 3.1 |  | House & Driveway |  | 2021-07-22 08:21 | 2021-09-22 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 3.2 |  | Well Locaton |  | 2021-07-23 08:21 | 2021-09-23 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 3.3 |  | Septic Location |  | 2021-07-24 08:21 | 2021-09-24 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 3.4 |  | Fire Hydrant & Truck Access |  | 2021-07-27 08:21 | 2021-09-25 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 3.5 |  | Plot Plan |  | 2021-07-27 08:21 | 2021-09-25 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 4 | FINANCIAL - LOAN |  |  | 2021-07-28 08:21 | 2021-10-01 08:21 |  | 0 | 384 | 0 | 0 |  |  |  | 0 | 0
| 4.1 |  | Land Cost |  | 2021-07-28 08:21 | 2021-09-28 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.2 |  | Interest on Land |  | 2021-07-29 08:21 | 2021-09-29 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.3 |  | Interest on Const. Loan |  | 2021-07-30 08:21 | 2021-09-30 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.4 |  | Points, Etc. |  | 2021-07-31 08:21 | 2021-10-01 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 5 | SEWER & WATER HOOKUP |  |  | 2021-08-03 08:21 | 2021-10-02 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 6 | HEALTH PERMIT |  |  | 2021-08-03 08:21 | 2021-10-06 08:21 |  | 0 | 376 | 0 | 0 |  |  |  | 0 | 0
| 6.1 |  | Fees |  | 2021-08-03 08:21 | 2021-10-02 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 6.2 |  | Percolation Test |  | 2021-08-04 08:21 | 2021-10-05 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 6.3 |  | Soils Engineer |  | 2021-08-05 08:21 | 2021-10-06 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 7 | INSURANCE |  |  | 2021-08-06 08:21 | 2021-10-07 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 8 | LOT CLOSING COSTS |  |  | 2021-08-07 08:21 | 2021-10-08 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 9 | BUILDING PERMITS |  |  | 2021-08-10 08:21 | 2021-10-09 08:21 |  | 0 | 360 | 0 | 0 |  |  |  | 0 | 0
| 9.1 |  | Fees |  | 2021-08-10 08:21 | 2021-10-09 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 9.2 |  | Inspection Schedule |  | 2021-08-10 08:21 | 2021-10-09 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 10 | PRELIMINARY LIST ONLY |  |  | 2021-08-11 08:21 | 2021-10-12 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 11 | BUILD PHASE |  |  | 2021-08-12 08:21 | 2021-10-13 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 12 | SPECIAL & DRY IN MATERIALS |  |  | 2021-08-14 08:21 | 2021-10-16 08:21 |  | 0 | 368 | 0 | 0 |  |  |  | 0 | 0
| 12.1 |  | Rough Hardware, Misc. |  | 2021-08-14 08:21 | 2021-10-15 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 12.2 |  | Lolly Columns |  | 2021-08-17 08:21 | 2021-10-16 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 12.3 |  | Steel Beams |  | 2021-08-17 08:21 | 2021-10-16 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 12.4 |  | Rough Lumber, Trusses |  | 2021-08-17 08:21 | 2021-10-16 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 13 | WINDOWS/OPENINGS |  |  | 2021-08-19 08:21 | 2021-10-22 08:21 |  | 0 | 376 | 0 | 0 |  |  |  | 0 | 0
| 13.1 |  | Windows, Grills, Screens |  | 2021-08-19 08:21 | 2021-10-20 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 13.2 |  | Exterior Doors,Screens |  | 2021-08-20 08:21 | 2021-10-21 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 13.3 |  | Skylights and Light Tubes |  | 2021-08-21 08:21 | 2021-10-22 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 14 | DEMOLITION |  |  | 2021-08-24 08:21 | 2021-10-23 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 15 | LOT CLEARING |  |  | 2021-08-24 08:21 | 2021-10-27 08:21 |  | 0 | 376 | 0 | 0 |  |  |  | 0 | 0
| 15.1 |  | Debris Removal & Clearing |  | 2021-08-24 08:21 | 2021-10-23 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 15.2 |  | Dump Fee |  | 2021-08-25 08:21 | 2021-10-26 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 15.3 |  | Bury Stumps, etc. |  | 2021-08-26 08:21 | 2021-10-27 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 16 | DRIVEWAY, rough |  |  | 2021-08-28 08:21 | 2021-10-30 08:21 |  | 0 | 368 | 0 | 0 |  |  |  | 0 | 0
| 16.1 |  | Grade |  | 2021-08-28 08:21 | 2021-10-29 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 16.2 |  | Base Rock, Culverts |  | 2021-08-31 08:21 | 2021-10-30 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 17 | UTILITIES |  |  | 2021-08-31 08:21 | 2021-11-02 08:21 |  | 0 | 368 | 0 | 0 |  |  |  | 0 | 0
| 17.1 |  | Temporary at startup |  | 2021-08-31 08:21 | 2021-10-30 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 17.2 |  | Transfer to permanent |  | 2021-09-01 08:21 | 2021-11-02 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 18 | WELL or PUBLIC WATER |  |  | 2021-09-02 08:21 | 2021-11-03 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 19 | SEPTIC or PUBLIC SEWER |  |  | 2021-09-03 08:21 | 2021-11-04 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 20 | LAYOUT HOUSE FOOTPRINT |  |  | 2021-09-07 08:21 | 2021-11-06 08:21 |  | 0 | 360 | 0 | 0 |  |  |  | 0 | 0
| 20.1 |  | Establish Finish Floor Height |  | 2021-09-07 08:21 | 2021-11-06 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 20.2 |  | Set Back Distances |  | 2021-09-07 08:21 | 2021-11-06 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 21 | DIG FOUNDATION |  |  | 2021-09-07 08:21 | 2021-11-06 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 22 | ROCK PROBLEM |  |  | 2021-09-08 08:21 | 2021-11-09 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 23 | PREPARE FOR FOOTINGS |  |  | 2021-09-10 08:21 | 2021-11-12 08:21 |  | 0 | 368 | 0 | 0 |  |  |  | 0 | 0
| 23.1 |  | Lay out and excavate |  | 2021-09-10 08:21 | 2021-11-11 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 23.2 |  | Form, Rebar, Grade Pegs |  | 2021-09-11 08:21 | 2021-11-12 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 24 | POUR FOOTINGS & PADS |  |  | 2021-09-14 08:21 | 2021-11-13 08:21 |  | 0 | 360 | 0 | 0 |  |  |  | 0 | 0
| 24.1 |  | Yds. of Concrete |  | 2021-09-14 08:21 | 2021-11-13 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 25 | SET BRICK POINTS |  |  | 2021-09-14 08:21 | 2021-11-13 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 26 | TERMITE TREATMENT |  |  | 2021-09-15 08:21 | 2021-11-16 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 27 | RADON CONTROL |  |  | 2021-09-16 08:21 | 2021-11-17 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 28 | FOUNDATION WALLS |  |  | 2021-09-18 08:21 | 2021-11-24 08:21 |  | 0 | 384 | 0 | 0 |  |  |  | 0 | 0
| 28.1 |  | Block/Course |  | 2021-09-18 08:21 | 2021-11-19 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 28.2 |  | Piers |  | 2021-09-21 08:21 | 2021-11-20 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 28.3 |  | Pour Wall, Yds. Of Concrete |  | 2021-09-21 08:21 | 2021-11-20 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 28.4 |  | Lintels, Rebar |  | 2021-09-21 08:21 | 2021-11-20 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 28.5 |  | Parging |  | 2021-09-22 08:21 | 2021-11-23 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 28.6 |  | Cement, Sand, etc. |  | 2021-09-23 08:21 | 2021-11-24 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 29 | WATERPROOF FOUNDATION. |  |  | 2021-09-24 08:21 | 2021-11-25 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 30 | COLUMNS/BEAMS SET |  |  | 2021-09-25 08:21 | 2021-11-26 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 31 | UNDERGROUND PLUMBING |  |  | 2021-09-28 08:21 | 2021-11-27 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 32 | BRICK/STONE, to finish grade |  |  | 2021-09-28 08:21 | 2021-11-27 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 33 | GARAGE DOORS |  |  | 2021-09-29 08:21 | 2021-12-01 08:21 |  | 0 | 368 | 0 | 0 |  |  |  | 0 | 0
| 33.1 |  | Openers |  | 2021-09-29 08:21 | 2021-11-30 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 33.2 |  | Trim, Backing, Weatherstrip |  | 2021-09-30 08:21 | 2021-12-01 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 34 | DRAIN TILE |  |  | 2021-10-01 08:21 | 2021-12-02 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 35 | FIRE PLACE - INTERIOR |  |  | 2021-10-05 08:21 | 2021-12-04 08:21 |  | 0 | 360 | 0 | 0 |  |  |  | 0 | 0
| 35.1 |  | Pour Hearth |  | 2021-10-05 08:21 | 2021-12-04 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 35.2 |  | Firebox, or Set Prefab |  | 2021-10-05 08:21 | 2021-12-04 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 35.3 |  | Brick or Stone Facing |  | 2021-10-05 08:21 | 2021-12-04 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 36 | PREPARE CONC. SLABS ETC. |  |  | 2021-10-07 08:21 | 2021-12-11 08:21 |  | 0 | 384 | 0 | 0 |  |  |  | 0 | 0
| 36.1 |  | Gravel, Wire, Poly, Grade Stakes |  | 2021-10-07 08:21 | 2021-12-08 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 36.2 |  | Labor to Prepare for Slab |  | 2021-10-08 08:21 | 2021-12-09 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 36.3 |  | Rebar, Wire, form boards |  | 2021-10-09 08:21 | 2021-12-10 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 36.4 |  | Labor-Prepare, Form other Conc. |  | 2021-10-12 08:21 | 2021-12-11 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 36.5 |  | Deck & Post Hole footings, etc. |  | 2021-10-12 08:21 | 2021-12-11 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 37 | POUR CONCRETE-SLABS |  |  | 2021-10-13 08:21 | 2021-12-15 08:21 |  | 0 | 368 | 0 | 0 |  |  |  | 0 | 0
| 37.1 |  | Concrete |  | 2021-10-13 08:21 | 2021-12-14 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 37.2 |  | Rebar, Wire, form boards |  | 2021-10-14 08:21 | 2021-12-15 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 38 | SPECIAL BACKING, BLOCKING |  |  | 2021-10-15 08:21 | 2021-12-16 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 39 | BACK FILL, rough |  |  | 2021-10-16 08:21 | 2021-12-17 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 40 | CHIMNEY, exterior |  |  | 2021-10-19 08:21 | 2021-12-21 08:21 |  | 0 | 368 | 0 | 0 |  |  |  | 0 | 0
| 40.1 |  | Block, Flue |  | 2021-10-19 08:21 | 2021-12-18 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 40.2 |  | Brick, Stone |  | 2021-10-19 08:21 | 2021-12-18 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 40.3 |  | Prefab Fireplace & Piping |  | 2021-10-20 08:21 | 2021-12-21 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 41 | FIRE SPRINKLER SYSTEM |  |  | 2021-10-21 08:21 | 2021-12-22 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 42 | ROUGH-IN PLUMBING |  |  | 2021-10-23 08:21 | 2021-12-25 08:21 |  | 0 | 368 | 0 | 0 |  |  |  | 0 | 0
| 42.1 |  | Waste |  | 2021-10-23 08:21 | 2021-12-24 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 42.2 |  | Water |  | 2021-10-26 08:21 | 2021-12-25 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 43 | ROUGH-IN HEAT & A/C |  |  | 2021-10-26 08:21 | 2021-12-29 08:21 |  | 0 | 376 | 0 | 0 |  |  |  | 0 | 0
| 43.1 |  | Ducts & Vents |  | 2021-10-26 08:21 | 2021-12-25 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 43.2 |  | Bath Fans & Vents |  | 2021-10-27 08:21 | 2021-12-28 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 43.3 |  | Kitchen Hood, Dryer Vent |  | 2021-10-28 08:21 | 2021-12-29 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 44 | DECKS-PORCHES-RAILINGS |  |  | 2021-10-30 08:21 | 2022-01-01 08:21 |  | 0 | 368 | 0 | 0 |  |  |  | 0 | 0
| 44.1 |  | Stair, Railings, Pickets |  | 2021-10-30 08:21 | 2021-12-31 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 44.2 |  | Gazebos, Pergola |  | 2021-11-02 08:21 | 2022-01-01 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 45 | ROOFING |  |  | 2021-11-02 08:21 | 2022-01-08 08:21 |  | 0 | 400 | 0 | 0 |  |  |  | 0 | 0
| 45.1 |  | Squares of Roofing |  | 2021-11-02 08:21 | 2022-01-01 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 45.2 |  | Squares Siding |  | 2021-11-03 08:21 | 2022-01-04 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 45.3 |  | Squares rigid insulation |  | 2021-11-04 08:21 | 2022-01-05 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 45.4 |  | Rake & Fascia |  | 2021-11-05 08:21 | 2022-01-06 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 45.5 |  | Soffit, Vents |  | 2021-11-06 08:21 | 2022-01-07 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 45.6 |  | Drip Edge, Flashing, Hardware |  | 2021-11-09 08:21 | 2022-01-08 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 45.7 |  | Roof Paper, Siding Paper |  | 2021-11-09 08:21 | 2022-01-08 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 46 | FASCIA & SOFFIT |  |  | 2021-11-09 08:21 | 2022-01-08 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 47 | SHINGLES/FLASHING |  |  | 2021-11-10 08:21 | 2022-01-11 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 48 | WOOD SIDING |  |  | 2021-11-11 08:21 | 2022-01-12 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 49 | BRICK/STONE SIDING |  |  | 2021-11-12 08:21 | 2022-01-13 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 50 | ROUGH-IN ELECTRIC |  |  | 2021-11-16 08:21 | 2022-01-18 08:21 |  | 0 | 368 | 0 | 0 |  |  |  | 0 | 0
| 50.1 |  | Tv, Stereo, Phone, Intercom |  | 2021-11-16 08:21 | 2022-01-15 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 50.2 |  | Electric Wire, Boxes |  | 2021-11-16 08:21 | 2022-01-15 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 50.3 |  | Vacuum, Misc. |  | 2021-11-16 08:21 | 2022-01-15 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 50.4 |  | Security |  | 2021-11-17 08:21 | 2022-01-18 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 51 | INSULATION |  |  | 2021-11-19 08:21 | 2022-01-25 08:21 |  | 0 | 384 | 0 | 0 |  |  |  | 0 | 0
| 51.1 |  | Crawl Space, Basement |  | 2021-11-19 08:21 | 2022-01-20 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 51.2 |  | Ceilings |  | 2021-11-20 08:21 | 2022-01-21 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 51.3 |  | Walls |  | 2021-11-23 08:21 | 2022-01-22 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 51.4 |  | Attic, rafters |  | 2021-11-23 08:21 | 2022-01-22 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 51.5 |  | Caulk-Windows, Doors, Etc. |  | 2021-11-23 08:21 | 2022-01-22 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 51.6 |  | Firestuffing |  | 2021-11-24 08:21 | 2022-01-25 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 52 | STAIRS |  |  | 2021-11-26 08:21 | 2022-01-28 08:21 |  | 0 | 368 | 0 | 0 |  |  |  | 0 | 0
| 52.1 |  | Treads & Risers |  | 2021-11-26 08:21 | 2022-01-27 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 52.2 |  | Railing & Grasp |  | 2021-11-27 08:21 | 2022-01-28 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 53 | EXTERIOR PAINT |  |  | 2021-11-30 08:21 | 2022-01-29 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 54 | DRYWALL |  |  | 2021-11-30 08:21 | 2022-02-04 08:21 |  | 0 | 392 | 0 | 0 |  |  |  | 0 | 0
| 54.1 |  | Hang |  | 2021-11-30 08:21 | 2022-01-29 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 54.2 |  | Tape |  | 2021-12-01 08:21 | 2022-02-01 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 54.3 |  | Block & Skim Coats |  | 2021-12-02 08:21 | 2022-02-02 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 54.4 |  | Sand |  | 2021-12-03 08:21 | 2022-02-03 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 54.5 |  | Clean Up |  | 2021-12-04 08:21 | 2022-02-04 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 55 | INTERIOR PAINT |  |  | 2021-12-07 08:21 | 2022-02-05 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 56 | TRIM CARPENTRY |  |  | 2021-12-07 08:21 | 2022-02-12 08:21 |  | 0 | 400 | 0 | 0 |  |  |  | 0 | 0
| 56.1 |  | Stair Railings, Pickets |  | 2021-12-07 08:21 | 2022-02-05 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 56.2 |  | Interior Doors |  | 2021-12-08 08:21 | 2022-02-08 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 56.3 |  | Base |  | 2021-12-09 08:21 | 2022-02-09 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 56.4 |  | Casing Trim |  | 2021-12-10 08:21 | 2022-02-10 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 56.5 |  | Window Stool |  | 2021-12-11 08:21 | 2022-02-11 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 56.6 |  | Closet Shelving |  | 2021-12-14 08:21 | 2022-02-12 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 56.7 |  | Decorator Mouldings, Etc. |  | 2021-12-14 08:21 | 2022-02-12 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 56.8 |  | Finish Hardware, Mirrors, Etc. |  | 2021-12-14 08:21 | 2022-02-12 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 57 | CABINETS-VANITIES-TOPS |  |  | 2021-12-16 08:21 | 2022-02-19 08:21 |  | 0 | 384 | 0 | 0 |  |  |  | 0 | 0
| 57.1 |  | Cabinets, Bath Vanities |  | 2021-12-16 08:21 | 2022-02-16 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 57.2 |  | Kitchen Counter Tops |  | 2021-12-17 08:21 | 2022-02-17 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 57.3 |  | Bath Vanity Tops |  | 2021-12-18 08:21 | 2022-02-18 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 57.4 |  | Medicine Cabinets |  | 2021-12-21 08:21 | 2022-02-19 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 58 | GUTTER & DOWN SPOUT |  |  | 2021-12-21 08:21 | 2022-02-19 08:21 |  | 0 | 360 | 0 | 0 |  |  |  | 0 | 0
| 58.1 |  | Stormwater Control |  | 2021-12-21 08:21 | 2022-02-19 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 59 | FINISH GRADING |  |  | 2021-12-22 08:21 | 2022-02-22 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 60 | FINISH DRIVEWAY |  |  | 2021-12-23 08:21 | 2022-02-23 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 61 | WALKS-DRIVEWAY APRON |  |  | 2021-12-25 08:21 | 2022-02-26 08:21 |  | 0 | 368 | 0 | 0 |  |  |  | 0 | 0
| 61.1 |  | Prepare |  | 2021-12-25 08:21 | 2022-02-25 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 61.2 |  | Concrete |  | 2021-12-28 08:21 | 2022-02-26 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 61.3 |  | Rebar, Wire, form boards |  | 2021-12-28 08:21 | 2022-02-26 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 62 | CERAMIC TILE |  |  | 2021-12-29 08:21 | 2022-03-02 08:21 |  | 0 | 368 | 0 | 0 |  |  |  | 0 | 0
| 62.1 |  | Backer Board & Prep |  | 2021-12-29 08:21 | 2022-03-01 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 62.2 |  | Tile & Grout |  | 2021-12-30 08:21 | 2022-03-02 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 63 | ELEC-SWITCH/PLUG/PANEL |  |  | 2021-12-31 08:21 | 2022-03-03 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 64 | LANDSCAPING |  |  | 2022-01-01 08:21 | 2022-03-04 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 65 | LAWN SEEDING |  |  | 2022-01-04 08:21 | 2022-03-05 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 66 | VINYL FLOORING |  |  | 2022-01-04 08:21 | 2022-03-08 08:21 |  | 0 | 368 | 0 | 0 |  |  |  | 0 | 0
| 66.1 |  | Subfloor |  | 2022-01-04 08:21 | 2022-03-05 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 66.2 |  | Square Yards of Vinyl |  | 2022-01-05 08:21 | 2022-03-08 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 67 | CARPETING |  |  | 2022-01-07 08:21 | 2022-03-11 08:21 |  | 0 | 368 | 0 | 0 |  |  |  | 0 | 0
| 67.1 |  | Square yards of Pad |  | 2022-01-07 08:21 | 2022-03-10 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 67.2 |  | Square Yards of Carpet |  | 2022-01-08 08:21 | 2022-03-11 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 68 | WOOD FLOORS-STAIRS |  |  | 2022-01-11 08:21 | 2022-03-15 08:21 |  | 0 | 368 | 0 | 0 |  |  |  | 0 | 0
| 68.1 |  | Install |  | 2022-01-11 08:21 | 2022-03-12 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 68.2 |  | Sand, Seal, Stain |  | 2022-01-11 08:21 | 2022-03-12 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 68.3 |  | Finish Coat |  | 2022-01-12 08:21 | 2022-03-15 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 69 | APPLIANCES |  |  | 2022-01-14 08:21 | 2022-03-18 08:21 |  | 0 | 368 | 0 | 0 |  |  |  | 0 | 0
| 69.1 |  | Purchase & Delivery |  | 2022-01-14 08:21 | 2022-03-17 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 69.2 |  | Installation |  | 2022-01-15 08:21 | 2022-03-18 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 70 | HEATING & A/C |  |  | 2022-01-18 08:21 | 2022-03-19 08:21 |  | 0 | 360 | 0 | 0 |  |  |  | 0 | 0
| 70.1 |  | Install & Test Equipment |  | 2022-01-18 08:21 | 2022-03-19 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 70.2 |  | Grills & Thermostat |  | 2022-01-18 08:21 | 2022-03-19 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 71 | PLUMBING TRIM |  |  | 2022-01-19 08:21 | 2022-03-22 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 72 | ELECTRICAL TRIM |  |  | 2022-01-20 08:21 | 2022-03-23 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 73 | FINAL CLEAN |  |  | 2022-01-21 08:21 | 2022-03-24 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 74 | WALK THROUGH |  |  | 2022-01-22 08:21 | 2022-03-25 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
| 75 | FINISH PUNCH LIST |  |  | 2022-01-25 08:21 | 2022-03-26 08:21 |  | 0 | 360 | 0 | 0 | Open | Medium |  | 0 | 0
This document has been created with the help of https://ganttpro.com online service
You are free to use the document for your purposes with no limitations. To edit it, please, create a copy or use https://ganttpro.com