## Exhibition Planning
Create professional Gantt charts in GanttPRO in a few clicks
Exhibition Planning | [8 empty] | 2021-04-13 07:58
Color | WBS Number |  |  | Task name / Title | Assigned to | Planned start date | Planned end date | Deadline | Progress (%) | Duration (hours) | Estimated hours | Time log (minutes) | Status | Priority | Task description | Cost | Actual cost
| 1 | Basics |  |  |  | 2021-04-14 07:58 | 2021-04-28 07:58 |  | 0 | 88 | 0 | 0 |  |  |  | 0 | 0
| 1.1 |  | Select appropriate show |  |  | 2021-04-14 07:58 | 2021-04-18 07:58 |  | 0 | 24 | 0 | 0 | Open | Medium |  | 0 | 0
| 1.2 |  | Set budget |  |  | 2021-04-17 07:58 | 2021-04-19 07:58 |  | 0 | 24 | 0 | 0 | Open | Medium |  | 0 | 0
| 1.3 |  | Decide type of stand: |  |  | 2021-04-20 07:58 | 2021-04-25 07:58 |  | 0 | 32 | 0 | 0 |  |  |  | 0 | 0
| 1.3.1 |  |  | Shell scheme |  | 2021-04-20 07:58 | 2021-04-24 07:58 |  | 0 | 24 | 0 | 0 | Open | Medium |  | 0 | 0
| 1.3.2 |  |  | Space only |  | 2021-04-21 07:58 | 2021-04-25 07:58 |  | 0 | 24 | 0 | 0 | Open | Medium |  | 0 | 0
| 1.4 |  | Agree stand size and location |  |  | 2021-04-26 07:58 | 2021-04-28 07:58 |  | 0 | 24 | 0 | 0 | Open | Medium |  | 0 | 0
| 1.5 |  | Learn about the most common exhibiting mistakes before you book |  |  | 2021-04-21 07:58 | 2021-04-28 07:58 |  | 0 | 48 | 0 | 0 | Open | Medium |  | 0 | 0
| 2 | Setting objectives |  |  |  | 2021-04-24 07:58 | 2021-04-28 07:58 |  | 0 | 40 | 0 | 0 |  |  |  | 0 | 0
| 2.1 |  | Define your audience |  |  | 2021-04-24 07:58 | 2021-04-26 07:58 |  | 0 | 24 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.2 |  | What does success look like to you? |  |  | 2021-04-25 07:58 | 2021-04-28 07:58 |  | 0 | 32 | 0 | 0 |  |  |  | 0 | 0
| 2.2.1 |  |  | Set sales target |  | 2021-04-25 07:58 | 2021-04-27 07:58 |  | 0 | 24 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.2.2 |  |  | Set leads target |  | 2021-04-26 07:58 | 2021-04-28 07:58 |  | 0 | 24 | 0 | 0 | Open | Medium |  | 0 | 0
| 3 | Show offering |  |  |  | 2021-04-27 07:58 | 2021-05-08 07:58 |  | 0 | 64 | 0 | 0 |  |  |  | 0 | 0
| 3.1 |  | Decide which products and services to exhibit |  |  | 2021-04-27 07:58 | 2021-05-01 07:58 |  | 0 | 24 | 0 | 0 | Open | Medium |  | 0 | 0
| 3.2 |  | What’s your ‘big enticement’? Will you: |  |  | 2021-05-02 07:58 | 2021-05-04 07:58 |  | 0 | 24 | 0 | 0 |  |  |  | 0 | 0
| 3.2.1 |  |  | Launch a product / service? |  | 2021-05-02 07:58 | 2021-05-02 07:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 3.2.2 |  |  | Offer a show-only discount / deal? |  | 2021-05-03 07:58 | 2021-05-03 07:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 3.2.3 |  |  | Provide demonstrations or free trials? |  | 2021-05-04 07:58 | 2021-05-04 07:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 3.3 |  | Review speaker opportunities |  |  | 2021-05-05 07:58 | 2021-05-05 07:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 3.4 |  | Research workshop or breakout session opportunities |  |  | 2021-05-08 07:58 | 2021-05-08 07:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 4 | Stand design and requirements |  |  |  | 2021-05-05 07:58 | 2021-05-22 07:58 |  | 0 | 96 | 0 | 0 |  |  |  | 0 | 0
| 4.1 |  | Write a good stand brief for your provider |  |  | 2021-05-05 07:58 | 2021-05-05 07:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.2 |  | Decide stand requirements: |  |  | 2021-05-08 07:58 | 2021-05-17 07:58 |  | 0 | 64 | 0 | 0 |  |  |  | 0 | 0
| 4.2.1 |  |  | Location |  | 2021-05-08 07:58 | 2021-05-10 07:58 |  | 0 | 24 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.2.2 |  |  | Lighting |  | 2021-05-11 07:58 | 2021-05-11 07:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.2.3 |  |  | Utilities such as water, electricity, internet, phone lines |  | 2021-05-11 07:58 | 2021-05-11 07:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.2.4 |  |  | On-stand furniture |  | 2021-05-11 07:58 | 2021-05-11 07:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.2.5 |  |  | Carpets / floor covering |  | 2021-05-11 07:58 | 2021-05-11 07:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.2.6 |  |  | Catering / refreshments |  | 2021-05-12 07:58 | 2021-05-12 07:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.2.7 |  |  | Cutlery / cups / plates etc |  | 2021-05-12 07:58 | 2021-05-12 07:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.2.8 |  |  | AV equipment and/or presentations |  | 2021-05-15 07:58 | 2021-05-16 07:58 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.2.9 |  |  | Formal / informal meeting areas |  | 2021-05-16 07:58 | 2021-05-16 07:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.2.10 |  |  | USB sticks, adaptors, chargers, cables |  | 2021-05-16 07:58 | 2021-05-16 07:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.2.11 |  |  | Waste bins |  | 2021-05-17 07:58 | 2021-05-17 07:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.3 |  | Do you have a data capture system? |  |  | 2021-05-18 07:58 | 2021-05-18 07:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.4 |  | Will your stand meet safety regulations? |  |  | 2021-05-19 07:58 | 2021-05-19 07:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.5 |  | Do you have insurance? |  |  | 2021-05-22 07:58 | 2021-05-22 07:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.6 |  | Do you need security or night sheets? |  |  | 2021-05-22 07:58 | 2021-05-22 07:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.7 |  | Does the stand need to be stored after the show? |  |  | 2021-05-22 07:58 | 2021-05-22 07:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5 | Team |  |  |  | 2021-05-23 07:58 | 2021-06-02 07:58 |  | 0 | 72 | 0 | 0 |  |  |  | 0 | 0
| 5.1 |  | Decide on your exhibition team |  |  | 2021-05-23 07:58 | 2021-05-25 07:58 |  | 0 | 24 | 0 | 0 |  |  |  | 0 | 0
| 5.1.1 |  |  | Are they knowledgeable? |  | 2021-05-23 07:58 | 2021-05-23 07:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.1.2 |  |  | Are they experienced events professionals? |  | 2021-05-24 07:58 | 2021-05-25 07:58 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.2 |  | Create stand rota |  |  | 2021-05-25 07:58 | 2021-05-26 07:58 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.3 |  | Is branded clothing required? |  |  | 2021-05-26 07:58 | 2021-05-26 07:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.4 |  | Book hotel rooms and transport |  |  | 2021-05-26 07:58 | 2021-05-26 07:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.5 |  | Create name badges |  |  | 2021-05-26 07:58 | 2021-05-29 07:58 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.6 |  | Set expenses budget |  |  | 2021-05-30 07:58 | 2021-05-30 07:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.7 |  | Brief team (exhibition goals, lead targets, dress code, stand rules, etc) |  |  | 2021-05-31 07:58 | 2021-06-02 07:58 |  | 0 | 24 | 0 | 0 | Open | Medium |  | 0 | 0
| 6 | Pre-event marketing |  |  |  | 2021-06-05 07:58 | 2021-06-08 07:58 |  | 0 | 32 | 0 | 0 |  |  |  | 0 | 0
| 6.1 |  | Learn how to attract more visitors to your stand |  |  | 2021-06-05 07:58 | 2021-06-05 07:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 6.2 |  | Promote event on website |  |  | 2021-06-06 07:58 | 2021-06-06 07:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 6.3 |  | Promote event on social media |  |  | 2021-06-05 07:58 | 2021-06-06 07:58 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 6.4 |  | Notify clients and prospects |  |  | 2021-06-07 07:58 | 2021-06-07 07:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 6.5 |  | Create press release and distribute to target media |  |  | 2021-06-08 07:58 | 2021-06-08 07:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 7 | On-stand marketing |  |  |  | 2021-06-09 07:58 | 2021-06-19 07:58 |  | 0 | 56 | 0 | 0 |  |  |  | 0 | 0
| 7.1 |  | Decide on promotional gifts |  |  | 2021-06-09 07:58 | 2021-06-09 07:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 7.2 |  | Design and print sufficient collateral |  |  | 2021-06-12 07:58 | 2021-06-12 07:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 7.3 |  | Design and print sufficient business cards |  |  | 2021-06-13 07:58 | 2021-06-13 07:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 7.4 |  | Design and print pop-ups / roller banners etc |  |  | 2021-06-14 07:58 | 2021-06-14 07:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 7.5 |  | Sign and return order forms and declarations |  |  | 2021-06-15 07:58 | 2021-06-15 07:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 7.6 |  | Note shipping |  |  | 2021-06-15 07:58 | 2021-06-15 07:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 7.7 |  | Note set-up and dismantle times |  |  | 2021-06-15 07:58 | 2021-06-15 07:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 7.8 |  | Note artwork deadlines |  |  | 2021-06-16 07:58 | 2021-06-16 07:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 7.9 |  | Note show guide deadlines |  |  | 2021-06-19 07:58 | 2021-06-19 07:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 8 | Paperwork and timelines |  |  |  | 2021-06-09 07:58 | 2021-06-19 07:58 |  | 0 | 56 | 0 | 0 |  |  |  | 0 | 0
| 8.1 |  | Decide on promotional gifts |  |  | 2021-06-09 07:58 | 2021-06-09 07:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 8.2 |  | Design and print sufficient collateral |  |  | 2021-06-12 07:58 | 2021-06-13 07:58 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 8.3 |  | Design and print sufficient business cards |  |  | 2021-06-14 07:58 | 2021-06-14 07:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 8.4 |  | Design and print pop-ups / roller banners etc |  |  | 2021-06-15 07:58 | 2021-06-15 07:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 8.5 |  | Sign and return order forms and declarations |  |  | 2021-06-14 07:58 | 2021-06-16 07:58 |  | 0 | 24 | 0 | 0 | Open | Medium |  | 0 | 0
| 8.6 |  | Note shipping |  |  | 2021-06-15 07:58 | 2021-06-15 07:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 8.7 |  | Note set-up and dismantle times |  |  | 2021-06-16 07:58 | 2021-06-16 07:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 8.8 |  | Note artwork deadlines |  |  | 2021-06-19 07:58 | 2021-06-19 07:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 8.9 |  | Note show guide deadlines |  |  | 2021-06-19 07:58 | 2021-06-19 07:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 9 | At the event |  |  |  | 2021-06-20 07:58 | 2021-06-26 07:58 |  | 0 | 40 | 0 | 0 |  |  |  | 0 | 0
| 9.1 |  | Take list of important contact numbers |  |  | 2021-06-20 07:58 | 2021-06-20 07:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 9.2 |  | Take contract |  |  | 2021-06-21 07:58 | 2021-06-21 07:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 9.3 |  | Take stand layout plan |  |  | 2021-06-22 07:58 | 2021-06-22 07:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 9.4 |  | Take show stationery |  |  | 2021-06-23 07:58 | 2021-06-23 07:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 9.5 |  | Take a First Aid kit |  |  | 2021-06-26 07:58 | 2021-06-26 07:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 10 | Post-event activity and evaluation |  |  |  | 2021-06-26 07:58 | 2021-06-30 07:58 |  | 0 | 40 | 0 | 0 |  |  |  | 0 | 0
| 10.1 |  | Have all scheduled leads been followed up? |  |  | 2021-06-26 07:58 | 2021-06-26 07:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 10.2 |  | Have all non-scheduled leads been followed up within 3 days of the event? |  |  | 2021-06-27 07:58 | 2021-06-27 07:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 10.3 |  | Evaluate results against objectives |  |  | 2021-06-28 07:58 | 2021-06-28 07:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 10.4 |  | Evaluate results against investment. |  |  | 2021-06-29 07:58 | 2021-06-29 07:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 10.5 |  | Communicate outcomes to stand team and thank you’s. |  |  | 2021-06-30 07:58 | 2021-06-30 07:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
This document has been created with the help of https://ganttpro.com online service
You are free to use the document for your purposes with no limitations. To edit it, please, create a copy or use https://ganttpro.com