## Workshop Planning Checklist
Create professional Gantt charts in GanttPRO in a few clicks
Workshop Planning Checklist | [8 empty] | 2021-04-13 09:26
Color | WBS Number |  |  | Task name / Title | Assigned to | Planned start date | Planned end date | Deadline | Progress (%) | Duration (hours) | Estimated hours | Time log (minutes) | Status | Priority | Task description | Cost | Actual cost
| 1 | 8 Weeks Before Program |  |  |  | 2021-04-14 09:26 | 2021-04-27 09:26 |  | 11 | 80 | 0 | 0 |  |  |  | 0 | 0
| 1.1 |  | Open registration |  |  | 2021-04-14 09:26 | 2021-04-18 09:26 |  | 0 | 24 | 0 | 0 | Open | Medium |  | 0 | 0
| 1.2 |  | Make sure the information on registration form is consistent |  |  | 2021-04-15 09:26 | 2021-04-19 09:26 |  | 0 | 24 | 0 | 0 | Open | Medium |  | 0 | 0
| 1.3 |  | Initiate arrangements with caterer |  |  | 2021-04-18 09:26 | 2021-04-20 09:26 |  | 0 | 24 | 0 | 0 | Open | Medium |  | 0 | 0
| 1.4 |  | Design a PDF flyer |  |  | 2021-04-18 09:26 | 2021-04-20 09:26 |  | 0 | 24 | 0 | 0 | Open | Medium |  | 0 | 0
| 1.5 |  | Verify driving directions to be included in PR |  |  | 2021-04-18 09:26 | 2021-04-20 09:26 |  | 0 | 24 | 0 | 0 | Open | Medium |  | 0 | 0
| 1.6 |  | Send PR information to PR Coordinator |  |  | 2021-04-20 09:26 | 2021-04-26 09:26 |  | 0 | 40 | 0 | 0 |  |  |  | 0 | 0
| 1.6.1 |  |  | release times |  | 2021-04-20 09:26 | 2021-04-24 09:26 |  | 0 | 24 | 0 | 0 | Open | Medium |  | 0 | 0
| 1.6.2 |  |  | suggested text, including PDF flyer link |  | 2021-04-21 09:26 | 2021-04-25 09:26 |  | 0 | 24 | 0 | 0 | Open | Medium |  | 0 | 0
| 1.6.3 |  |  | Update social media with workshop details. |  | 2021-04-22 09:26 | 2021-04-26 09:26 |  | 0 | 24 | 0 | 0 | Open | Medium |  | 0 | 0
| 1.7 |  | Confirm arrangements with presenter(s) |  |  | 2021-04-24 09:26 | 2021-04-26 09:26 |  | 100 | 24 | 0 | 0 | Done | Medium |  | 0 | 0
| 1.8 |  | Request presenter photo and bio for PR |  |  | 2021-04-24 09:26 | 2021-04-27 09:26 |  | 0 | 32 | 0 | 0 | Open | Medium |  | 0 | 0
| 2 | 6 Weeks Before Program |  |  |  | 2021-04-28 09:26 | 2021-05-08 09:26 |  | 0 | 56 | 0 | 0 |  |  |  | 0 | 0
| 2.1 |  | Promote weekly via PR Coordinator on relevant listservs and social media |  |  | 2021-04-28 09:26 | 2021-05-02 09:26 |  | 0 | 24 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.2 |  | Request giveaways, folders, emergency kit |  |  | 2021-05-01 09:26 | 2021-05-03 09:26 |  | 0 | 24 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.3 |  | Photocopy all registration checks |  |  | 2021-05-02 09:26 | 2021-05-04 09:26 |  | 0 | 24 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.4 |  | Keep copies of all receipts, bills, and contracts. |  |  | 2021-05-03 09:26 | 2021-05-05 09:26 |  | 0 | 24 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.5 |  | Make sure committee registers |  |  | 2021-05-04 09:26 | 2021-05-08 09:26 |  | 0 | 24 | 0 | 0 | Open | Medium |  | 0 | 0
| 3 | 4 Weeks Before Program |  |  |  | 2021-05-09 09:26 | 2021-05-18 09:26 |  | 0 | 64 | 0 | 0 |  |  |  | 0 | 0
| 3.1 |  | Confirm arrangements with venue |  |  | 2021-05-09 09:26 | 2021-05-15 09:26 |  | 0 | 40 | 0 | 0 |  |  |  | 0 | 0
| 3.1.1 |  |  | technology |  | 2021-05-09 09:26 | 2021-05-11 09:26 |  | 0 | 24 | 0 | 0 | Open | Medium |  | 0 | 0
| 3.1.2 |  |  | parking hours |  | 2021-05-10 09:26 | 2021-05-12 09:26 |  | 0 | 24 | 0 | 0 | Open | Medium |  | 0 | 0
| 3.1.3 |  |  | etc. |  | 2021-05-11 09:26 | 2021-05-15 09:26 |  | 0 | 24 | 0 | 0 | Open | Medium |  | 0 | 0
| 3.2 |  | Continue promotion, monitor registration. |  |  | 2021-05-12 09:26 | 2021-05-16 09:26 |  | 0 | 24 | 0 | 0 | Open | Medium |  | 0 | 0
| 3.3 |  | Develop evaluations |  |  | 2021-05-15 09:26 | 2021-05-18 09:26 |  | 0 | 32 | 0 | 0 | Open | Medium |  | 0 | 0
| 4 | 2 Weeks Before Program |  |  |  | 2021-05-22 09:26 | 2021-05-30 09:26 |  | 0 | 56 | 0 | 0 |  |  |  | 0 | 0
| 4.1 |  | Continue promotion, monitor registration |  |  | 2021-05-22 09:26 | 2021-05-24 09:26 |  | 0 | 24 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.2 |  | Confirm committee assignments |  |  | 2021-05-23 09:26 | 2021-05-25 09:26 |  | 0 | 24 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.3 |  | Prepare print agenda, evaluation form, receipts, and other handouts. |  |  | 2021-05-24 09:26 | 2021-05-26 09:26 |  | 0 | 24 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.4 |  | Purchase thank you gifts |  |  | 2021-05-25 09:26 | 2021-05-29 09:26 |  | 0 | 24 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.5 |  | Make sure attendees have good directions |  |  | 2021-05-26 09:26 | 2021-05-30 09:26 |  | 0 | 24 | 0 | 0 | Open | Medium |  | 0 | 0
| 5 | 1 Week Before Program |  |  |  | 2021-05-31 09:26 | 2021-06-06 09:26 |  | 0 | 40 | 0 | 0 |  |  |  | 0 | 0
| 5.1 |  | Give final count to caterer |  |  | 2021-05-31 09:26 | 2021-06-01 09:26 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.2 |  | Finalize details with presenter(s) |  |  | 2021-06-01 09:26 | 2021-06-02 09:26 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.3 |  | Purchase water, breakfast, and snack items |  |  | 2021-06-02 09:26 | 2021-06-05 09:26 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.4 |  | Print nametags, signage, and list of names of registered attendees |  |  | 2021-06-05 09:26 | 2021-06-06 09:26 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.5 |  | Assemble folders or information packets |  |  | 2021-06-05 09:26 | 2021-06-06 09:26 |  | 0 | 16 | 0 | 0 |  |  |  | 0 | 0
| 5.5.1 |  |  | agenda |  | 2021-06-05 09:26 | 2021-06-06 09:26 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.5.2 |  |  | evaluation form |  | 2021-06-05 09:26 | 2021-06-06 09:26 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.5.3 |  |  | Wi-Fi password |  | 2021-06-05 09:26 | 2021-06-06 09:26 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.5.4 |  |  | other handouts |  | 2021-06-05 09:26 | 2021-06-06 09:26 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.6 |  | Print list of attendees for registration table checklist |  |  | 2021-06-05 09:26 | 2021-06-06 09:26 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 6 | Day of Program |  |  |  | 2021-06-07 09:26 | 2021-06-07 09:26 |  | 0 | 8 | 0 | 0 |  |  |  | 0 | 0
| 6.1 |  | Double-check technology and Wi-Fi |  |  | 2021-06-07 09:26 | 2021-06-07 09:26 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 6.2 |  | Set up signage |  |  | 2021-06-07 09:26 | 2021-06-07 09:26 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 6.3 |  | Set up registration table, folders, and giveaway table |  |  | 2021-06-07 09:26 | 2021-06-07 09:26 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 6.4 |  | Make sure coffee service and morning catering is set up |  |  | 2021-06-07 09:26 | 2021-06-07 09:26 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 6.5 |  | Check off attendees |  |  | 2021-06-07 09:26 | 2021-06-07 09:26 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 6.6 |  | Introduce program, any housekeeping items, and introduce speaker |  |  | 2021-06-07 09:26 | 2021-06-07 09:26 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 6.7 |  | Photograph throughout day for newsletter |  |  | 2021-06-07 09:26 | 2021-06-07 09:26 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 6.8 |  | Encourage return of evaluations |  |  | 2021-06-07 09:26 | 2021-06-07 09:26 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 6.9 |  | Distribute giveaways and any door prizes |  |  | 2021-06-07 09:26 | 2021-06-07 09:26 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 6.10 |  | Distribute thank you gifts or checks to presenter(s) |  |  | 2021-06-07 09:26 | 2021-06-07 09:26 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 7 | After Program |  |  |  | 2021-06-08 09:26 | 2021-06-09 09:26 |  | 0 | 8 | 0 | 0 |  |  |  | 0 | 0
| 7.1 |  | Complete final Activity Budget Proposal and Expense Report |  |  | 2021-06-08 09:26 | 2021-06-08 09:26 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 7.2 |  | Pay any outstanding expenses. |  |  | 2021-06-08 09:26 | 2021-06-08 09:26 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 7.3 |  | Collect and analyze evaluations. Share with planning committee |  |  | 2021-06-08 09:26 | 2021-06-09 09:26 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 7.4 |  | Send copy of evaluation to presenter(s) |  |  | 2021-06-08 09:26 | 2021-06-08 09:26 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 7.5 |  | Send thank you note presenter(s) |  |  | 2021-06-08 09:26 | 2021-06-08 09:26 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 7.6 |  | Include a summary of workshop |  |  | 2021-06-08 09:26 | 2021-06-08 09:26 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 7.7 |  | Follow up on any potential new members |  |  | 2021-06-08 09:26 | 2021-06-08 09:26 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 7.8 |  | Request PowerPoint slides or documents from presenter(s) |  |  | 2021-06-08 09:26 | 2021-06-08 09:26 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 7.9 |  | If you used electronic evaluations, re-send link to participants and give a deadline. |  |  | 2021-06-08 09:26 | 2021-06-08 09:26 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
This document has been created with the help of https://ganttpro.com online service
You are free to use the document for your purposes with no limitations. To edit it, please, create a copy or use https://ganttpro.com