## 12 Month Real Estate Marketing
Create professional Gantt charts in GanttPRO in a few clicks
12 Month Real Estate Marketing Plan | [7 empty] | 2020-06-16 14:41
Color | WBS Number |  | Task name / Title | Assigned to | Planned start date | Planned end date | Deadline | Progress (%) | Duration (hours) | Estimated hours | Time log (minutes) | Status | Priority | Task description | Cost | Actual cost
| 1 | Executive Summary |  |  | 2020-06-17 14:41 | 2020-06-19 14:41 |  | 0 | 24 | 0 | 0 |  |  |  | 0 | 0
| 1.1 |  | Corporate Status and Ownership |  | 2020-06-17 14:41 | 2020-06-19 14:41 |  | 0 | 24 | 0 | 0 | Open | Medium |  | 0 | 0
| 2 | Business Model and Value Proposition |  |  | 2020-06-19 14:41 | 2020-06-23 14:41 |  | 0 | 24 | 0 | 0 |  |  |  | 0 | 0
| 2.1 |  | Parameters and Guidelines |  | 2020-06-19 14:41 | 2020-06-23 14:41 |  | 0 | 24 | 0 | 0 | Open | Medium |  | 0 | 0
| 3 | Buying, Holding and Selling Properties |  |  | 2020-06-22 14:41 | 2020-06-30 14:41 |  | 11 | 56 | 0 | 0 |  |  |  | 0 | 0
| 3.1 |  | Lead Generation |  | 2020-06-22 14:41 | 2020-06-22 14:41 |  | 100 | 8 | 0 | 0 | Done | Medium |  | 0 | 0
| 3.2 |  | Researching Properties |  | 2020-06-22 14:41 | 2020-06-22 14:41 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 3.3 |  | The Maximum Purchase Price Worksheet |  | 2020-06-23 14:41 | 2020-06-23 14:41 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 3.4 |  | Making Offers |  | 2020-06-23 14:41 | 2020-06-23 14:41 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 3.5 |  | Financing |  | 2020-06-24 14:41 | 2020-06-24 14:41 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 3.6 |  | Managing Cash Flow |  | 2020-06-25 14:41 | 2020-06-25 14:41 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 3.7 |  | Turnaround Time |  | 2020-06-26 14:41 | 2020-06-26 14:41 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 3.8 |  | Rehabbing Properties |  | 2020-06-29 14:41 | 2020-06-29 14:41 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 3.9 |  | Selling Properties |  | 2020-06-30 14:41 | 2020-06-30 14:41 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 4 | Marketing Plan |  |  | 2020-07-01 14:41 | 2020-07-03 14:41 |  | 0 | 24 | 0 | 0 |  |  |  | 0 | 0
| 4.1 |  | Competition |  | 2020-07-01 14:41 | 2020-07-03 14:41 |  | 0 | 24 | 0 | 0 | Open | Medium |  | 0 | 0
| 5 | Industry Review |  |  | 2020-07-03 14:41 | 2020-07-07 14:41 |  | 0 | 24 | 0 | 0 |  |  |  | 0 | 0
| 5.1 |  | Key Industry Benefits |  | 2020-07-03 14:41 | 2020-07-07 14:41 |  | 0 | 24 | 0 | 0 | Open | Medium |  | 0 | 0
| 6 | Implementation |  |  | 2020-07-06 14:41 | 2020-08-03 14:41 |  | 7 | 168 | 0 | 0 |  |  |  | 0 | 0
| 6.1 |  | Future Services |  | 2020-07-06 14:41 | 2020-07-06 14:41 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 6.2 |  | Write Business Plan |  | 2020-07-06 14:41 | 2020-07-06 14:41 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 6.3 |  | Meet with Attorney |  | 2020-07-07 14:41 | 2020-07-07 14:41 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 6.4 |  | Incorporate |  | 2020-07-08 14:41 | 2020-07-08 14:41 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 6.5 |  | Attorney Writes Operating Agreement |  | 2020-07-09 14:41 | 2020-07-09 14:41 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 6.6 |  | Attorney Writes Sales Contract |  | 2020-07-10 14:41 | 2020-07-10 14:41 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 6.7 |  | Meet with Accountant |  | 2020-07-13 14:41 | 2020-07-13 14:41 |  | 100 | 8 | 0 | 0 | Done | Medium |  | 0 | 0
| 6.8 |  | Print Business Cards |  | 2020-07-13 14:41 | 2020-07-13 14:41 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 6.9 |  | Create Website |  | 2020-07-13 14:41 | 2020-07-13 14:41 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 6.10 |  | Create Regional Pay-per-Click Internet Advertising |  | 2020-07-14 14:41 | 2020-07-14 14:41 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 6.11 |  | Print and Distribute Neighborhood Signs |  | 2020-07-15 14:41 | 2020-07-15 14:41 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 6.12 |  | Join Foreclosure Finder Service |  | 2020-07-16 14:41 | 2020-07-16 14:41 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 6.13 |  | Create Property Database |  | 2020-07-17 14:41 | 2020-07-17 14:41 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 6.14 |  | Create Templates for Letter-Writing Campaign |  | 2020-07-20 14:41 | 2020-07-20 14:41 |  | 100 | 8 | 0 | 0 | Done | Medium |  | 0 | 0
| 6.15 |  | Establish Investor Relationships |  | 2020-07-20 14:41 | 2020-07-20 14:41 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 6.16 |  | Establish Mortgage Banker Relationships |  | 2020-07-20 14:41 | 2020-07-20 14:41 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 6.17 |  | Secure Financing for Property |  | 2020-07-21 14:41 | 2020-07-21 14:41 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 6.18 |  | Begin Making Offers |  | 2020-07-22 14:41 | 2020-07-22 14:41 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 6.19 |  | Establish Flat Fee MLS Service Relationship |  | 2020-07-23 14:41 | 2020-07-23 14:41 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 6.20 |  | Open Bank Account |  | 2020-07-24 14:41 | 2020-07-24 14:41 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 6.21 |  | Establish Title Company Relationship |  | 2020-07-27 14:41 | 2020-07-27 14:41 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 6.22 |  | Put Property |  | 2020-07-27 14:41 | 2020-07-27 14:41 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 6.23 |  | Under Contract & Open Escrow |  | 2020-07-27 14:41 | 2020-07-27 14:41 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 6.24 |  | Property Inspection |  | 2020-07-28 14:41 | 2020-07-28 14:41 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 6.25 |  | Contractor Bids for Rehab |  | 2020-07-29 14:41 | 2020-07-29 14:41 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 6.26 |  | Assign Contract or Close Escrow |  | 2020-07-30 14:41 | 2020-07-30 14:41 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 6.27 |  | Rehab Property |  | 2020-07-31 14:41 | 2020-07-31 14:41 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 6.28 |  | Market, Sell & Close Escrow on Property |  | 2020-08-03 14:41 | 2020-08-03 14:41 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 6.29 |  | Search for Property |  | 2020-08-03 14:41 | 2020-08-03 14:41 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 7 | Financial Plan |  |  | 2020-08-04 14:41 | 2020-08-13 14:41 |  | 0 | 64 | 0 | 0 |  |  |  | 0 | 0
| 7.1 |  | Important Assumptions |  | 2020-08-04 14:41 | 2020-08-04 14:41 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 7.2 |  | Exit Strategy |  | 2020-08-05 14:41 | 2020-08-05 14:41 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 7.3 |  | Sales Forecast |  | 2020-08-06 14:41 | 2020-08-06 14:41 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 7.4 |  | Net Profits from Buying and Selling Properties |  | 2020-08-07 14:41 | 2020-08-07 14:41 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 7.5 |  | Net Profits from Rental Property |  | 2020-08-10 14:41 | 2020-08-10 14:41 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 7.6 |  | Rental Property Income |  | 2020-08-10 14:41 | 2020-08-10 14:41 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 7.7 |  | Personnel Plan |  | 2020-08-10 14:41 | 2020-08-10 14:41 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 7.8 |  | Projected Profit and Loss |  | 2020-08-11 14:41 | 2020-08-11 14:41 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 7.9 |  | Projected Cash Flow |  | 2020-08-12 14:41 | 2020-08-12 14:41 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 7.10 |  | Projected Balance Sheet |  | 2020-08-13 14:41 | 2020-08-13 14:41 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
This document has been created with the help of https://ganttpro.com online service
You are free to use the document for your purposes with no limitations. To edit it, please, create a copy or use https://ganttpro.com