## Book Marketing Plan
Create professional Gantt charts in GanttPRO in a few clicks
Book Marketing Plan | [8 empty] | 2020-06-16 14:58
Color | WBS Number |  |  | Task name / Title | Assigned to | Planned start date | Planned end date | Deadline | Progress (%) | Duration (hours) | Estimated hours | Time log (minutes) | Status | Priority | Task description | Cost | Actual cost
| 1 | Market analysis before the start |  |  |  | 2020-06-17 14:58 | 2020-06-20 14:58 |  | 0 | 24 | 0 | 0 |  |  |  | 0 | 0
| 1.1 |  | Competitors analysis |  |  | 2020-06-17 14:58 | 2020-06-18 14:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 1.2 |  | SWOT analysis |  |  | 2020-06-18 14:58 | 2020-06-19 14:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 1.3 |  | Target audience analysis |  |  | 2020-06-19 14:58 | 2020-06-20 14:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 2 | Digital marketing plan |  |  |  | 2020-06-22 14:58 | 2020-08-11 14:58 |  | 0 | 288 | 0 | 0 |  |  |  | 0 | 0
| 2.1 |  | WEBSITE |  |  | 2020-06-22 14:58 | 2020-06-29 14:58 |  | 0 | 40 | 0 | 0 |  |  |  | 0 | 0
| 2.1.1 |  |  | Email list signup |  | 2020-06-22 14:58 | 2020-06-23 14:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.1.2 |  |  | Author bio |  | 2020-06-23 14:58 | 2020-06-24 14:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.1.3 |  |  | Speaking page |  | 2020-06-24 14:58 | 2020-06-25 14:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.1.4 |  |  | Book page |  | 2020-06-25 14:58 | 2020-06-26 14:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.1.5 |  |  | Blog |  | 2020-06-26 14:58 | 2020-06-27 14:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.1.6 |  |  | Evergreen content |  | 2020-06-27 14:58 | 2020-06-28 14:58 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.1.7 |  |  | Links to social media |  | 2020-06-28 14:58 | 2020-06-29 14:58 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.2 |  | SOCIAL MEDIA |  |  | 2020-06-30 14:58 | 2020-07-05 14:58 |  | 0 | 32 | 0 | 0 |  |  |  | 0 | 0
| 2.2.1 |  |  | Facebook Page |  | 2020-06-30 14:58 | 2020-07-01 14:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.2.2 |  |  | Twitter |  | 2020-07-01 14:58 | 2020-07-02 14:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.2.3 |  |  | LinkedIn |  | 2020-07-02 14:58 | 2020-07-03 14:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.2.4 |  |  | Pinterest |  | 2020-07-03 14:58 | 2020-07-04 14:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.2.5 |  |  | YouTube |  | 2020-07-04 14:58 | 2020-07-05 14:58 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.3 |  | EMAIL MARKETING |  |  | 2020-07-06 14:58 | 2020-07-09 14:58 |  | 0 | 24 | 0 | 0 |  |  |  | 0 | 0
| 2.3.1 |  |  | Automated emails |  | 2020-07-06 14:58 | 2020-07-07 14:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.3.2 |  |  | Email list sign-up |  | 2020-07-07 14:58 | 2020-07-08 14:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.3.3 |  |  | Custom template |  | 2020-07-08 14:58 | 2020-07-09 14:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.4 |  | PODCASTING |  |  | 2020-07-10 14:58 | 2020-07-12 14:58 |  | 0 | 8 | 0 | 0 |  |  |  | 0 | 0
| 2.4.1 |  |  | Create podcast episodes |  | 2020-07-10 14:58 | 2020-07-11 14:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.4.2 |  |  | Add you podcast on iTunes |  | 2020-07-11 14:58 | 2020-07-12 14:58 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.5 |  | AMAZON PRESENCE |  |  | 2020-07-13 14:58 | 2020-07-20 14:58 |  | 0 | 40 | 0 | 0 |  |  |  | 0 | 0
| 2.5.1 |  |  | Book page |  | 2020-07-13 14:58 | 2020-07-14 14:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.5.2 |  |  | Product description |  | 2020-07-14 14:58 | 2020-07-15 14:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.5.3 |  |  | Endorsements and reviews |  | 2020-07-15 14:58 | 2020-07-16 14:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.5.4 |  |  | Author page |  | 2020-07-16 14:58 | 2020-07-17 14:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.5.5 |  |  | Author bio |  | 2020-07-17 14:58 | 2020-07-18 14:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.5.6 |  |  | Blog and Twitter feeds (linked) |  | 2020-07-18 14:58 | 2020-07-19 14:58 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.5.7 |  |  | Videos |  | 2020-07-19 14:58 | 2020-07-20 14:58 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.6 |  | BOOK TRAILER |  |  | 2020-07-21 14:58 | 2020-07-24 14:58 |  | 0 | 24 | 0 | 0 |  |  |  | 0 | 0
| 2.6.1 |  |  | Script |  | 2020-07-21 14:58 | 2020-07-22 14:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.6.2 |  |  | Production |  | 2020-07-22 14:58 | 2020-07-23 14:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.6.3 |  |  | Post production |  | 2020-07-23 14:58 | 2020-07-24 14:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.7 |  | MEDIA OUTREACH |  |  | 2020-07-25 14:58 | 2020-07-29 14:58 |  | 0 | 16 | 0 | 0 |  |  |  | 0 | 0
| 2.7.1 |  |  | Media list |  | 2020-07-25 14:58 | 2020-07-26 14:58 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.7.2 |  |  | List of pitches and angles |  | 2020-07-26 14:58 | 2020-07-27 14:58 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.7.3 |  |  | Email templates for outreach |  | 2020-07-27 14:58 | 2020-07-28 14:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.7.4 |  |  | Spreadsheet for tracking outreach results |  | 2020-07-28 14:58 | 2020-07-29 14:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.8 |  | PAID ADVERTISING |  |  | 2020-07-30 14:58 | 2020-08-05 14:58 |  | 0 | 32 | 0 | 0 |  |  |  | 0 | 0
| 2.8.1 |  |  | Google Adwords |  | 2020-07-30 14:58 | 2020-07-31 14:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.8.2 |  |  | Facebook ads |  | 2020-07-31 14:58 | 2020-08-01 14:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.8.3 |  |  | LinkedIn ads |  | 2020-08-01 14:58 | 2020-08-02 14:58 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.8.4 |  |  | Instagram ads |  | 2020-08-02 14:58 | 2020-08-03 14:58 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.8.5 |  |  | StumbleUpon ads |  | 2020-08-03 14:58 | 2020-08-04 14:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.8.6 |  |  | Book aggregators |  | 2020-08-04 14:58 | 2020-08-05 14:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.9 |  | ONLINE BOOK TOUR |  |  | 2020-08-06 14:58 | 2020-08-11 14:58 |  | 0 | 24 | 0 | 0 |  |  |  | 0 | 0
| 2.9.1 |  |  | Interviews on podcasts and blogs |  | 2020-08-06 14:58 | 2020-08-07 14:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.9.2 |  |  | Guest posts |  | 2020-08-07 14:58 | 2020-08-08 14:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.9.3 |  |  | Live chats |  | 2020-08-08 14:58 | 2020-08-09 14:58 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.9.4 |  |  | Webinars |  | 2020-08-09 14:58 | 2020-08-10 14:58 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.9.5 |  |  | Lections |  | 2020-08-10 14:58 | 2020-08-11 14:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 3 | Offline marketing |  |  |  | 2020-08-13 14:58 | 2020-08-29 14:58 |  | 0 | 96 | 0 | 0 |  |  |  | 0 | 0
| 3.1 |  | LOCAL OPPORTUNITIES |  |  | 2020-08-13 14:58 | 2020-08-17 14:58 |  | 0 | 16 | 0 | 0 |  |  |  | 0 | 0
| 3.1.1 |  |  | Bookstores |  | 2020-08-13 14:58 | 2020-08-14 14:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 3.1.2 |  |  | Groups, clubs, associations |  | 2020-08-14 14:58 | 2020-08-15 14:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 3.1.3 |  |  | Newspapers, TV, radio, etc. |  | 2020-08-15 14:58 | 2020-08-16 14:58 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 3.1.4 |  |  | Schools, universities, etc. |  | 2020-08-16 14:58 | 2020-08-17 14:58 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 3.2 |  | LIVE EVENTS |  |  | 2020-08-18 14:58 | 2020-08-20 14:58 |  | 0 | 16 | 0 | 0 |  |  |  | 0 | 0
| 3.2.1 |  |  | Speak at conferences, conventions, and festivals |  | 2020-08-18 14:58 | 2020-08-19 14:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 3.2.2 |  |  | Host events at conferences, conventions, and festivals |  | 2020-08-19 14:58 | 2020-08-20 14:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 3.3 |  | MEET WITH READERS |  |  | 2020-08-21 14:58 | 2020-08-24 14:58 |  | 0 | 8 | 0 | 0 |  |  |  | 0 | 0
| 3.3.1 |  |  | Choose the right locations for events |  | 2020-08-21 14:58 | 2020-08-22 14:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 3.3.2 |  |  | Make connections and set dates |  | 2020-08-22 14:58 | 2020-08-23 14:58 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 3.3.3 |  |  | Pre-plan and book your travel itinerary |  | 2020-08-23 14:58 | 2020-08-24 14:58 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 3.4 |  | ADVERTISING |  |  | 2020-08-25 14:58 | 2020-08-29 14:58 |  | 0 | 32 | 0 | 0 |  |  |  | 0 | 0
| 3.4.1 |  |  | Advertising on magazines |  | 2020-08-25 14:58 | 2020-08-26 14:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 3.4.2 |  |  | Advertising in book shop |  | 2020-08-26 14:58 | 2020-08-27 14:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 3.4.3 |  |  | Brochures/flyers |  | 2020-08-27 14:58 | 2020-08-28 14:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 3.4.4 |  |  | Newspapers, TV, radio, etc. |  | 2020-08-28 14:58 | 2020-08-29 14:58 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
This document has been created with the help of https://ganttpro.com online service
You are free to use the document for your purposes with no limitations. To edit it, please, create a copy or use https://ganttpro.com