## Event Marketing
Create professional Gantt charts in GanttPRO in a few clicks
Event Marketing | [7 empty] | 2020-06-17 15:05
Color | WBS Number |  | Task name / Title | Assigned to | Planned start date | Planned end date | Deadline | Progress (%) | Duration (hours) | Estimated hours | Time log (minutes) | Status | Priority | Task description | Cost | Actual cost
| 1 | National Marketing |  |  | 2020-06-18 15:05 | 2020-06-24 15:05 |  | 0 | 40 | 0 | 0 |  |  |  | 0 | 0
| 1.1 |  | Banner Ads |  | 2020-06-18 15:05 | 2020-06-23 15:05 |  | 0 | 32 | 0 | 0 | Open | Medium |  | 0 | 0
| 1.2 |  | Radio |  | 2020-06-21 15:05 | 2020-06-24 15:05 |  | 0 | 32 | 0 | 0 | Open | Medium |  | 0 | 0
| 2 | Local Marketing |  |  | 2020-06-23 15:05 | 2020-06-28 15:05 |  | 0 | 32 | 0 | 0 |  |  |  | 0 | 0
| 2.1 |  | Newspaper |  | 2020-06-23 15:05 | 2020-06-28 15:05 |  | 0 | 32 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.2 |  | In-Store Marketing |  | 2020-06-23 15:05 | 2020-06-28 15:05 |  | 0 | 32 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.3 |  | POP |  | 2020-06-23 15:05 | 2020-06-28 15:05 |  | 0 | 32 | 0 | 0 | Open | Medium |  | 0 | 0
| 3 | Public Relations |  |  | 2020-06-25 15:05 | 2020-07-06 15:05 |  | 0 | 64 | 0 | 0 |  |  |  | 0 | 0
| 3.1 |  | Public Events |  | 2020-06-25 15:05 | 2020-07-01 15:05 |  | 0 | 40 | 0 | 0 | Open | Medium |  | 0 | 0
| 3.2 |  | Sponsorships |  | 2020-06-28 15:05 | 2020-07-02 15:05 |  | 0 | 40 | 0 | 0 | Open | Medium |  | 0 | 0
| 3.3 |  | Press Releases |  | 2020-06-29 15:05 | 2020-07-05 15:05 |  | 0 | 40 | 0 | 0 | Open | Medium |  | 0 | 0
| 3.4 |  | Webinars |  | 2020-06-30 15:05 | 2020-07-06 15:05 |  | 0 | 40 | 0 | 0 | Open | Medium |  | 0 | 0
| 3.5 |  | Conferences |  | 2020-06-30 15:05 | 2020-07-06 15:05 |  | 0 | 40 | 0 | 0 | Open | Medium |  | 0 | 0
| 3.6 |  | Client Events |  | 2020-06-30 15:05 | 2020-07-06 15:05 |  | 0 | 40 | 0 | 0 | Open | Medium |  | 0 | 0
| 4 | Content Marketing |  |  | 2020-07-02 15:05 | 2020-07-12 15:05 |  | 0 | 56 | 0 | 0 |  |  |  | 0 | 0
| 4.1 |  | Sponsored Content |  | 2020-07-02 15:05 | 2020-07-08 15:05 |  | 0 | 40 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.2 |  | Landing Page |  | 2020-07-05 15:05 | 2020-07-09 15:05 |  | 0 | 40 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.3 |  | White Papers / ebooks |  | 2020-07-06 15:05 | 2020-07-12 15:05 |  | 0 | 40 | 0 | 0 | Open | Medium |  | 0 | 0
| 5 | Social Media |  |  | 2020-07-07 15:05 | 2020-07-15 15:05 |  | 0 | 56 | 0 | 0 |  |  |  | 0 | 0
| 5.1 |  | Twitter |  | 2020-07-07 15:05 | 2020-07-12 15:05 |  | 0 | 32 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.2 |  | Facebook |  | 2020-07-07 15:05 | 2020-07-12 15:05 |  | 0 | 32 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.3 |  | VK |  | 2020-07-08 15:05 | 2020-07-13 15:05 |  | 0 | 32 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.4 |  | Instagram |  | 2020-07-09 15:05 | 2020-07-14 15:05 |  | 0 | 32 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.5 |  | LinkedIn |  | 2020-07-12 15:05 | 2020-07-15 15:05 |  | 0 | 32 | 0 | 0 | Open | Medium |  | 0 | 0
| 6 | Online |  |  | 2020-07-14 15:05 | 2020-07-22 15:05 |  | 0 | 56 | 0 | 0 |  |  |  | 0 | 0
| 6.1 |  | Blog |  | 2020-07-14 15:05 | 2020-07-19 15:05 |  | 0 | 32 | 0 | 0 | Open | Medium |  | 0 | 0
| 6.2 |  | Website |  | 2020-07-14 15:05 | 2020-07-19 15:05 |  | 0 | 32 | 0 | 0 | Open | Medium |  | 0 | 0
| 6.3 |  | Mobile App |  | 2020-07-15 15:05 | 2020-07-20 15:05 |  | 0 | 32 | 0 | 0 | Open | Medium |  | 0 | 0
| 6.4 |  | Mobile Alerts |  | 2020-07-16 15:05 | 2020-07-21 15:05 |  | 0 | 32 | 0 | 0 | Open | Medium |  | 0 | 0
| 6.5 |  | Email Newsletter |  | 2020-07-19 15:05 | 2020-07-22 15:05 |  | 0 | 32 | 0 | 0 | Open | Medium |  | 0 | 0
| 7 | Advertising |  |  | 2020-07-21 15:05 | 2020-07-28 15:05 |  | 0 | 48 | 0 | 0 |  |  |  | 0 | 0
| 7.1 |  | Online |  | 2020-07-21 15:05 | 2020-07-26 15:05 |  | 0 | 32 | 0 | 0 | Open | Medium |  | 0 | 0
| 7.2 |  | Print |  | 2020-07-21 15:05 | 2020-07-26 15:05 |  | 0 | 32 | 0 | 0 | Open | Medium |  | 0 | 0
| 7.3 |  | Outdoor |  | 2020-07-21 15:05 | 2020-07-26 15:05 |  | 0 | 32 | 0 | 0 | Open | Medium |  | 0 | 0
| 7.4 |  | Radio |  | 2020-07-22 15:05 | 2020-07-27 15:05 |  | 0 | 32 | 0 | 0 | Open | Medium |  | 0 | 0
| 7.5 |  | Television |  | 2020-07-23 15:05 | 2020-07-28 15:05 |  | 0 | 32 | 0 | 0 | Open | Medium |  | 0 | 0
| 8 | Web |  |  | 2020-07-27 15:05 | 2020-08-05 15:05 |  | 0 | 64 | 0 | 0 |  |  |  | 0 | 0
| 8.1 |  | Development |  | 2020-07-27 15:05 | 2020-08-05 15:05 |  | 0 | 64 | 0 | 0 | Open | Medium |  | 0 | 0
| 8.2 |  | Pay-Per-Click Marketing |  | 2020-07-28 15:05 | 2020-08-05 15:05 |  | 0 | 56 | 0 | 0 | Open | Medium |  | 0 | 0
| 8.3 |  | SEO |  | 2020-07-28 15:05 | 2020-08-05 15:05 |  | 0 | 56 | 0 | 0 | Open | Medium |  | 0 | 0
| 9 | Market Research |  |  | 2020-07-29 15:05 | 2020-08-05 15:05 |  | 0 | 48 | 0 | 0 |  |  |  | 0 | 0
| 9.1 |  | Surveys |  | 2020-07-29 15:05 | 2020-08-04 15:05 |  | 0 | 40 | 0 | 0 | Open | Medium |  | 0 | 0
| 9.2 |  | Impact Studies |  | 2020-07-30 15:05 | 2020-08-05 15:05 |  | 0 | 40 | 0 | 0 | Open | Medium |  | 0 | 0
| 10 | Sales Campaigns |  |  | 2020-08-03 15:05 | 2020-08-12 15:05 |  | 0 | 64 | 0 | 0 |  |  |  | 0 | 0
| 10.1 |  | Campaign A |  | 2020-08-03 15:05 | 2020-08-09 15:05 |  | 0 | 40 | 0 | 0 | Open | Medium |  | 0 | 0
| 10.2 |  | Campaign B |  | 2020-08-04 15:05 | 2020-08-10 15:05 |  | 0 | 40 | 0 | 0 | Open | Medium |  | 0 | 0
| 10.3 |  | Campaign C |  | 2020-08-04 15:05 | 2020-08-10 15:05 |  | 0 | 40 | 0 | 0 | Open | Medium |  | 0 | 0
| 10.4 |  | Campaign D |  | 2020-08-04 15:05 | 2020-08-11 15:05 |  | 0 | 48 | 0 | 0 | Open | Medium |  | 0 | 0
| 10.5 |  | Campaign E |  | 2020-08-05 15:05 | 2020-08-12 15:05 |  | 0 | 48 | 0 | 0 | Open | Medium |  | 0 | 0
This document has been created with the help of https://ganttpro.com online service
You are free to use the document for your purposes with no limitations. To edit it, please, create a copy or use https://ganttpro.com