## Law Firm Marketing Plan
Create professional Gantt charts in GanttPRO in a few clicks
Law Firm Marketing Plan | [8 empty] | 2020-06-18 15:04
Color | WBS Number |  |  | Task name / Title | Assigned to | Planned start date | Planned end date | Deadline | Progress (%) | Duration (hours) | Estimated hours | Time log (minutes) | Status | Priority | Task description | Cost | Actual cost
| 1 | Executive Summary |  |  |  | 2020-06-19 15:04 | 2020-06-23 15:04 |  | 0 | 24 | 0 | 0 | Open | Medium |  | 0 | 0
| 2 | Target Audience |  |  |  | 2020-06-21 15:04 | 2020-06-29 15:04 |  | 0 | 48 | 0 | 0 |  |  |  | 0 | 0
| 2.1 |  | Identify ideal client personas |  |  | 2020-06-21 15:04 | 2020-06-23 15:04 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.2 |  | Put clients into groups |  |  | 2020-06-24 15:04 | 2020-06-25 15:04 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.3 |  | Match up each group |  |  | 2020-06-26 15:04 | 2020-06-29 15:04 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 3 | Value Proposition (Unique Selling Point) |  |  |  | 2020-06-28 15:04 | 2020-07-03 15:04 |  | 0 | 40 | 0 | 0 |  |  |  | 0 | 0
| 3.1 |  | Differentiate your firm from competitors |  |  | 2020-06-28 15:04 | 2020-06-30 15:04 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 3.2 |  | Identify threats |  |  | 2020-06-30 15:04 | 2020-07-01 15:04 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 3.3 |  | Describe your strength |  |  | 2020-07-02 15:04 | 2020-07-03 15:04 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 4 | Market Positioning Statement |  |  |  | 2020-07-04 15:04 | 2020-07-07 15:04 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 5 | Services & Pricing Strategy |  |  |  | 2020-07-06 15:04 | 2020-07-09 15:04 |  | 0 | 32 | 0 | 0 |  |  |  | 0 | 0
| 5.1 |  | Outline services |  |  | 2020-07-06 15:04 | 2020-07-08 15:04 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.2 |  | Explain pricing |  |  | 2020-07-08 15:04 | 2020-07-09 15:04 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 6 | Promotion Strategy (marketing channels) |  |  |  | 2020-07-11 15:04 | 2020-08-10 15:04 |  | 11 | 160 | 0 | 0 |  |  |  | 0 | 0
| 6.1 |  | Offline channels |  |  | 2020-07-11 15:04 | 2020-07-25 15:04 |  | 0 | 80 | 0 | 0 |  |  |  | 0 | 0
| 6.1.1 |  |  | PR |  | 2020-07-11 15:04 | 2020-07-15 15:04 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 6.1.2 |  |  | TV and Radio |  | 2020-07-15 15:04 | 2020-07-18 15:04 |  | 0 | 24 | 0 | 0 | Open | Medium |  | 0 | 0
| 6.1.3 |  |  | Physical/Print Advertising |  | 2020-07-18 15:04 | 2020-07-21 15:04 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 6.1.4 |  |  | Events & Seminars |  | 2020-07-21 15:04 | 2020-07-25 15:04 |  | 0 | 32 | 0 | 0 | Open | Medium |  | 0 | 0
| 6.2 |  | Online channels |  |  | 2020-07-25 15:04 | 2020-08-10 15:04 |  | 21 | 80 | 0 | 0 |  |  |  | 0 | 0
| 6.2.1 |  |  | Content Marketing |  | 2020-07-25 15:04 | 2020-08-10 15:04 |  | 0 | 80 | 0 | 0 | Open | Medium |  | 0 | 0
| 6.2.2 |  |  | PPC Advertising |  | 2020-07-28 15:04 | 2020-07-30 15:04 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 6.2.3 |  |  | SEO |  | 2020-07-25 15:04 | 2020-08-10 15:04 |  | 0 | 80 | 0 | 0 | Open | Medium |  | 0 | 0
| 6.2.4 |  |  | Social Media & Email Marketing |  | 2020-07-25 15:04 | 2020-08-03 15:04 |  | 100 | 48 | 0 | 0 | Done | Medium |  | 0 | 0
| 7 | Conversion Strategy |  |  |  | 2020-08-11 15:04 | 2020-08-25 15:04 |  | 0 | 80 | 0 | 0 |  |  |  | 0 | 0
| 7.1 |  | Define approach to outreach |  |  | 2020-08-11 15:04 | 2020-08-13 15:04 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 7.2 |  | Lead nurturing |  |  | 2020-08-13 15:04 | 2020-08-15 15:04 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 7.3 |  | Follow up |  |  | 2020-08-15 15:04 | 2020-08-18 15:04 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 7.4 |  | Consultations |  |  | 2020-08-18 15:04 | 2020-08-21 15:04 |  | 0 | 24 | 0 | 0 | Open | Medium |  | 0 | 0
| 7.5 |  | Other activities |  |  | 2020-08-21 15:04 | 2020-08-25 15:04 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 8 | Referral & Retention Strategy |  |  |  | 2020-08-25 15:04 | 2020-09-10 15:04 |  | 0 | 96 | 0 | 0 | Open | Medium |  | 0 | 0
| 9 | Budgets & Financial Projections |  |  |  | 2020-09-11 15:04 | 2020-09-22 15:04 |  | 0 | 64 | 0 | 0 |  |  |  | 0 | 0
| 9.1 |  | Total marketing spent |  |  | 2020-09-11 15:04 | 2020-09-14 15:04 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 9.2 |  | Total leads generated |  |  | 2020-09-12 15:04 | 2020-09-15 15:04 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 9.3 |  | Conversion rate |  |  | 2020-09-14 15:04 | 2020-09-16 15:04 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 9.4 |  | Average client acquisition cost |  |  | 2020-09-16 15:04 | 2020-09-17 15:04 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 9.5 |  | Average revenue per client |  |  | 2020-09-17 15:04 | 2020-09-19 15:04 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 9.6 |  | Total ROI |  |  | 2020-09-19 15:04 | 2020-09-22 15:04 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
This document has been created with the help of https://ganttpro.com online service
You are free to use the document for your purposes with no limitations. To edit it, please, create a copy or use https://ganttpro.com