## marketing-proposal-template
Create professional Gantt charts in GanttPRO in a few clicks
marketing-proposal-template | [8 empty] | 2020-11-20 14:12
Color | WBS Number |  |  | Task name / Title | Assigned to | Planned start date | Planned end date | Deadline | Progress (%) | Duration (hours) | Estimated hours | Time log (minutes) | Status | Priority | Task description | Cost | Actual cost
| 1 | ANALYSIS AND STRATEGY |  |  |  | 2020-11-21 14:12 | 2020-11-28 14:12 |  | 0 | 40 | 0 | 0 |  |  |  | 0 | 0
| 1.1 |  | COMPANY DEFINED |  |  | 2020-11-21 14:12 | 2020-11-22 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 1.2 |  | YOUR MISSION |  |  | 2020-11-22 14:12 | 2020-11-23 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 1.3 |  | YOUR VISION |  |  | 2020-11-23 14:12 | 2020-11-23 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 1.4 |  | TARGET AUDIENCE |  |  | 2020-11-26 14:12 | 2020-11-26 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 1.5 |  | YOUR MESSAGE |  |  | 2020-11-26 14:12 | 2020-11-26 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 1.6 |  | STRENGTHS DEFINED |  |  | 2020-11-26 14:12 | 2020-11-27 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 1.7 |  | WEAKNESSES DEFINED |  |  | 2020-11-27 14:12 | 2020-11-28 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 2 | SOCIAL MEDIA MARKETING (BUDGET) |  |  |  | 2020-11-29 14:12 | 2020-12-10 14:12 |  | 0 | 64 | 0 | 0 |  |  |  | 0 | 0
| 2.1 |  | HUMAN RESOURCES - COST |  |  | 2020-11-29 14:12 | 2020-11-30 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.2 |  | ADVERTISING |  |  | 2020-11-30 14:12 | 2020-11-30 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.3 |  | PROMOTIONS |  |  | 2020-12-03 14:12 | 2020-12-03 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.4 |  | AGENCY FEES / RETAINER |  |  | 2020-12-03 14:12 | 2020-12-03 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.5 |  | CONTENT CREATION |  |  | 2020-12-04 14:12 | 2020-12-05 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.6 |  | CONTENT MANAGEMENT |  |  | 2020-12-05 14:12 | 2020-12-06 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.7 |  | LICENSED CONTENT |  |  | 2020-12-06 14:12 | 2020-12-07 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.8 |  | SOFTWARE LICENSES |  |  | 2020-12-07 14:12 | 2020-12-07 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.9 |  | GRAPHIC DESIGN |  |  | 2020-12-10 14:12 | 2020-12-10 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.10 |  | VIDEO PRODUCTION |  |  | 2020-12-10 14:12 | 2020-12-10 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 3 | COMPETITIVE ANALYSIS |  |  |  | 2020-12-11 14:12 | 2020-12-17 14:12 |  | 0 | 40 | 0 | 0 |  |  |  | 0 | 0
| 3.1 |  | YOUR COMPANY'S COMPETITIVE EDGE |  |  | 2020-12-11 14:12 | 2020-12-12 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 3.2 |  | COMPETITION DEFINED |  |  | 2020-12-12 14:12 | 2020-12-13 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 3.3 |  | COMPETITION STRENGTHS |  |  | 2020-12-13 14:12 | 2020-12-14 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 3.4 |  | WHAT YOUR COMPANY CAN DO DIFFERENTLY |  |  | 2020-12-14 14:12 | 2020-12-14 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 3.5 |  | POTENTIAL ROADBLOCKS |  |  | 2020-12-17 14:12 | 2020-12-17 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 3.6 |  | BENEFITS |  |  | 2020-12-17 14:12 | 2020-12-17 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 4 | PLAN BUILDING |  |  |  | 2020-12-18 14:12 | 2020-12-25 14:12 |  | 0 | 40 | 0 | 0 |  |  |  | 0 | 0
| 4.1 |  | JOURNALISTS |  |  | 2020-12-18 14:12 | 2020-12-19 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.2 |  | BLOGGERS |  |  | 2020-12-19 14:12 | 2020-12-20 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.3 |  | SOCIAL MEDIA INFLUENCERS |  |  | 2020-12-20 14:12 | 2020-12-21 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.4 |  | SOCIAL MEDIA INTERACTORS |  |  | 2020-12-21 14:12 | 2020-12-21 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.5 |  | PEERS AND PARTNERS |  |  | 2020-12-24 14:12 | 2020-12-24 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.6 |  | CROSS PROMOTIONS |  |  | 2020-12-24 14:12 | 2020-12-24 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.7 |  | OTHER |  |  | 2020-12-24 14:12 | 2020-12-25 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5 | SOCIAL MEDIA AUDIT |  |  |  | 2020-12-28 14:12 | 2021-06-05 14:12 |  | 0 | 904 | 0 | 0 |  |  |  | 0 | 0
| 5.1 |  | FACEBOOK |  |  | 2020-12-28 14:12 | 2021-01-11 14:12 |  | 0 | 88 | 0 | 0 |  |  |  | 0 | 0
| 5.1.1 |  |  | LINK |  | 2020-12-28 14:12 | 2020-12-28 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.1.2 |  |  | PROFILE NAME |  | 2020-12-31 14:12 | 2020-12-31 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.1.3 |  |  | FOLLOWERS |  | 2020-12-31 14:12 | 2020-12-31 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.1.4 |  |  | DATE OF LAST ACTIVITY |  | 2020-12-31 14:12 | 2021-01-01 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.1.5 |  |  | FREQUENCY OF POSTS |  | 2021-01-01 14:12 | 2021-01-02 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.1.6 |  |  | MONTLY REFERRAL TRAFFIC |  | 2021-01-02 14:12 | 2021-01-03 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.1.7 |  |  | % OF CHANGE (LAST YEAR) |  | 2021-01-03 14:12 | 2021-01-04 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.1.8 |  |  | % OF CHANGE (LAST MONTH) |  | 2021-01-04 14:12 | 2021-01-04 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.1.9 |  |  | CLICKS PER POST |  | 2021-01-07 14:12 | 2021-01-07 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.1.10 |  |  | CLICKS PER POST (LAST MONTH) |  | 2021-01-07 14:12 | 2021-01-07 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.1.11 |  |  | CLICKS PER POST CHANGE |  | 2021-01-07 14:12 | 2021-01-08 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.1.12 |  |  | FACEBOOK REACH |  | 2021-01-08 14:12 | 2021-01-09 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.1.13 |  |  | FOLLOWERS (TODAY) |  | 2021-01-09 14:12 | 2021-01-10 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.1.14 |  |  | FOLLOWERS (LAST MONTH) |  | 2021-01-10 14:12 | 2021-01-11 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.1.15 |  |  | FOLLOWERS CHANGE |  | 2021-01-11 14:12 | 2021-01-11 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.2 |  | INSTAGRAM |  |  | 2021-01-14 14:12 | 2021-01-28 14:12 |  | 0 | 88 | 0 | 0 |  |  |  | 0 | 0
| 5.2.1 |  |  | LINK |  | 2021-01-14 14:12 | 2021-01-14 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.2.2 |  |  | PROFILE NAME |  | 2021-01-14 14:12 | 2021-01-15 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.2.3 |  |  | FOLLOWERS |  | 2021-01-15 14:12 | 2021-01-16 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.2.4 |  |  | DATE OF LAST ACTIVITY |  | 2021-01-16 14:12 | 2021-01-17 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.2.5 |  |  | FREQUENCY OF POSTS |  | 2021-01-17 14:12 | 2021-01-18 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.2.6 |  |  | MONTLY REFERRAL TRAFFIC |  | 2021-01-18 14:12 | 2021-01-18 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.2.7 |  |  | % OF CHANGE (LAST YEAR) |  | 2021-01-21 14:12 | 2021-01-21 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.2.8 |  |  | % OF CHANGE (LAST MONTH) |  | 2021-01-21 14:12 | 2021-01-21 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.2.9 |  |  | CLICKS PER POST |  | 2021-01-21 14:12 | 2021-01-22 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.2.10 |  |  | CLICKS PER POST (LAST MONTH) |  | 2021-01-22 14:12 | 2021-01-23 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.2.11 |  |  | CLICKS PER POST CHANGE |  | 2021-01-23 14:12 | 2021-01-24 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.2.12 |  |  | FOLLOWERS (TODAY) |  | 2021-01-25 14:12 | 2021-01-25 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.2.13 |  |  | FOLLOWERS (LAST MONTH) |  | 2021-01-28 14:12 | 2021-01-28 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.2.14 |  |  | FOLLOWERS CHANGE |  | 2021-01-28 14:12 | 2021-01-28 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.3 |  | TWITTER |  |  | 2021-01-29 14:12 | 2021-02-13 14:12 |  | 0 | 88 | 0 | 0 |  |  |  | 0 | 0
| 5.3.1 |  |  | LINK |  | 2021-01-29 14:12 | 2021-01-30 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.3.2 |  |  | PROFILE NAME |  | 2021-01-30 14:12 | 2021-01-31 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.3.3 |  |  | FOLLOWERS |  | 2021-01-31 14:12 | 2021-02-01 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.3.4 |  |  | DATE OF LAST ACTIVITY |  | 2021-02-01 14:12 | 2021-02-01 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.3.5 |  |  | FREQUENCY OF POSTS |  | 2021-02-04 14:12 | 2021-02-04 14:12 |  | 0 | 1 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.3.6 |  |  | MONTLY REFERRAL TRAFFIC |  | 2021-02-04 14:12 | 2021-02-04 14:12 |  | 0 | 1 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.3.7 |  |  | % OF CHANGE (LAST YEAR) |  | 2021-02-04 14:12 | 2021-02-05 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.3.8 |  |  | % OF CHANGE (LAST MONTH) |  | 2021-02-05 14:12 | 2021-02-06 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.3.9 |  |  | CLICKS PER POST |  | 2021-02-06 14:12 | 2021-02-07 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.3.10 |  |  | CLICKS PER POST (LAST MONTH) |  | 2021-02-07 14:12 | 2021-02-08 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.3.11 |  |  | CLICKS PER POST CHANGE |  | 2021-02-08 14:12 | 2021-02-08 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.3.12 |  |  | FOLLOWERS (TODAY) |  | 2021-02-11 14:12 | 2021-02-11 14:12 |  | 0 | 1 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.3.13 |  |  | FOLLOWERS (LAST MONTH) |  | 2021-02-11 14:12 | 2021-02-12 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.3.14 |  |  | FOLLOWERS CHANGE |  | 2021-02-12 14:12 | 2021-02-13 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.4 |  | LINKEDIN |  |  | 2021-02-14 14:12 | 2021-03-01 14:12 |  | 0 | 88 | 0 | 0 |  |  |  | 0 | 0
| 5.4.1 |  |  | LINK |  | 2021-02-14 14:12 | 2021-02-15 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.4.2 |  |  | PROFILE NAME |  | 2021-02-15 14:12 | 2021-02-15 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.4.3 |  |  | FOLLOWERS |  | 2021-02-18 14:12 | 2021-02-18 14:12 |  | 0 | 1 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.4.4 |  |  | DATE OF LAST ACTIVITY |  | 2021-02-18 14:12 | 2021-02-18 14:12 |  | 0 | 1 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.4.5 |  |  | FREQUENCY OF POSTS |  | 2021-02-18 14:12 | 2021-02-19 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.4.6 |  |  | MONTLY REFERRAL TRAFFIC |  | 2021-02-19 14:12 | 2021-02-20 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.4.7 |  |  | % OF CHANGE (LAST YEAR) |  | 2021-02-20 14:12 | 2021-02-21 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.4.8 |  |  | % OF CHANGE (LAST MONTH) |  | 2021-02-21 14:12 | 2021-02-22 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.4.9 |  |  | CLICKS PER POST |  | 2021-02-22 14:12 | 2021-02-22 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.4.10 |  |  | CLICKS PER POST (LAST MONTH) |  | 2021-02-25 14:12 | 2021-02-25 14:12 |  | 0 | 1 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.4.11 |  |  | CLICKS PER POST CHANGE |  | 2021-02-25 14:12 | 2021-02-25 14:12 |  | 0 | 1 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.4.12 |  |  | FOLLOWERS (TODAY) |  | 2021-02-26 14:12 | 2021-02-27 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.4.13 |  |  | FOLLOWERS (LAST MONTH) |  | 2021-02-27 14:12 | 2021-02-28 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.4.14 |  |  | FOLLOWERS CHANGE |  | 2021-02-28 14:12 | 2021-03-01 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.5 |  | SNAPCHAT |  |  | 2021-03-18 14:12 | 2021-04-02 14:12 |  | 0 | 88 | 0 | 0 |  |  |  | 0 | 0
| 5.5.1 |  |  | LINK |  | 2021-03-18 14:12 | 2021-03-19 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.5.2 |  |  | PROFILE NAME |  | 2021-03-19 14:12 | 2021-03-20 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.5.3 |  |  | FOLLOWERS |  | 2021-03-20 14:12 | 2021-03-21 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.5.4 |  |  | DATE OF LAST ACTIVITY |  | 2021-03-21 14:12 | 2021-03-22 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.5.5 |  |  | FREQUENCY OF POSTS |  | 2021-03-22 14:12 | 2021-03-22 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.5.6 |  |  | MONTLY REFERRAL TRAFFIC |  | 2021-03-25 14:12 | 2021-03-25 14:12 |  | 0 | 1 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.5.7 |  |  | % OF CHANGE (LAST YEAR) |  | 2021-03-25 14:12 | 2021-03-25 14:12 |  | 0 | 1 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.5.8 |  |  | % OF CHANGE (LAST MONTH) |  | 2021-03-25 14:12 | 2021-03-26 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.5.9 |  |  | CLICKS PER POST |  | 2021-03-26 14:12 | 2021-03-27 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.5.10 |  |  | CLICKS PER POST (LAST MONTH) |  | 2021-03-27 14:12 | 2021-03-28 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.5.11 |  |  | CLICKS PER POST CHANGE |  | 2021-03-28 14:12 | 2021-03-29 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.5.12 |  |  | FOLLOWERS (TODAY) |  | 2021-04-01 14:12 | 2021-04-01 14:12 |  | 0 | 1 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.5.13 |  |  | FOLLOWERS (LAST MONTH) |  | 2021-04-01 14:12 | 2021-04-01 14:12 |  | 0 | 1 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.5.14 |  |  | FOLLOWERS CHANGE |  | 2021-04-01 14:12 | 2021-04-02 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.6 |  | PINTEREST |  |  | 2021-04-03 14:12 | 2021-04-18 14:12 |  | 0 | 88 | 0 | 0 |  |  |  | 0 | 0
| 5.6.1 |  |  | LINK |  | 2021-04-03 14:12 | 2021-04-04 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.6.2 |  |  | PROFILE NAME |  | 2021-04-04 14:12 | 2021-04-05 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.6.3 |  |  | FOLLOWERS |  | 2021-04-05 14:12 | 2021-04-05 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.6.4 |  |  | DATE OF LAST ACTIVITY |  | 2021-04-08 14:12 | 2021-04-08 14:12 |  | 0 | 1 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.6.5 |  |  | FREQUENCY OF POSTS |  | 2021-04-08 14:12 | 2021-04-08 14:12 |  | 0 | 1 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.6.6 |  |  | MONTLY REFERRAL TRAFFIC |  | 2021-04-08 14:12 | 2021-04-09 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.6.7 |  |  | % OF CHANGE (LAST YEAR) |  | 2021-04-09 14:12 | 2021-04-10 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.6.8 |  |  | % OF CHANGE (LAST MONTH) |  | 2021-04-10 14:12 | 2021-04-11 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.6.9 |  |  | CLICKS PER POST |  | 2021-04-11 14:12 | 2021-04-12 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.6.10 |  |  | CLICKS PER POST (LAST MONTH) |  | 2021-04-12 14:12 | 2021-04-12 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.6.11 |  |  | CLICKS PER POST CHANGE |  | 2021-04-15 14:12 | 2021-04-15 14:12 |  | 0 | 1 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.6.12 |  |  | FOLLOWERS (TODAY) |  | 2021-04-15 14:12 | 2021-04-16 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.6.13 |  |  | FOLLOWERS (LAST MONTH) |  | 2021-04-16 14:12 | 2021-04-17 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.6.14 |  |  | FOLLOWERS CHANGE |  | 2021-04-17 14:12 | 2021-04-18 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.7 |  | TUMBLR |  |  | 2021-04-19 14:12 | 2021-05-03 14:12 |  | 0 | 88 | 0 | 0 |  |  |  | 0 | 0
| 5.7.1 |  |  | LINK |  | 2021-04-19 14:12 | 2021-04-19 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.7.2 |  |  | PROFILE NAME |  | 2021-04-22 14:12 | 2021-04-22 14:12 |  | 0 | 1 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.7.3 |  |  | FOLLOWERS |  | 2021-04-22 14:12 | 2021-04-22 14:12 |  | 0 | 1 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.7.4 |  |  | DATE OF LAST ACTIVITY |  | 2021-04-22 14:12 | 2021-04-23 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.7.5 |  |  | FREQUENCY OF POSTS |  | 2021-04-23 14:12 | 2021-04-24 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.7.6 |  |  | MONTLY REFERRAL TRAFFIC |  | 2021-04-24 14:12 | 2021-04-25 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.7.7 |  |  | % OF CHANGE (LAST YEAR) |  | 2021-04-25 14:12 | 2021-04-26 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.7.8 |  |  | % OF CHANGE (LAST MONTH) |  | 2021-04-26 14:12 | 2021-04-26 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.7.9 |  |  | CLICKS PER POST |  | 2021-04-29 14:12 | 2021-04-29 14:12 |  | 0 | 1 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.7.10 |  |  | CLICKS PER POST (LAST MONTH) |  | 2021-04-29 14:12 | 2021-04-29 14:12 |  | 0 | 1 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.7.11 |  |  | CLICKS PER POST CHANGE |  | 2021-04-29 14:12 | 2021-04-30 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.7.12 |  |  | FOLLOWERS (TODAY) |  | 2021-05-01 14:12 | 2021-05-02 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.7.13 |  |  | FOLLOWERS (LAST MONTH) |  | 2021-05-02 14:12 | 2021-05-03 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.7.14 |  |  | FOLLOWERS CHANGE |  | 2021-05-03 14:12 | 2021-05-03 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.8 |  | YOUTUBE |  |  | 2021-05-06 14:12 | 2021-05-20 14:12 |  | 0 | 81 | 0 | 0 |  |  |  | 0 | 0
| 5.8.1 |  |  | LINK |  | 2021-05-06 14:12 | 2021-05-06 14:12 |  | 0 | 1 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.8.2 |  |  | PROFILE NAME |  | 2021-05-06 14:12 | 2021-05-07 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.8.3 |  |  | FOLLOWERS |  | 2021-05-07 14:12 | 2021-05-08 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.8.4 |  |  | DATE OF LAST ACTIVITY |  | 2021-05-08 14:12 | 2021-05-09 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.8.5 |  |  | FREQUENCY OF POSTS |  | 2021-05-09 14:12 | 2021-05-10 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.8.6 |  |  | MONTLY REFERRAL TRAFFIC |  | 2021-05-10 14:12 | 2021-05-10 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.8.7 |  |  | % OF CHANGE (LAST YEAR) |  | 2021-05-13 14:12 | 2021-05-13 14:12 |  | 0 | 1 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.8.8 |  |  | % OF CHANGE (LAST MONTH) |  | 2021-05-13 14:12 | 2021-05-13 14:12 |  | 0 | 1 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.8.9 |  |  | CLICKS PER POST |  | 2021-05-13 14:12 | 2021-05-14 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.8.10 |  |  | CLICKS PER POST (LAST MONTH) |  | 2021-05-14 14:12 | 2021-05-15 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.8.11 |  |  | CLICKS PER POST CHANGE |  | 2021-05-15 14:12 | 2021-05-16 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.8.12 |  |  | FOLLOWERS (TODAY) |  | 2021-05-17 14:12 | 2021-05-17 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.8.13 |  |  | FOLLOWERS (LAST MONTH) |  | 2021-05-20 14:12 | 2021-05-20 14:12 |  | 0 | 1 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.8.14 |  |  | FOLLOWERS CHANGE |  | 2021-05-20 14:12 | 2021-05-20 14:12 |  | 0 | 1 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.9 |  | OTHER |  |  | 2021-05-21 14:12 | 2021-06-05 14:12 |  | 0 | 88 | 0 | 0 |  |  |  | 0 | 0
| 5.9.1 |  |  | LINK |  | 2021-05-21 14:12 | 2021-05-22 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.9.2 |  |  | PROFILE NAME |  | 2021-05-22 14:12 | 2021-05-23 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.9.3 |  |  | FOLLOWERS |  | 2021-05-23 14:12 | 2021-05-24 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.9.4 |  |  | DATE OF LAST ACTIVITY |  | 2021-05-24 14:12 | 2021-05-24 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.9.5 |  |  | FREQUENCY OF POSTS |  | 2021-05-27 14:12 | 2021-05-27 14:12 |  | 0 | 1 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.9.6 |  |  | MONTLY REFERRAL TRAFFIC |  | 2021-05-27 14:12 | 2021-05-27 14:12 |  | 0 | 1 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.9.7 |  |  | % OF CHANGE (LAST YEAR) |  | 2021-05-27 14:12 | 2021-05-28 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.9.8 |  |  | % OF CHANGE (LAST MONTH) |  | 2021-05-28 14:12 | 2021-05-29 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.9.9 |  |  | CLICKS PER POST |  | 2021-05-29 14:12 | 2021-05-30 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.9.10 |  |  | CLICKS PER POST (LAST MONTH) |  | 2021-05-30 14:12 | 2021-05-31 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.9.11 |  |  | CLICKS PER POST CHANGE |  | 2021-05-31 14:12 | 2021-05-31 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.9.12 |  |  | FOLLOWERS (TODAY) |  | 2021-06-03 14:12 | 2021-06-03 14:12 |  | 0 | 1 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.9.13 |  |  | FOLLOWERS (LAST MONTH) |  | 2021-06-03 14:12 | 2021-06-04 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.9.14 |  |  | FOLLOWERS CHANGE |  | 2021-06-04 14:12 | 2021-06-05 14:12 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
This document has been created with the help of https://ganttpro.com online service
You are free to use the document for your purposes with no limitations. To edit it, please, create a copy or use https://ganttpro.com