## Restaurant Marketing Plan
Create professional Gantt charts in GanttPRO in a few clicks
Restaurant Marketing Plan | [7 empty] | 2020-05-12 14:56
Color | WBS Number |  | Task name / Title | Assigned to | Planned start date | Planned end date | Deadline | Progress (%) | Duration (hours) | Estimated hours | Time log (minutes) | Status | Priority | Task description | Cost | Actual cost
| 1 | General |  |  | 2020-05-13 14:56 | 2020-06-07 14:56 |  | 0 | 136 | 0 | 0 |  |  |  | 0 | 0
| 1.1 |  | Start to interview/build team of professionals |  | 2020-05-13 14:56 | 2020-05-15 14:56 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 1.2 |  | Collect info on permits/licenses |  | 2020-05-15 14:56 | 2020-05-15 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 1.3 |  | Insurance |  | 2020-05-15 14:56 | 2020-05-17 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 1.4 |  | Banking |  | 2020-05-16 14:56 | 2020-05-18 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 1.5 |  | Liquor license |  | 2020-05-17 14:56 | 2020-05-19 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 1.6 |  | Federal ID number |  | 2020-05-18 14:56 | 2020-05-20 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 1.7 |  | Credit application sheet |  | 2020-05-19 14:56 | 2020-05-21 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 1.8 |  | Liquor license |  | 2020-05-20 14:56 | 2020-05-22 14:56 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 1.9 |  | Employee meal policy |  | 2020-05-21 14:56 | 2020-05-23 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 1.10 |  | Employee timekeeping system |  | 2020-05-22 14:56 | 2020-05-24 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 1.11 |  | Alcoholic beverage server certification |  | 2020-05-23 14:56 | 2020-05-25 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 1.12 |  | Tax permits |  | 2020-05-24 14:56 | 2020-05-26 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 1.13 |  | Banking |  | 2020-05-25 14:56 | 2020-05-27 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 1.14 |  | Payroll processing |  | 2020-05-26 14:56 | 2020-05-28 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 1.15 |  | Credit card merchant accounts |  | 2020-05-27 14:56 | 2020-05-29 14:56 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 1.16 |  | Accounting software |  | 2020-05-28 14:56 | 2020-05-30 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 1.17 |  | Petty cash |  | 2020-05-29 14:56 | 2020-05-31 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 1.18 |  | Deposit procedures |  | 2020-05-30 14:56 | 2020-06-01 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 1.19 |  | Insurance |  | 2020-05-31 14:56 | 2020-06-02 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 1.20 |  | Bank supplies |  | 2020-06-01 14:56 | 2020-06-03 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 1.21 |  | Accounting/bookkeeping system |  | 2020-06-02 14:56 | 2020-06-04 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 1.22 |  | Permits, licenses, inspections, approvals |  | 2020-06-03 14:56 | 2020-06-05 14:56 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 1.23 |  | Initial change order |  | 2020-06-04 14:56 | 2020-06-06 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 1.24 |  | POS/merchant accounts |  | 2020-06-05 14:56 | 2020-06-07 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 2 | Strategy & Concept |  |  | 2020-06-07 14:56 | 2020-06-18 14:56 |  | 0 | 64 | 0 | 0 |  |  |  | 0 | 0
| 2.1 |  | Examine successful concepts |  | 2020-06-07 14:56 | 2020-06-09 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.2 |  | Local market |  | 2020-06-08 14:56 | 2020-06-10 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.3 |  | Visit existing restaurants |  | 2020-06-09 14:56 | 2020-06-11 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.4 |  | Menu price range |  | 2020-06-10 14:56 | 2020-06-12 14:56 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.5 |  | Preliminary food & bar menus |  | 2020-06-11 14:56 | 2020-06-13 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.6 |  | Further define concept |  | 2020-06-12 14:56 | 2020-06-14 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.7 |  | Points of difference |  | 2020-06-13 14:56 | 2020-06-15 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.8 |  | Concept validation/testing |  | 2020-06-14 14:56 | 2020-06-16 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.9 |  | Determine name of restaurant |  | 2020-06-15 14:56 | 2020-06-17 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.10 |  | Finalize concept |  | 2020-06-16 14:56 | 2020-06-18 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 3 | Design & Contruction |  |  | 2020-06-18 14:56 | 2020-06-26 14:56 |  | 0 | 40 | 0 | 0 |  |  |  | 0 | 0
| 3.1 |  | Graphic artist |  | 2020-06-18 14:56 | 2020-06-20 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 3.2 |  | List of architects |  | 2020-06-19 14:56 | 2020-06-21 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 3.3 |  | List of general contractors |  | 2020-06-20 14:56 | 2020-06-22 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 3.4 |  | List of interior design firms |  | 2020-06-21 14:56 | 2020-06-23 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 3.5 |  | Ansul system |  | 2020-06-22 14:56 | 2020-06-24 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 3.6 |  | Construction & development costs |  | 2020-06-23 14:56 | 2020-06-25 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 3.7 |  | Exits |  | 2020-06-24 14:56 | 2020-06-26 14:56 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 4 | Architectural/design |  |  | 2020-06-26 14:56 | 2020-08-31 14:56 |  | 0 | 384 | 0 | 0 |  |  |  | 0 | 0
| 4.1 |  | Contractor |  | 2020-06-26 14:56 | 2020-06-28 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.2 |  | Design |  | 2020-06-27 14:56 | 2020-06-29 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.3 |  | Patio / outside seating |  | 2020-06-28 14:56 | 2020-06-30 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.4 |  | Utilites billing changes |  | 2020-06-29 14:56 | 2020-07-01 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.5 |  | Utilities |  | 2020-06-30 14:56 | 2020-07-02 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.6 |  | Back door |  | 2020-07-01 14:56 | 2020-07-03 14:56 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.7 |  | Bathroom partitions & accessories |  | 2020-07-02 14:56 | 2020-07-04 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.8 |  | Burgler alarm system |  | 2020-07-03 14:56 | 2020-07-05 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.9 |  | Canopies & awnings |  | 2020-07-04 14:56 | 2020-07-06 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.10 |  | Carpentry |  | 2020-07-05 14:56 | 2020-07-07 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.11 |  | Carpet |  | 2020-07-06 14:56 | 2020-07-08 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.12 |  | Concrete |  | 2020-07-07 14:56 | 2020-07-09 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.13 |  | Construction timeline |  | 2020-07-08 14:56 | 2020-07-10 14:56 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.14 |  | Design elements |  | 2020-07-09 14:56 | 2020-07-11 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.15 |  | Door locks |  | 2020-07-10 14:56 | 2020-07-12 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.16 |  | Door/exits hardware |  | 2020-07-11 14:56 | 2020-07-13 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.17 |  | Doors & Windows |  | 2020-07-12 14:56 | 2020-07-14 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.18 |  | Doors, frames & hardware |  | 2020-07-13 14:56 | 2020-07-15 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.19 |  | Drywall |  | 2020-07-14 14:56 | 2020-07-16 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.20 |  | Electrical/Lighting |  | 2020-07-15 14:56 | 2020-07-17 14:56 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.21 |  | Exterior painting |  | 2020-07-16 14:56 | 2020-07-18 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.22 |  | Flooring |  | 2020-07-17 14:56 | 2020-07-19 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.23 |  | Locks |  | 2020-07-18 14:56 | 2020-07-20 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.24 |  | Kitchen fire control |  | 2020-07-19 14:56 | 2020-07-21 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.25 |  | List of inspectors |  | 2020-07-20 14:56 | 2020-07-22 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.26 |  | Masonry |  | 2020-07-21 14:56 | 2020-07-23 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.27 |  | Mechanical |  | 2020-07-22 14:56 | 2020-07-24 14:56 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.28 |  | Parking lot |  | 2020-07-23 14:56 | 2020-07-25 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.29 |  | Paving |  | 2020-07-24 14:56 | 2020-07-26 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.30 |  | Plumbing |  | 2020-07-25 14:56 | 2020-07-27 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.31 |  | Resilient flooring |  | 2020-07-26 14:56 | 2020-07-28 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.32 |  | Roofing & waterproofing |  | 2020-07-27 14:56 | 2020-07-29 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.33 |  | Select contractor |  | 2020-07-28 14:56 | 2020-07-30 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.34 |  | Smoke detectors |  | 2020-07-29 14:56 | 2020-07-31 14:56 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.35 |  | Sound/music system |  | 2020-07-30 14:56 | 2020-08-01 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.36 |  | Specialty items |  | 2020-07-31 14:56 | 2020-08-02 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.37 |  | Sprinkler system |  | 2020-08-01 14:56 | 2020-08-03 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.38 |  | Water |  | 2020-08-02 14:56 | 2020-08-04 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.39 |  | Tile |  | 2020-08-03 14:56 | 2020-08-05 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.40 |  | Electrical service |  | 2020-08-04 14:56 | 2020-08-06 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.41 |  | Gas service |  | 2020-08-05 14:56 | 2020-08-07 14:56 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.42 |  | Grease trap |  | 2020-08-06 14:56 | 2020-08-08 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.43 |  | Landscaping |  | 2020-08-07 14:56 | 2020-08-09 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.44 |  | Sound |  | 2020-08-08 14:56 | 2020-08-10 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.45 |  | Waste water |  | 2020-08-09 14:56 | 2020-08-11 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.46 |  | Water service |  | 2020-08-10 14:56 | 2020-08-12 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.47 |  | Water quality |  | 2020-08-11 14:56 | 2020-08-13 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.48 |  | Cleaning crew |  | 2020-08-12 14:56 | 2020-08-14 14:56 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.49 |  | Exterior signage |  | 2020-08-13 14:56 | 2020-08-15 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.50 |  | Supplier, contractor, sub |  | 2020-08-14 14:56 | 2020-08-16 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.51 |  | Compressors & valves |  | 2020-08-15 14:56 | 2020-08-17 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.52 |  | Electrical labeling |  | 2020-08-16 14:56 | 2020-08-18 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.53 |  | Inspections |  | 2020-08-17 14:56 | 2020-08-19 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.54 |  | Building & equipment plans |  | 2020-08-18 14:56 | 2020-08-20 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.55 |  | Walk |  | 2020-08-19 14:56 | 2020-08-21 14:56 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.56 |  | Alarm system |  | 2020-08-20 14:56 | 2020-08-22 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.57 |  | Beverage service |  | 2020-08-21 14:56 | 2020-08-23 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.58 |  | Fire extinguishers |  | 2020-08-22 14:56 | 2020-08-24 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.59 |  | Exterior signage light timer |  | 2020-08-23 14:56 | 2020-08-25 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.60 |  | Equipment plans |  | 2020-08-24 14:56 | 2020-08-26 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.61 |  | Exterior cleanup |  | 2020-08-25 14:56 | 2020-08-27 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.62 |  | Final clean |  | 2020-08-26 14:56 | 2020-08-28 14:56 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.63 |  | Wash windows |  | 2020-08-27 14:56 | 2020-08-29 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.64 |  | Parking lot striping |  | 2020-08-28 14:56 | 2020-08-30 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.65 |  | Continue construction punch list |  | 2020-08-29 14:56 | 2020-08-31 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 5 | Furniture, Fixtures & Equipment |  |  | 2020-08-31 14:56 | 2020-10-01 14:56 |  | 0 | 176 | 0 | 0 |  |  |  | 0 | 0
| 5.1 |  | Preliminary equipment requirements |  | 2020-08-31 14:56 | 2020-09-02 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.2 |  | Equipment lists |  | 2020-09-01 14:56 | 2020-09-03 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.3 |  | Lease or purchase kitchen equipment |  | 2020-09-02 14:56 | 2020-09-04 14:56 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.4 |  | Exterior signage |  | 2020-09-03 14:56 | 2020-09-05 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.5 |  | Safe for office |  | 2020-09-04 14:56 | 2020-09-06 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.6 |  | Soda system installation |  | 2020-09-05 14:56 | 2020-09-07 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.7 |  | Communications/phone system |  | 2020-09-06 14:56 | 2020-09-08 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.8 |  | Interior signs |  | 2020-09-07 14:56 | 2020-09-09 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.9 |  | Office equipment |  | 2020-09-08 14:56 | 2020-09-10 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.10 |  | Office furniture |  | 2020-09-09 14:56 | 2020-09-11 14:56 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.11 |  | Receiving scale |  | 2020-09-10 14:56 | 2020-09-12 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.12 |  | Restrooms |  | 2020-09-11 14:56 | 2020-09-13 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.13 |  | Janitorial equipment |  | 2020-09-12 14:56 | 2020-09-14 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.14 |  | Emergency equipment procedures |  | 2020-09-13 14:56 | 2020-09-15 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.15 |  | Equipment tests |  | 2020-09-14 14:56 | 2020-09-16 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.16 |  | Kitchen clock |  | 2020-09-15 14:56 | 2020-09-17 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.17 |  | Kitchen tools/toolkit |  | 2020-09-16 14:56 | 2020-09-18 14:56 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.18 |  | Ansul system |  | 2020-09-17 14:56 | 2020-09-19 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.19 |  | R&M binder for all equipment |  | 2020-09-18 14:56 | 2020-09-20 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.20 |  | Storage shelves |  | 2020-09-19 14:56 | 2020-09-21 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.21 |  | Calibrate temperatures on equipment |  | 2020-09-20 14:56 | 2020-09-22 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.22 |  | Check walk |  | 2020-09-21 14:56 | 2020-09-23 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.23 |  | Clean & sanitize walk |  | 2020-09-22 14:56 | 2020-09-24 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.24 |  | Receive furniture |  | 2020-09-23 14:56 | 2020-09-25 14:56 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.25 |  | Test all equipment |  | 2020-09-24 14:56 | 2020-09-26 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.26 |  | Complete equipment warranty cards |  | 2020-09-25 14:56 | 2020-09-27 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.27 |  | Final clean all equipment |  | 2020-09-26 14:56 | 2020-09-28 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.28 |  | Hang pictures, wall decore |  | 2020-09-27 14:56 | 2020-09-29 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.29 |  | Install interior plants |  | 2020-09-28 14:56 | 2020-09-30 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.30 |  | Run ice machine |  | 2020-09-29 14:56 | 2020-10-01 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 6 | Finance & Legal |  |  | 2020-10-01 14:56 | 2020-10-21 14:56 |  | 0 | 120 | 0 | 0 |  |  |  | 0 | 0
| 6.1 |  | Financing |  | 2020-10-01 14:56 | 2020-10-03 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 6.2 |  | Bank/SBA lending |  | 2020-10-02 14:56 | 2020-10-04 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 6.3 |  | Business plan |  | 2020-10-03 14:56 | 2020-10-05 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 6.4 |  | Capital/construction/opening budget |  | 2020-10-04 14:56 | 2020-10-06 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 6.5 |  | List of possible names for restaurant |  | 2020-10-05 14:56 | 2020-10-07 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 6.6 |  | Financial feasibility |  | 2020-10-06 14:56 | 2020-10-08 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 6.7 |  | Attorney & CPA |  | 2020-10-07 14:56 | 2020-10-09 14:56 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 6.8 |  | Business entity |  | 2020-10-08 14:56 | 2020-10-10 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 6.9 |  | Personal career accomplishments/work history |  | 2020-10-09 14:56 | 2020-10-11 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 6.10 |  | Review financial projections with your CPA |  | 2020-10-10 14:56 | 2020-10-12 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 6.11 |  | Select attorney |  | 2020-10-11 14:56 | 2020-10-13 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 6.12 |  | Select CPA |  | 2020-10-12 14:56 | 2020-10-14 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 6.13 |  | Business plan |  | 2020-10-13 14:56 | 2020-10-15 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 6.14 |  | Capital/construction/opening budget |  | 2020-10-14 14:56 | 2020-10-16 14:56 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 6.15 |  | Personal financial statement |  | 2020-10-15 14:56 | 2020-10-17 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 6.16 |  | Buy |  | 2020-10-16 14:56 | 2020-10-18 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 6.17 |  | Landlord approvals |  | 2020-10-17 14:56 | 2020-10-19 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 6.18 |  | Tax ID numbers/accounts |  | 2020-10-18 14:56 | 2020-10-20 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 6.19 |  | Line of credit |  | 2020-10-19 14:56 | 2020-10-21 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 7 | Food & Beverage |  |  | 2020-10-21 14:56 | 2020-11-05 14:56 |  | 0 | 80 | 0 | 0 |  |  |  | 0 | 0
| 7.1 |  | List of available suppliers |  | 2020-10-21 14:56 | 2020-10-23 14:56 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 7.2 |  | Beer |  | 2020-10-22 14:56 | 2020-10-24 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 7.3 |  | Food inventory |  | 2020-10-23 14:56 | 2020-10-25 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 7.4 |  | Liquor |  | 2020-10-24 14:56 | 2020-10-26 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 7.5 |  | Liquor, beer & wine inventory |  | 2020-10-25 14:56 | 2020-10-27 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 7.6 |  | Price menu |  | 2020-10-26 14:56 | 2020-10-28 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 7.7 |  | Standard recipe files |  | 2020-10-27 14:56 | 2020-10-29 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 7.8 |  | Wine |  | 2020-10-28 14:56 | 2020-10-30 14:56 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 7.9 |  | Wine list |  | 2020-10-29 14:56 | 2020-10-31 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 7.10 |  | HACCAP training / certification |  | 2020-10-30 14:56 | 2020-11-01 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 7.11 |  | Menus |  | 2020-10-31 14:56 | 2020-11-02 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 7.12 |  | Initial food order |  | 2020-11-01 14:56 | 2020-11-03 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 7.13 |  | Photographs of menu items |  | 2020-11-02 14:56 | 2020-11-04 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 7.14 |  | Initial alcoholic beverage order |  | 2020-11-03 14:56 | 2020-11-05 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 8 | Marketing |  |  | 2020-11-05 14:56 | 2020-11-15 14:56 |  | 0 | 56 | 0 | 0 |  |  |  | 0 | 0
| 8.1 |  | Competitive analysis |  | 2020-11-05 14:56 | 2020-11-07 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 8.2 |  | Menu boards & pictures |  | 2020-11-06 14:56 | 2020-11-08 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 8.3 |  | Banners |  | 2020-11-07 14:56 | 2020-11-09 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 8.4 |  | Gift certificates |  | 2020-11-08 14:56 | 2020-11-10 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 8.5 |  | Local charities |  | 2020-11-09 14:56 | 2020-11-11 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 8.6 |  | Printing |  | 2020-11-10 14:56 | 2020-11-12 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 8.7 |  | Public relations for opening |  | 2020-11-11 14:56 | 2020-11-13 14:56 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 8.8 |  | Yellow page ad |  | 2020-11-12 14:56 | 2020-11-14 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 8.9 |  | Opening party(s) |  | 2020-11-13 14:56 | 2020-11-15 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 9 | Ongoing Services |  |  | 2020-11-15 14:56 | 2020-12-07 14:56 |  | 0 | 128 | 0 | 0 |  |  |  | 0 | 0
| 9.1 |  | Insurance agent |  | 2020-11-15 14:56 | 2020-11-17 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 9.2 |  | Dining room cleaning |  | 2020-11-16 14:56 | 2020-11-18 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 9.3 |  | Hood/kitchen cleaning |  | 2020-11-17 14:56 | 2020-11-19 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 9.4 |  | Interior plant service |  | 2020-11-18 14:56 | 2020-11-20 14:56 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 9.5 |  | Landscaping/lawn services |  | 2020-11-19 14:56 | 2020-11-21 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 9.6 |  | Security guards |  | 2020-11-20 14:56 | 2020-11-22 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 9.7 |  | Payroll processing |  | 2020-11-21 14:56 | 2020-11-23 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 9.8 |  | Music |  | 2020-11-22 14:56 | 2020-11-24 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 9.9 |  | Chemicals |  | 2020-11-23 14:56 | 2020-11-25 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 9.10 |  | Grease trap |  | 2020-11-24 14:56 | 2020-11-26 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 9.11 |  | Knife & blade sharpening |  | 2020-11-25 14:56 | 2020-11-27 14:56 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 9.12 |  | Monthly accounting |  | 2020-11-26 14:56 | 2020-11-28 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 9.13 |  | Pest control |  | 2020-11-27 14:56 | 2020-11-29 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 9.14 |  | Trash disposal |  | 2020-11-28 14:56 | 2020-11-30 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 9.15 |  | Window washing |  | 2020-11-29 14:56 | 2020-12-01 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 9.16 |  | Armored car service |  | 2020-11-30 14:56 | 2020-12-02 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 9.17 |  | Building & HVAC repairs |  | 2020-12-01 14:56 | 2020-12-03 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 9.18 |  | Dishwasher service |  | 2020-12-02 14:56 | 2020-12-04 14:56 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 9.19 |  | Laundry & linen |  | 2020-12-03 14:56 | 2020-12-05 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 9.20 |  | Equipment repairs |  | 2020-12-04 14:56 | 2020-12-06 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 9.21 |  | Equipment repairs |  | 2020-12-05 14:56 | 2020-12-07 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 10 | Operations |  |  | 2020-12-07 14:56 | 2021-01-12 14:56 |  | 0 | 208 | 0 | 0 |  |  |  | 0 | 0
| 10.1 |  | Visit restaurants with similar offerings |  | 2020-12-07 14:56 | 2020-12-09 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 10.2 |  | Menu & recipes |  | 2020-12-08 14:56 | 2020-12-10 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 10.3 |  | Table mix & arrangement |  | 2020-12-09 14:56 | 2020-12-11 14:56 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 10.4 |  | Hours of operation |  | 2020-12-10 14:56 | 2020-12-12 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 10.5 |  | Vending machines |  | 2020-12-11 14:56 | 2020-12-13 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 10.6 |  | Checklists |  | 2020-12-12 14:56 | 2020-12-14 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 10.7 |  | Guest (table ready) call system |  | 2020-12-13 14:56 | 2020-12-15 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 10.8 |  | Happy hour |  | 2020-12-14 14:56 | 2020-12-16 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 10.9 |  | Menu analysis |  | 2020-12-15 14:56 | 2020-12-17 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 10.10 |  | Menu item cost |  | 2020-12-16 14:56 | 2020-12-18 14:56 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 10.11 |  | Prep lists with pars |  | 2020-12-17 14:56 | 2020-12-19 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 10.12 |  | Product specs |  | 2020-12-18 14:56 | 2020-12-20 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 10.13 |  | Reservation policy |  | 2020-12-19 14:56 | 2020-12-21 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 10.14 |  | Station setup sheets with pars |  | 2020-12-20 14:56 | 2020-12-22 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 10.15 |  | Emergency exit procedures |  | 2020-12-21 14:56 | 2020-12-23 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 10.16 |  | Bulletin board |  | 2020-12-22 14:56 | 2020-12-24 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 10.17 |  | Children's amenities |  | 2020-12-23 14:56 | 2020-12-25 14:56 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 10.18 |  | Cleaning & maintenance schedules |  | 2020-12-24 14:56 | 2020-12-26 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 10.19 |  | Emergency numbers |  | 2020-12-25 14:56 | 2020-12-27 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 10.20 |  | Entertainment |  | 2020-12-26 14:56 | 2020-12-28 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 10.21 |  | Floor maintenance |  | 2020-12-27 14:56 | 2020-12-29 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 10.22 |  | Valet parking |  | 2020-12-28 14:56 | 2020-12-30 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 10.23 |  | Approved vendor list |  | 2020-12-29 14:56 | 2020-12-31 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 10.24 |  | Birthday specials |  | 2020-12-30 14:56 | 2021-01-01 14:56 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 10.25 |  | Seating chart & waitstaff sections |  | 2020-12-31 14:56 | 2021-01-02 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 10.26 |  | Initial food, beverage & supplies orders |  | 2021-01-01 14:56 | 2021-01-03 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 10.27 |  | Order & delivery schedule |  | 2021-01-02 14:56 | 2021-01-04 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 10.28 |  | Padlocks for cooler doors |  | 2021-01-03 14:56 | 2021-01-05 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 10.29 |  | Deposit bags |  | 2021-01-04 14:56 | 2021-01-06 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 10.30 |  | Hostess stand supplies |  | 2021-01-05 14:56 | 2021-01-07 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 10.31 |  | Light levels |  | 2021-01-06 14:56 | 2021-01-08 14:56 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 10.32 |  | Change order |  | 2021-01-07 14:56 | 2021-01-09 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 10.33 |  | Check inventory levels |  | 2021-01-08 14:56 | 2021-01-10 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 10.34 |  | Opening inventory |  | 2021-01-09 14:56 | 2021-01-11 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 10.35 |  | Customer comment cards |  | 2021-01-10 14:56 | 2021-01-12 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 11 | Personnel |  |  | 2021-01-12 14:56 | 2021-02-05 14:56 |  | 0 | 128 | 0 | 0 |  |  |  | 0 | 0
| 11.1 |  | Employee benefits |  | 2021-01-12 14:56 | 2021-01-14 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 11.2 |  | Employee job descriptions |  | 2021-01-13 14:56 | 2021-01-15 14:56 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 11.3 |  | Management team |  | 2021-01-14 14:56 | 2021-01-16 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 11.4 |  | Organizational chart |  | 2021-01-15 14:56 | 2021-01-17 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 11.5 |  | Employee handbook |  | 2021-01-16 14:56 | 2021-01-18 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 11.6 |  | Employee training manuals |  | 2021-01-17 14:56 | 2021-01-19 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 11.7 |  | Management training materials |  | 2021-01-18 14:56 | 2021-01-20 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 11.8 |  | Master training schedule |  | 2021-01-19 14:56 | 2021-01-21 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 11.9 |  | Sidework procedures & schedules |  | 2021-01-20 14:56 | 2021-01-22 14:56 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 11.10 |  | Staff pay scales |  | 2021-01-21 14:56 | 2021-01-23 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 11.11 |  | Staffing needs |  | 2021-01-22 14:56 | 2021-01-24 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 11.12 |  | Employee recruiting |  | 2021-01-23 14:56 | 2021-01-25 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 11.13 |  | Food safety training |  | 2021-01-24 14:56 | 2021-01-26 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 11.14 |  | Assemble new employee materials |  | 2021-01-25 14:56 | 2021-01-27 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 11.15 |  | Employee files |  | 2021-01-26 14:56 | 2021-01-28 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 11.16 |  | OSHA |  | 2021-01-27 14:56 | 2021-01-29 14:56 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 11.17 |  | Alcoholic beverage server certification |  | 2021-01-28 14:56 | 2021-01-30 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 11.18 |  | HACCAP training / certification |  | 2021-01-29 14:56 | 2021-01-31 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 11.19 |  | Safety checklist & audit |  | 2021-01-30 14:56 | 2021-02-01 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 11.20 |  | Wine training program |  | 2021-01-31 14:56 | 2021-02-02 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 11.21 |  | Safety & first aid training |  | 2021-02-01 14:56 | 2021-02-03 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 11.22 |  | Conduct practice runs/mock service |  | 2021-02-02 14:56 | 2021-02-04 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 11.23 |  | Finalize opening week employee schedules |  | 2021-02-03 14:56 | 2021-02-05 14:56 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 12 | Site / Planning |  |  | 2021-02-05 14:56 | 2021-03-08 14:56 |  | 0 | 184 | 0 | 0 |  |  |  | 0 | 0
| 12.1 |  | Potential of local markets |  | 2021-02-05 14:56 | 2021-02-07 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 12.2 |  | Facility requirements |  | 2021-02-06 14:56 | 2021-02-08 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 12.3 |  | Site/location criteria |  | 2021-02-07 14:56 | 2021-02-09 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 12.4 |  | Competitive analysis |  | 2021-02-08 14:56 | 2021-02-10 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 12.5 |  | Square footage |  | 2021-02-09 14:56 | 2021-02-11 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 12.6 |  | Tenent rep broker |  | 2021-02-10 14:56 | 2021-02-12 14:56 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 12.7 |  | Bar seating |  | 2021-02-11 14:56 | 2021-02-13 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 12.8 |  | Building/fire/safety codes |  | 2021-02-12 14:56 | 2021-02-14 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 12.9 |  | Electrical service |  | 2021-02-13 14:56 | 2021-02-15 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 12.10 |  | Floor plan (existing space) |  | 2021-02-14 14:56 | 2021-02-16 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 12.11 |  | Floor slope evaluation |  | 2021-02-15 14:56 | 2021-02-17 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 12.12 |  | Lighting fixtures |  | 2021-02-16 14:56 | 2021-02-18 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 12.13 |  | Liquor license |  | 2021-02-17 14:56 | 2021-02-19 14:56 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 12.14 |  | List of existing kitchen equipment |  | 2021-02-18 14:56 | 2021-02-20 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 12.15 |  | Number of tables/seats |  | 2021-02-19 14:56 | 2021-02-21 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 12.16 |  | Parking |  | 2021-02-20 14:56 | 2021-02-22 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 12.17 |  | Sales to investment analysis |  | 2021-02-21 14:56 | 2021-02-23 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 12.18 |  | Traffic patterns |  | 2021-02-22 14:56 | 2021-02-24 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 12.19 |  | Zoning requirements |  | 2021-02-23 14:56 | 2021-02-25 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 12.20 |  | Cleanup required |  | 2021-02-24 14:56 | 2021-02-26 14:56 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 12.21 |  | Gas main / lines |  | 2021-02-25 14:56 | 2021-02-27 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 12.22 |  | Health department |  | 2021-02-26 14:56 | 2021-02-28 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 12.23 |  | HVAC system |  | 2021-02-27 14:56 | 2021-03-01 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 12.24 |  | Plans for location/site area |  | 2021-02-28 14:56 | 2021-03-02 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 12.25 |  | Sewer lines |  | 2021-03-01 14:56 | 2021-03-03 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 12.26 |  | Termite report |  | 2021-03-02 14:56 | 2021-03-04 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 12.27 |  | Gas |  | 2021-03-03 14:56 | 2021-03-05 14:56 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 12.28 |  | Utility requirements |  | 2021-03-04 14:56 | 2021-03-06 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 12.29 |  | Water lines |  | 2021-03-05 14:56 | 2021-03-07 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 12.30 |  | Site selection decision |  | 2021-03-06 14:56 | 2021-03-08 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 13 | Smallwares / Supplies |  |  | 2021-03-08 14:56 | 2021-03-21 14:56 |  | 0 | 72 | 0 | 0 |  |  |  | 0 | 0
| 13.1 |  | Uniforms |  | 2021-03-08 14:56 | 2021-03-10 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 13.2 |  | Dishroom items |  | 2021-03-09 14:56 | 2021-03-11 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 13.3 |  | Smallware & kitchen utensils |  | 2021-03-10 14:56 | 2021-03-12 14:56 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 13.4 |  | Dining room |  | 2021-03-11 14:56 | 2021-03-13 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 13.5 |  | Bar |  | 2021-03-12 14:56 | 2021-03-14 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 13.6 |  | Tabletop items |  | 2021-03-13 14:56 | 2021-03-15 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 13.7 |  | First aid kit |  | 2021-03-14 14:56 | 2021-03-16 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 13.8 |  | Tip trays, check presentation folders |  | 2021-03-15 14:56 | 2021-03-17 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 13.9 |  | Initial chemicals order |  | 2021-03-16 14:56 | 2021-03-18 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 13.10 |  | Linen |  | 2021-03-17 14:56 | 2021-03-19 14:56 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 13.11 |  | Initial paper good order |  | 2021-03-18 14:56 | 2021-03-20 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 13.12 |  | Janitorial supplies |  | 2021-03-19 14:56 | 2021-03-21 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 14 | Technology |  |  | 2021-03-21 14:56 | 2021-03-30 14:56 |  | 0 | 56 | 0 | 0 |  |  |  | 0 | 0
| 14.1 |  | POS phone line |  | 2021-03-21 14:56 | 2021-03-23 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 14.2 |  | POS system |  | 2021-03-22 14:56 | 2021-03-24 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 14.3 |  | Website |  | 2021-03-23 14:56 | 2021-03-25 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 14.4 |  | Computer software |  | 2021-03-24 14:56 | 2021-03-26 14:56 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 14.5 |  | POS system |  | 2021-03-25 14:56 | 2021-03-27 14:56 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 14.6 |  | Phone on hold message |  | 2021-03-26 14:56 | 2021-03-28 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 14.7 |  | Internet service provider |  | 2021-03-27 14:56 | 2021-03-29 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 14.8 |  | POS/register |  | 2021-03-28 14:56 | 2021-03-30 14:56 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
This document has been created with the help of https://ganttpro.com online service
You are free to use the document for your purposes with no limitations. To edit it, please, create a copy or use https://ganttpro.com