## Sample Marketing Action Plan
Create professional Gantt charts in GanttPRO in a few clicks
Sample Marketing Action Plan | [8 empty] | 2020-05-12 14:59
Color | WBS Number |  |  | Task name / Title | Assigned to | Planned start date | Planned end date | Deadline | Progress (%) | Duration (hours) | Estimated hours | Time log (minutes) | Status | Priority | Task description | Cost | Actual cost
| 1 | Executive summary |  |  |  | 2020-05-13 14:59 | 2020-05-18 14:59 |  | 0 | 24 | 0 | 0 |  |  |  | 0 | 0
| 1.1 |  | Objectives of plan |  |  | 2020-05-13 14:59 | 2020-05-14 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 1.2 |  | Challenges of organization |  |  | 2020-05-14 14:59 | 2020-05-15 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 1.3 |  | Expectations if marketing plan was successful |  |  | 2020-05-15 14:59 | 2020-05-16 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 1.4 |  | Alignment |  |  | 2020-05-16 14:59 | 2020-05-17 14:59 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 1.5 |  | Mission |  |  | 2020-05-17 14:59 | 2020-05-18 14:59 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 2 | Target markets |  |  |  | 2020-05-19 14:59 | 2020-05-22 14:59 |  | 0 | 24 | 0 | 0 |  |  |  | 0 | 0
| 2.1 |  | Demographics |  |  | 2020-05-19 14:59 | 2020-05-20 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.2 |  | Lifestyle |  |  | 2020-05-20 14:59 | 2020-05-21 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.3 |  | Actions |  |  | 2020-05-21 14:59 | 2020-05-22 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 3 | Organization’s strategies and plans |  |  |  | 2020-05-23 14:59 | 2020-05-28 14:59 |  | 0 | 24 | 0 | 0 |  |  |  | 0 | 0
| 3.1 |  | New products, markets |  |  | 2020-05-23 14:59 | 2020-05-24 14:59 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 3.2 |  | Promotions |  |  | 2020-05-24 14:59 | 2020-05-25 14:59 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 3.3 |  | Expansion |  |  | 2020-05-25 14:59 | 2020-05-26 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 3.4 |  | Assessment |  |  | 2020-05-26 14:59 | 2020-05-27 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 3.5 |  | Current marketing efforts |  |  | 2020-05-27 14:59 | 2020-05-28 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 4 | Marketing metrics- performance/interactivity |  |  |  | 2020-05-29 14:59 | 2020-06-02 14:59 |  | 0 | 16 | 0 | 0 |  |  |  | 0 | 0
| 4.1 |  | Search Engine positioning (for keywords ) |  |  | 2020-05-29 14:59 | 2020-05-30 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.2 |  | Analytics |  |  | 2020-05-30 14:59 | 2020-05-31 14:59 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.3 |  | Facebook Insights/ likes |  |  | 2020-05-31 14:59 | 2020-06-01 14:59 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.4 |  | Twitter activity |  |  | 2020-06-01 14:59 | 2020-06-02 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5 | Industry analysis |  |  |  | 2020-06-03 14:59 | 2020-06-09 14:59 |  | 0 | 32 | 0 | 0 |  |  |  | 0 | 0
| 5.1 |  | SWOT situational analysis |  |  | 2020-06-03 14:59 | 2020-06-04 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.2 |  | Competitor analysis and environment |  |  | 2020-06-04 14:59 | 2020-06-05 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.3 |  | Consumer analysis (different behaviors of target markets ) |  |  | 2020-06-05 14:59 | 2020-06-06 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.4 |  | Market research/Consumer insights |  |  | 2020-06-06 14:59 | 2020-06-07 14:59 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.5 |  | focus group |  |  | 2020-06-07 14:59 | 2020-06-08 14:59 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.6 |  | If service organization |  |  | 2020-06-08 14:59 | 2020-06-09 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 6 | Service blueprint |  |  |  | 2020-06-10 14:59 | 2020-06-12 14:59 |  | 0 | 16 | 0 | 0 |  |  |  | 0 | 0
| 6.1 |  | Service gap analysis |  |  | 2020-06-10 14:59 | 2020-06-11 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 6.2 |  | Summarize challenges |  |  | 2020-06-11 14:59 | 2020-06-12 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 7 | Brand Blueprint |  |  |  | 2020-06-13 14:59 | 2020-06-21 14:59 |  | 0 | 40 | 0 | 0 |  |  |  | 0 | 0
| 7.1 |  | Brand Personality– How to get your brand unstuck? |  |  | 2020-06-13 14:59 | 2020-06-14 14:59 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 7.2 |  | Current image, mindset, behavior |  |  | 2020-06-14 14:59 | 2020-06-15 14:59 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 7.3 |  | Desired behavior |  |  | 2020-06-15 14:59 | 2020-06-16 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 7.4 |  | Challenges to overcome |  |  | 2020-06-16 14:59 | 2020-06-17 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 7.5 |  | Brand Properties |  |  | 2020-06-17 14:59 | 2020-06-18 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 7.6 |  | Product/service features |  |  | 2020-06-18 14:59 | 2020-06-19 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 7.7 |  | Logo |  |  | 2020-06-19 14:59 | 2020-06-20 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 7.8 |  | Tagline |  |  | 2020-06-20 14:59 | 2020-06-21 14:59 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 8 | Brand Essence |  |  |  | 2020-06-22 14:59 | 2020-06-29 14:59 |  | 0 | 40 | 0 | 0 |  |  |  | 0 | 0
| 8.1 |  | Organizational touchstone |  |  | 2020-06-22 14:59 | 2020-06-23 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 8.2 |  | Customer insights and key benefit |  |  | 2020-06-23 14:59 | 2020-06-24 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 8.3 |  | Recommendations for Clarified Brand |  |  | 2020-06-24 14:59 | 2020-06-25 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 8.4 |  | Suggestions for Logo, Tagline |  |  | 2020-06-25 14:59 | 2020-06-26 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 8.5 |  | Brand Promise – 4-6 core elements of brand ( reflecting value / benefits) |  |  | 2020-06-26 14:59 | 2020-06-27 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 8.6 |  | Universal Selling Points (USP) |  |  | 2020-06-27 14:59 | 2020-06-28 14:59 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 8.7 |  | Value Proposition |  |  | 2020-06-28 14:59 | 2020-06-29 14:59 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 9 | Brand Blueprint Elements |  |  |  | 2020-06-30 14:59 | 2020-07-12 14:59 |  | 0 | 72 | 0 | 0 |  |  |  | 0 | 0
| 9.1 |  | Competitive context |  |  | 2020-06-30 14:59 | 2020-07-01 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 9.2 |  | Target markets |  |  | 2020-07-01 14:59 | 2020-07-02 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 9.3 |  | Current image, mindset, behavior |  |  | 2020-07-02 14:59 | 2020-07-03 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 9.4 |  | Desired behavior |  |  | 2020-07-03 14:59 | 2020-07-04 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 9.5 |  | Challenges to overcome |  |  | 2020-07-04 14:59 | 2020-07-05 14:59 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 9.6 |  | Brand Properties |  |  | 2020-07-05 14:59 | 2020-07-06 14:59 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 9.7 |  | Brand Essence |  |  | 2020-07-06 14:59 | 2020-07-07 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 9.8 |  | Customer insights/benefit |  |  | 2020-07-07 14:59 | 2020-07-08 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 9.9 |  | Brand Recommendations (logo, tagline) |  |  | 2020-07-08 14:59 | 2020-07-09 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 9.10 |  | Brand Promise |  |  | 2020-07-09 14:59 | 2020-07-10 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 9.11 |  | Universal Selling Points |  |  | 2020-07-10 14:59 | 2020-07-11 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 9.12 |  | Value Proposition |  |  | 2020-07-11 14:59 | 2020-07-12 14:59 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 10 | Integrated Media Sample |  |  |  | 2020-07-13 14:59 | 2020-08-03 14:59 |  | 0 | 120 | 0 | 0 |  |  |  | 0 | 0
| 10.1 |  | Flyers/ brochures |  |  | 2020-07-13 14:59 | 2020-07-14 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 10.2 |  | YouTube -Video |  |  | 2020-07-14 14:59 | 2020-07-15 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 10.3 |  | Facebook |  |  | 2020-07-15 14:59 | 2020-07-16 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 10.4 |  | Twitter |  |  | 2020-07-16 14:59 | 2020-07-17 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 10.5 |  | Email blast |  |  | 2020-07-17 14:59 | 2020-07-18 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 10.6 |  | Blog |  |  | 2020-07-18 14:59 | 2020-07-19 14:59 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 10.7 |  | Social bookmarks |  |  | 2020-07-19 14:59 | 2020-07-20 14:59 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 10.8 |  | Pinterest |  |  | 2020-07-20 14:59 | 2020-07-21 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 10.9 |  | Instagram |  |  | 2020-07-21 14:59 | 2020-07-22 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 10.10 |  | TV/radio |  |  | 2020-07-22 14:59 | 2020-07-23 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 10.11 |  | Infographic |  |  | 2020-07-23 14:59 | 2020-07-24 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 10.12 |  | Newspaper |  |  | 2020-07-24 14:59 | 2020-07-25 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 10.13 |  | Posters |  |  | 2020-07-25 14:59 | 2020-07-26 14:59 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 10.14 |  | Newsletter ( online) |  |  | 2020-07-26 14:59 | 2020-07-27 14:59 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 10.15 |  | Personal networks |  |  | 2020-07-27 14:59 | 2020-07-28 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 10.16 |  | friends, family, org. |  |  | 2020-07-28 14:59 | 2020-07-29 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 10.17 |  | Local businesses |  |  | 2020-07-29 14:59 | 2020-07-30 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 10.18 |  | WOM friends |  |  | 2020-07-30 14:59 | 2020-07-31 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 10.19 |  | Events |  |  | 2020-07-31 14:59 | 2020-08-01 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 10.20 |  | Past participants/buyers |  |  | 2020-08-01 14:59 | 2020-08-02 14:59 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 10.21 |  | Partner organizations |  |  | 2020-08-02 14:59 | 2020-08-03 14:59 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 11 | Implementation (What resources) |  |  |  | 2020-08-04 14:59 | 2020-08-11 14:59 |  | 0 | 40 | 0 | 0 |  |  |  | 0 | 0
| 11.1 |  | staff |  |  | 2020-08-04 14:59 | 2020-08-05 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 11.2 |  | management |  |  | 2020-08-05 14:59 | 2020-08-06 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 11.3 |  | staff availability |  |  | 2020-08-06 14:59 | 2020-08-07 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 11.4 |  | expertise to implement the plan |  |  | 2020-08-07 14:59 | 2020-08-08 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 11.5 |  | outsource elements of plan (use outside vendors) |  |  | 2020-08-08 14:59 | 2020-08-09 14:59 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 11.6 |  | time |  |  | 2020-08-09 14:59 | 2020-08-10 14:59 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 11.7 |  | resources (financial) |  |  | 2020-08-10 14:59 | 2020-08-11 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 12 | Monitoring Evaluation |  |  |  | 2020-08-12 14:59 | 2020-08-18 14:59 |  | 0 | 32 | 0 | 0 |  |  |  | 0 | 0
| 12.1 |  | Monitoring metrics |  |  | 2020-08-12 14:59 | 2020-08-13 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 12.2 |  | Website - Google Analytics |  |  | 2020-08-13 14:59 | 2020-08-14 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 12.3 |  | Social media insights |  |  | 2020-08-14 14:59 | 2020-08-15 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 12.4 |  | Digital footprint changes |  |  | 2020-08-15 14:59 | 2020-08-16 14:59 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 12.5 |  | Company Alerts |  |  | 2020-08-16 14:59 | 2020-08-17 14:59 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 12.6 |  | Evaluation |  |  | 2020-08-17 14:59 | 2020-08-18 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 13 | MEASURE results |  |  |  | 2020-08-19 14:59 | 2020-08-25 14:59 |  | 0 | 32 | 0 | 0 |  |  |  | 0 | 0
| 13.1 |  | Determine Return on Investment (ROI) or Social ROI (SROI) |  |  | 2020-08-19 14:59 | 2020-08-20 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 13.2 |  | Sustainability |  |  | 2020-08-20 14:59 | 2020-08-21 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 13.3 |  | Plan for ongoing feedback from target markets |  |  | 2020-08-21 14:59 | 2020-08-22 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 13.4 |  | Innovate digital media and distribution channels |  |  | 2020-08-22 14:59 | 2020-08-23 14:59 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 13.5 |  | Adjust strategy to maximize efforts |  |  | 2020-08-23 14:59 | 2020-08-24 14:59 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 13.6 |  | Integrate Social Enterprise (digital tools throughout departments of organization to facilitate upward and downward communications) |  |  | 2020-08-24 14:59 | 2020-08-25 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 14 | Analysis and strategy |  |  |  | 2020-08-26 14:59 | 2020-09-02 14:59 |  | 0 | 40 | 0 | 0 |  |  |  | 0 | 0
| 14.1 |  | Company defined |  |  | 2020-08-26 14:59 | 2020-08-27 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 14.2 |  | Your mission |  |  | 2020-08-27 14:59 | 2020-08-28 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 14.3 |  | Your vision |  |  | 2020-08-28 14:59 | 2020-08-29 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 14.4 |  | Target audience |  |  | 2020-08-29 14:59 | 2020-08-30 14:59 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 14.5 |  | Your message |  |  | 2020-08-30 14:59 | 2020-08-31 14:59 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 14.6 |  | Strengths defined |  |  | 2020-08-31 14:59 | 2020-09-01 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 14.7 |  | Weaknesses defined |  |  | 2020-09-01 14:59 | 2020-09-02 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 15 | Social media marketing (budget) |  |  |  | 2020-09-03 14:59 | 2020-09-14 14:59 |  | 0 | 56 | 0 | 0 |  |  |  | 0 | 0
| 15.1 |  | Human resources - cost |  |  | 2020-09-03 14:59 | 2020-09-04 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 15.2 |  | Advertising |  |  | 2020-09-04 14:59 | 2020-09-05 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 15.3 |  | Promotions |  |  | 2020-09-05 14:59 | 2020-09-06 14:59 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 15.4 |  | Agency fees / retainer |  |  | 2020-09-06 14:59 | 2020-09-07 14:59 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 15.5 |  | Hardware |  |  | 2020-09-07 14:59 | 2020-09-08 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 15.6 |  | Content creation |  |  | 2020-09-08 14:59 | 2020-09-09 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 15.7 |  | Content management |  |  | 2020-09-09 14:59 | 2020-09-10 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 15.8 |  | Licensed content |  |  | 2020-09-10 14:59 | 2020-09-11 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 15.9 |  | Software licenses |  |  | 2020-09-11 14:59 | 2020-09-12 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 15.10 |  | Graphic design |  |  | 2020-09-12 14:59 | 2020-09-13 14:59 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 15.11 |  | Video production |  |  | 2020-09-13 14:59 | 2020-09-14 14:59 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 16 | Competitive analysis |  |  |  | 2020-09-15 14:59 | 2020-09-21 14:59 |  | 0 | 32 | 0 | 0 |  |  |  | 0 | 0
| 16.1 |  | Your company's competitive edge |  |  | 2020-09-15 14:59 | 2020-09-16 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 16.2 |  | Competition defined |  |  | 2020-09-16 14:59 | 2020-09-17 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 16.3 |  | Competition strengths |  |  | 2020-09-17 14:59 | 2020-09-18 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 16.4 |  | What your company can do differently |  |  | 2020-09-18 14:59 | 2020-09-19 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 16.5 |  | Potential roadblocks |  |  | 2020-09-19 14:59 | 2020-09-20 14:59 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 16.6 |  | Benefits |  |  | 2020-09-20 14:59 | 2020-09-21 14:59 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 17 | Plan |  |  |  | 2020-09-22 14:59 | 2020-09-30 14:59 |  | 0 | 48 | 0 | 0 |  |  |  | 0 | 0
| 17.1 |  | Journalists |  |  | 2020-09-22 14:59 | 2020-09-23 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 17.2 |  | Bloggers |  |  | 2020-09-23 14:59 | 2020-09-24 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 17.3 |  | Social media influencers |  |  | 2020-09-24 14:59 | 2020-09-25 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 17.4 |  | Social media interactors |  |  | 2020-09-25 14:59 | 2020-09-26 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 17.5 |  | Peers and partners |  |  | 2020-09-26 14:59 | 2020-09-27 14:59 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 17.6 |  | Cross promotions |  |  | 2020-09-27 14:59 | 2020-09-28 14:59 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 17.7 |  | Other |  |  | 2020-09-28 14:59 | 2020-09-29 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 17.8 |  | Other |  |  | 2020-09-29 14:59 | 2020-09-30 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18 | Social media audit |  |  |  | 2020-10-02 14:59 | 2021-03-26 14:59 |  | 0 | 1000 | 0 | 0 |  |  |  | 0 | 0
| 18.1 |  | Facebook |  |  | 2020-10-02 14:59 | 2020-10-17 14:59 |  | 0 | 88 | 0 | 0 |  |  |  | 0 | 0
| 18.1.1 |  |  | Link |  | 2020-10-02 14:59 | 2020-10-03 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.1.2 |  |  | Profile name |  | 2020-10-03 14:59 | 2020-10-04 14:59 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.1.3 |  |  | Followers |  | 2020-10-04 14:59 | 2020-10-05 14:59 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.1.4 |  |  | Date of last activity |  | 2020-10-05 14:59 | 2020-10-06 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.1.5 |  |  | Frequency of posts |  | 2020-10-06 14:59 | 2020-10-07 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.1.6 |  |  | Montly referral traffic |  | 2020-10-07 14:59 | 2020-10-08 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.1.7 |  |  | % of change (last year) |  | 2020-10-08 14:59 | 2020-10-09 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.1.8 |  |  | % of change (last month) |  | 2020-10-09 14:59 | 2020-10-10 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.1.9 |  |  | Clicks per post |  | 2020-10-10 14:59 | 2020-10-11 14:59 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.1.10 |  |  | Clicks per post (last month) |  | 2020-10-11 14:59 | 2020-10-12 14:59 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.1.11 |  |  | Clicks per post change |  | 2020-10-12 14:59 | 2020-10-13 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.1.12 |  |  | Facebook reach |  | 2020-10-13 14:59 | 2020-10-14 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.1.13 |  |  | Followers (today) |  | 2020-10-14 14:59 | 2020-10-15 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.1.14 |  |  | Followers (last month) |  | 2020-10-15 14:59 | 2020-10-16 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.1.15 |  |  | Followers change |  | 2020-10-16 14:59 | 2020-10-17 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.2 |  | INSTAGRAM |  |  | 2020-10-18 14:59 | 2020-11-02 14:59 |  | 0 | 80 | 0 | 0 |  |  |  | 0 | 0
| 18.2.1 |  |  | LINK |  | 2020-10-18 14:59 | 2020-10-19 14:59 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.2.2 |  |  | PROFILE NAME |  | 2020-10-19 14:59 | 2020-10-20 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.2.3 |  |  | FOLLOWERS |  | 2020-10-20 14:59 | 2020-10-21 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.2.4 |  |  | DATE OF LAST ACTIVITY |  | 2020-10-21 14:59 | 2020-10-22 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.2.5 |  |  | FREQUENCY OF POSTS |  | 2020-10-22 14:59 | 2020-10-23 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.2.6 |  |  | MONTLY REFERRAL TRAFFIC |  | 2020-10-23 14:59 | 2020-10-24 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.2.7 |  |  | % OF CHANGE (LAST YEAR) |  | 2020-10-24 14:59 | 2020-10-25 14:59 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.2.8 |  |  | % OF CHANGE (LAST MONTH) |  | 2020-10-25 14:59 | 2020-10-26 14:59 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.2.9 |  |  | CLICKS PER POST |  | 2020-10-26 14:59 | 2020-10-27 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.2.10 |  |  | CLICKS PER POST (LAST MONTH) |  | 2020-10-27 14:59 | 2020-10-28 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.2.11 |  |  | CLICKS PER POST CHANGE |  | 2020-10-28 14:59 | 2020-10-29 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.2.12 |  |  | FACEBOOK REACH |  | 2020-10-29 14:59 | 2020-10-30 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.2.13 |  |  | FOLLOWERS (TODAY) |  | 2020-10-30 14:59 | 2020-10-31 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.2.14 |  |  | FOLLOWERS (LAST MONTH) |  | 2020-10-31 14:59 | 2020-11-01 14:59 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.2.15 |  |  | FOLLOWERS CHANGE |  | 2020-11-01 14:59 | 2020-11-02 14:59 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.3 |  | TWITTER |  |  | 2020-11-03 14:59 | 2020-11-18 14:59 |  | 0 | 88 | 0 | 0 |  |  |  | 0 | 0
| 18.3.1 |  |  | LINK |  | 2020-11-03 14:59 | 2020-11-04 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.3.2 |  |  | PROFILE NAME |  | 2020-11-04 14:59 | 2020-11-05 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.3.3 |  |  | FOLLOWERS |  | 2020-11-05 14:59 | 2020-11-06 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.3.4 |  |  | DATE OF LAST ACTIVITY |  | 2020-11-06 14:59 | 2020-11-07 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.3.5 |  |  | FREQUENCY OF POSTS |  | 2020-11-07 14:59 | 2020-11-08 14:59 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.3.6 |  |  | MONTLY REFERRAL TRAFFIC |  | 2020-11-08 14:59 | 2020-11-09 14:59 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.3.7 |  |  | % OF CHANGE (LAST YEAR) |  | 2020-11-09 14:59 | 2020-11-10 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.3.8 |  |  | % OF CHANGE (LAST MONTH) |  | 2020-11-10 14:59 | 2020-11-11 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.3.9 |  |  | CLICKS PER POST |  | 2020-11-11 14:59 | 2020-11-12 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.3.10 |  |  | CLICKS PER POST (LAST MONTH) |  | 2020-11-12 14:59 | 2020-11-13 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.3.11 |  |  | CLICKS PER POST CHANGE |  | 2020-11-13 14:59 | 2020-11-14 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.3.12 |  |  | FACEBOOK REACH |  | 2020-11-14 14:59 | 2020-11-15 14:59 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.3.13 |  |  | FOLLOWERS (TODAY) |  | 2020-11-15 14:59 | 2020-11-16 14:59 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.3.14 |  |  | FOLLOWERS (LAST MONTH) |  | 2020-11-16 14:59 | 2020-11-17 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.3.15 |  |  | FOLLOWERS CHANGE |  | 2020-11-17 14:59 | 2020-11-18 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.4 |  | LINKED-IN |  |  | 2020-11-19 14:59 | 2020-12-04 14:59 |  | 0 | 88 | 0 | 0 |  |  |  | 0 | 0
| 18.4.1 |  |  | LINK |  | 2020-11-19 14:59 | 2020-11-20 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.4.2 |  |  | PROFILE NAME |  | 2020-11-20 14:59 | 2020-11-21 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.4.3 |  |  | FOLLOWERS |  | 2020-11-21 14:59 | 2020-11-22 14:59 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.4.4 |  |  | DATE OF LAST ACTIVITY |  | 2020-11-22 14:59 | 2020-11-23 14:59 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.4.5 |  |  | FREQUENCY OF POSTS |  | 2020-11-23 14:59 | 2020-11-24 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.4.6 |  |  | MONTLY REFERRAL TRAFFIC |  | 2020-11-24 14:59 | 2020-11-25 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.4.7 |  |  | % OF CHANGE (LAST YEAR) |  | 2020-11-25 14:59 | 2020-11-26 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.4.8 |  |  | % OF CHANGE (LAST MONTH) |  | 2020-11-26 14:59 | 2020-11-27 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.4.9 |  |  | CLICKS PER POST |  | 2020-11-27 14:59 | 2020-11-28 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.4.10 |  |  | CLICKS PER POST (LAST MONTH) |  | 2020-11-28 14:59 | 2020-11-29 14:59 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.4.11 |  |  | CLICKS PER POST CHANGE |  | 2020-11-29 14:59 | 2020-11-30 14:59 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.4.12 |  |  | FACEBOOK REACH |  | 2020-11-30 14:59 | 2020-12-01 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.4.13 |  |  | FOLLOWERS (TODAY) |  | 2020-12-01 14:59 | 2020-12-02 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.4.14 |  |  | FOLLOWERS (LAST MONTH) |  | 2020-12-02 14:59 | 2020-12-03 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.4.15 |  |  | FOLLOWERS CHANGE |  | 2020-12-03 14:59 | 2020-12-04 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.5 |  | GOOGLE+ |  |  | 2020-12-05 14:59 | 2020-12-20 14:59 |  | 0 | 80 | 0 | 0 |  |  |  | 0 | 0
| 18.5.1 |  |  | LINK |  | 2020-12-05 14:59 | 2020-12-06 14:59 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.5.2 |  |  | PROFILE NAME |  | 2020-12-06 14:59 | 2020-12-07 14:59 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.5.3 |  |  | FOLLOWERS |  | 2020-12-07 14:59 | 2020-12-08 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.5.4 |  |  | DATE OF LAST ACTIVITY |  | 2020-12-08 14:59 | 2020-12-09 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.5.5 |  |  | FREQUENCY OF POSTS |  | 2020-12-09 14:59 | 2020-12-10 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.5.6 |  |  | MONTLY REFERRAL TRAFFIC |  | 2020-12-10 14:59 | 2020-12-11 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.5.7 |  |  | % OF CHANGE (LAST YEAR) |  | 2020-12-11 14:59 | 2020-12-12 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.5.8 |  |  | % OF CHANGE (LAST MONTH) |  | 2020-12-12 14:59 | 2020-12-13 14:59 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.5.9 |  |  | CLICKS PER POST |  | 2020-12-13 14:59 | 2020-12-14 14:59 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.5.10 |  |  | CLICKS PER POST (LAST MONTH) |  | 2020-12-14 14:59 | 2020-12-15 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.5.11 |  |  | CLICKS PER POST CHANGE |  | 2020-12-15 14:59 | 2020-12-16 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.5.12 |  |  | FACEBOOK REACH |  | 2020-12-16 14:59 | 2020-12-17 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.5.13 |  |  | FOLLOWERS (TODAY) |  | 2020-12-17 14:59 | 2020-12-18 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.5.14 |  |  | FOLLOWERS (LAST MONTH) |  | 2020-12-18 14:59 | 2020-12-19 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.5.15 |  |  | FOLLOWERS CHANGE |  | 2020-12-19 14:59 | 2020-12-20 14:59 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.6 |  | SNAPCHAT |  |  | 2020-12-21 14:59 | 2021-01-05 14:59 |  | 0 | 88 | 0 | 0 |  |  |  | 0 | 0
| 18.6.1 |  |  | LINK |  | 2020-12-21 14:59 | 2020-12-22 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.6.2 |  |  | PROFILE NAME |  | 2020-12-22 14:59 | 2020-12-23 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.6.3 |  |  | FOLLOWERS |  | 2020-12-23 14:59 | 2020-12-24 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.6.4 |  |  | DATE OF LAST ACTIVITY |  | 2020-12-24 14:59 | 2020-12-25 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.6.5 |  |  | FREQUENCY OF POSTS |  | 2020-12-25 14:59 | 2020-12-26 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.6.6 |  |  | MONTLY REFERRAL TRAFFIC |  | 2020-12-26 14:59 | 2020-12-27 14:59 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.6.7 |  |  | % OF CHANGE (LAST YEAR) |  | 2020-12-27 14:59 | 2020-12-28 14:59 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.6.8 |  |  | % OF CHANGE (LAST MONTH) |  | 2020-12-28 14:59 | 2020-12-29 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.6.9 |  |  | CLICKS PER POST |  | 2020-12-29 14:59 | 2020-12-30 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.6.10 |  |  | CLICKS PER POST (LAST MONTH) |  | 2020-12-30 14:59 | 2020-12-31 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.6.11 |  |  | CLICKS PER POST CHANGE |  | 2020-12-31 14:59 | 2021-01-01 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.6.12 |  |  | FACEBOOK REACH |  | 2021-01-01 14:59 | 2021-01-02 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.6.13 |  |  | FOLLOWERS (TODAY) |  | 2021-01-02 14:59 | 2021-01-03 14:59 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.6.14 |  |  | FOLLOWERS (LAST MONTH) |  | 2021-01-03 14:59 | 2021-01-04 14:59 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.6.15 |  |  | FOLLOWERS CHANGE |  | 2021-01-04 14:59 | 2021-01-05 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.7 |  | PINTEREST |  |  | 2021-01-06 14:59 | 2021-01-21 14:59 |  | 0 | 88 | 0 | 0 |  |  |  | 0 | 0
| 18.7.1 |  |  | LINK |  | 2021-01-06 14:59 | 2021-01-07 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.7.2 |  |  | PROFILE NAME |  | 2021-01-07 14:59 | 2021-01-08 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.7.3 |  |  | FOLLOWERS |  | 2021-01-08 14:59 | 2021-01-09 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.7.4 |  |  | DATE OF LAST ACTIVITY |  | 2021-01-09 14:59 | 2021-01-10 14:59 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.7.5 |  |  | FREQUENCY OF POSTS |  | 2021-01-10 14:59 | 2021-01-11 14:59 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.7.6 |  |  | MONTLY REFERRAL TRAFFIC |  | 2021-01-11 14:59 | 2021-01-12 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.7.7 |  |  | % OF CHANGE (LAST YEAR) |  | 2021-01-12 14:59 | 2021-01-13 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.7.8 |  |  | % OF CHANGE (LAST MONTH) |  | 2021-01-13 14:59 | 2021-01-14 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.7.9 |  |  | CLICKS PER POST |  | 2021-01-14 14:59 | 2021-01-15 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.7.10 |  |  | CLICKS PER POST (LAST MONTH) |  | 2021-01-15 14:59 | 2021-01-16 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.7.11 |  |  | CLICKS PER POST CHANGE |  | 2021-01-16 14:59 | 2021-01-17 14:59 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.7.12 |  |  | FACEBOOK REACH |  | 2021-01-17 14:59 | 2021-01-18 14:59 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.7.13 |  |  | FOLLOWERS (TODAY) |  | 2021-01-18 14:59 | 2021-01-19 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.7.14 |  |  | FOLLOWERS (LAST MONTH) |  | 2021-01-19 14:59 | 2021-01-20 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.7.15 |  |  | FOLLOWERS CHANGE |  | 2021-01-20 14:59 | 2021-01-21 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.8 |  | TUMBLR |  |  | 2021-01-22 14:59 | 2021-02-06 14:59 |  | 0 | 88 | 0 | 0 |  |  |  | 0 | 0
| 18.8.1 |  |  | LINK |  | 2021-01-22 14:59 | 2021-01-23 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.8.2 |  |  | PROFILE NAME |  | 2021-01-23 14:59 | 2021-01-24 14:59 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.8.3 |  |  | FOLLOWERS |  | 2021-01-24 14:59 | 2021-01-25 14:59 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.8.4 |  |  | DATE OF LAST ACTIVITY |  | 2021-01-25 14:59 | 2021-01-26 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.8.5 |  |  | FREQUENCY OF POSTS |  | 2021-01-26 14:59 | 2021-01-27 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.8.6 |  |  | MONTLY REFERRAL TRAFFIC |  | 2021-01-27 14:59 | 2021-01-28 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.8.7 |  |  | % OF CHANGE (LAST YEAR) |  | 2021-01-28 14:59 | 2021-01-29 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.8.8 |  |  | % OF CHANGE (LAST MONTH) |  | 2021-01-29 14:59 | 2021-01-30 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.8.9 |  |  | CLICKS PER POST |  | 2021-01-30 14:59 | 2021-01-31 14:59 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.8.10 |  |  | CLICKS PER POST (LAST MONTH) |  | 2021-01-31 14:59 | 2021-02-01 14:59 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.8.11 |  |  | CLICKS PER POST CHANGE |  | 2021-02-01 14:59 | 2021-02-02 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.8.12 |  |  | FACEBOOK REACH |  | 2021-02-02 14:59 | 2021-02-03 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.8.13 |  |  | FOLLOWERS (TODAY) |  | 2021-02-03 14:59 | 2021-02-04 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.8.14 |  |  | FOLLOWERS (LAST MONTH) |  | 2021-02-04 14:59 | 2021-02-05 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.8.15 |  |  | FOLLOWERS CHANGE |  | 2021-02-05 14:59 | 2021-02-06 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.9 |  | YOUTUBE |  |  | 2021-02-07 14:59 | 2021-02-22 14:59 |  | 0 | 80 | 0 | 0 |  |  |  | 0 | 0
| 18.9.1 |  |  | LINK |  | 2021-02-07 14:59 | 2021-02-08 14:59 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.9.2 |  |  | PROFILE NAME |  | 2021-02-08 14:59 | 2021-02-09 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.9.3 |  |  | FOLLOWERS |  | 2021-02-09 14:59 | 2021-02-10 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.9.4 |  |  | DATE OF LAST ACTIVITY |  | 2021-02-10 14:59 | 2021-02-11 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.9.5 |  |  | FREQUENCY OF POSTS |  | 2021-02-11 14:59 | 2021-02-12 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.9.6 |  |  | MONTLY REFERRAL TRAFFIC |  | 2021-02-12 14:59 | 2021-02-13 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.9.7 |  |  | % OF CHANGE (LAST YEAR) |  | 2021-02-13 14:59 | 2021-02-14 14:59 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.9.8 |  |  | % OF CHANGE (LAST MONTH) |  | 2021-02-14 14:59 | 2021-02-15 14:59 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.9.9 |  |  | CLICKS PER POST |  | 2021-02-15 14:59 | 2021-02-16 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.9.10 |  |  | CLICKS PER POST (LAST MONTH) |  | 2021-02-16 14:59 | 2021-02-17 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.9.11 |  |  | CLICKS PER POST CHANGE |  | 2021-02-17 14:59 | 2021-02-18 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.9.12 |  |  | FACEBOOK REACH |  | 2021-02-18 14:59 | 2021-02-19 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.9.13 |  |  | FOLLOWERS (TODAY) |  | 2021-02-19 14:59 | 2021-02-20 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.9.14 |  |  | FOLLOWERS (LAST MONTH) |  | 2021-02-20 14:59 | 2021-02-21 14:59 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.9.15 |  |  | FOLLOWERS CHANGE |  | 2021-02-21 14:59 | 2021-02-22 14:59 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.10 |  | OTHER |  |  | 2021-02-23 14:59 | 2021-03-10 14:59 |  | 0 | 88 | 0 | 0 |  |  |  | 0 | 0
| 18.10.1 |  |  | LINK |  | 2021-02-23 14:59 | 2021-02-24 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.10.2 |  |  | PROFILE NAME |  | 2021-02-24 14:59 | 2021-02-25 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.10.3 |  |  | FOLLOWERS |  | 2021-02-25 14:59 | 2021-02-26 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.10.4 |  |  | DATE OF LAST ACTIVITY |  | 2021-02-26 14:59 | 2021-02-27 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.10.5 |  |  | FREQUENCY OF POSTS |  | 2021-02-27 14:59 | 2021-02-28 14:59 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.10.6 |  |  | MONTLY REFERRAL TRAFFIC |  | 2021-02-28 14:59 | 2021-03-01 14:59 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.10.7 |  |  | % OF CHANGE (LAST YEAR) |  | 2021-03-01 14:59 | 2021-03-02 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.10.8 |  |  | % OF CHANGE (LAST MONTH) |  | 2021-03-02 14:59 | 2021-03-03 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.10.9 |  |  | CLICKS PER POST |  | 2021-03-03 14:59 | 2021-03-04 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.10.10 |  |  | CLICKS PER POST (LAST MONTH) |  | 2021-03-04 14:59 | 2021-03-05 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.10.11 |  |  | CLICKS PER POST CHANGE |  | 2021-03-05 14:59 | 2021-03-06 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.10.12 |  |  | FACEBOOK REACH |  | 2021-03-06 14:59 | 2021-03-07 14:59 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.10.13 |  |  | FOLLOWERS (TODAY) |  | 2021-03-07 14:59 | 2021-03-08 14:59 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.10.14 |  |  | FOLLOWERS (LAST MONTH) |  | 2021-03-08 14:59 | 2021-03-09 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.10.15 |  |  | FOLLOWERS CHANGE |  | 2021-03-09 14:59 | 2021-03-10 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.11 |  | OTHER |  |  | 2021-03-11 14:59 | 2021-03-26 14:59 |  | 0 | 88 | 0 | 0 |  |  |  | 0 | 0
| 18.11.1 |  |  | LINK |  | 2021-03-11 14:59 | 2021-03-12 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.11.2 |  |  | PROFILE NAME |  | 2021-03-12 14:59 | 2021-03-13 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.11.3 |  |  | FOLLOWERS |  | 2021-03-13 14:59 | 2021-03-14 14:59 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.11.4 |  |  | DATE OF LAST ACTIVITY |  | 2021-03-14 14:59 | 2021-03-15 14:59 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.11.5 |  |  | FREQUENCY OF POSTS |  | 2021-03-15 14:59 | 2021-03-16 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.11.6 |  |  | MONTLY REFERRAL TRAFFIC |  | 2021-03-16 14:59 | 2021-03-17 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.11.7 |  |  | % OF CHANGE (LAST YEAR) |  | 2021-03-17 14:59 | 2021-03-18 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.11.8 |  |  | % OF CHANGE (LAST MONTH) |  | 2021-03-18 14:59 | 2021-03-19 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.11.9 |  |  | CLICKS PER POST |  | 2021-03-19 14:59 | 2021-03-20 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.11.10 |  |  | CLICKS PER POST (LAST MONTH) |  | 2021-03-20 14:59 | 2021-03-21 14:59 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.11.11 |  |  | CLICKS PER POST CHANGE |  | 2021-03-21 14:59 | 2021-03-22 14:59 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.11.12 |  |  | FACEBOOK REACH |  | 2021-03-22 14:59 | 2021-03-23 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.11.13 |  |  | FOLLOWERS (TODAY) |  | 2021-03-23 14:59 | 2021-03-24 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.11.14 |  |  | FOLLOWERS (LAST MONTH) |  | 2021-03-24 14:59 | 2021-03-25 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 18.11.15 |  |  | FOLLOWERS CHANGE |  | 2021-03-25 14:59 | 2021-03-26 14:59 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
This document has been created with the help of https://ganttpro.com online service
You are free to use the document for your purposes with no limitations. To edit it, please, create a copy or use https://ganttpro.com