## Small Business Marketing Plan
Create professional Gantt charts in GanttPRO in a few clicks
Small Business Marketing Plan | [8 empty] | 2020-05-12 14:14
Color | WBS Number |  |  | Task name / Title | Assigned to | Planned start date | Planned end date | Deadline | Progress (%) | Duration (hours) | Estimated hours | Time log (minutes) | Status | Priority | Task description | Cost | Actual cost
| 1 | Small business marketing plan |  |  |  | 2020-05-13 14:14 | 2020-05-14 14:14 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 2 | Business Overview |  |  |  | 2020-05-15 14:14 | 2020-05-18 14:14 |  | 0 | 16 | 0 | 0 |  |  |  | 0 | 0
| 2.1 |  | History Of Company |  |  | 2020-05-15 14:14 | 2020-05-16 14:14 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.2 |  | Business Profile |  |  | 2020-05-16 14:14 | 2020-05-17 14:14 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.3 |  | Form Of Business |  |  | 2020-05-17 14:14 | 2020-05-18 14:14 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 3 | The Market |  |  |  | 2020-05-19 14:14 | 2020-06-03 14:14 |  | 0 | 88 | 0 | 0 |  |  |  | 0 | 0
| 3.1 |  | Industry Trends |  |  | 2020-05-19 14:14 | 2020-05-20 14:14 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 3.2 |  | Market Analysis |  |  | 2020-05-20 14:14 | 2020-05-21 14:14 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 3.3 |  | Target Markets |  |  | 2020-05-21 14:14 | 2020-05-22 14:14 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 3.4 |  | Customer Profile |  |  | 2020-05-22 14:14 | 2020-05-23 14:14 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 3.5 |  | Competition |  |  | 2020-05-23 14:14 | 2020-05-24 14:14 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 3.6 |  | Legal and Regulatory Environment |  |  | 2020-05-24 14:14 | 2020-05-25 14:14 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 3.7 |  | SWOT Analysis |  |  | 2020-05-25 14:14 | 2020-05-26 14:14 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 3.8 |  | Risk/ Reward Analysis |  |  | 2020-05-26 14:14 | 2020-05-27 14:14 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 3.9 |  | Marketing Strategy |  |  | 2020-05-28 14:14 | 2020-06-03 14:14 |  | 0 | 32 | 0 | 0 |  |  |  | 0 | 0
| 3.9.1 |  |  | Overall Strategy |  | 2020-05-28 14:14 | 2020-05-29 14:14 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 3.9.2 |  |  | Description of Service |  | 2020-05-29 14:14 | 2020-05-30 14:14 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 3.9.3 |  |  | Pricing Policy |  | 2020-05-30 14:14 | 2020-05-31 14:14 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 3.9.4 |  |  | Placement/ Positioning |  | 2020-05-31 14:14 | 2020-06-01 14:14 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 3.9.5 |  |  | Service Delivery |  | 2020-06-01 14:14 | 2020-06-02 14:14 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 3.9.6 |  |  | Promotional strategy |  | 2020-06-02 14:14 | 2020-06-03 14:14 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 4 | Operations Plan |  |  |  | 2020-06-04 14:14 | 2020-06-07 14:14 |  | 0 | 24 | 0 | 0 |  |  |  | 0 | 0
| 4.1 |  | Details of Operation |  |  | 2020-06-04 14:14 | 2020-06-05 14:14 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.2 |  | Location and premises |  |  | 2020-06-05 14:14 | 2020-06-06 14:14 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.3 |  | Infrastructure |  |  | 2020-06-06 14:14 | 2020-06-07 14:14 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5 | Organization/Management |  |  |  | 2020-06-08 14:14 | 2020-06-15 14:14 |  | 0 | 40 | 0 | 0 |  |  |  | 0 | 0
| 5.1 |  | Ownership Structure |  |  | 2020-06-08 14:14 | 2020-06-09 14:14 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.2 |  | Directors Profile |  |  | 2020-06-09 14:14 | 2020-06-10 14:14 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.3 |  | Organization Chart |  |  | 2020-06-10 14:14 | 2020-06-11 14:14 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.4 |  | Management Team |  |  | 2020-06-11 14:14 | 2020-06-12 14:14 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.5 |  | Management Responsibilities |  |  | 2020-06-12 14:14 | 2020-06-13 14:14 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.6 |  | Staffing Plan |  |  | 2020-06-13 14:14 | 2020-06-14 14:14 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.7 |  | Trade Union Affiliation/ NBC Agreement |  |  | 2020-06-14 14:14 | 2020-06-15 14:14 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 6 | Financial Plan |  |  |  | 2020-06-16 14:14 | 2020-06-25 14:14 |  | 0 | 56 | 0 | 0 |  |  |  | 0 | 0
| 6.1 |  | Planned Capital Expenditure |  |  | 2020-06-16 14:14 | 2020-06-17 14:14 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 6.2 |  | Vehicle Costing Analysis |  |  | 2020-06-17 14:14 | 2020-06-18 14:14 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 6.3 |  | Loan Amortization Schedules |  |  | 2020-06-18 14:14 | 2020-06-19 14:14 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 6.4 |  | Route Planning Analysis |  |  | 2020-06-19 14:14 | 2020-06-20 14:14 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 6.5 |  | Financial Projections |  |  | 2020-06-21 14:14 | 2020-06-24 14:14 |  | 0 | 8 | 0 | 0 |  |  |  | 0 | 0
| 6.5.1 |  |  | Income Statement |  | 2020-06-21 14:14 | 2020-06-22 14:14 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 6.5.2 |  |  | Balance Sheet |  | 2020-06-22 14:14 | 2020-06-23 14:14 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 6.5.3 |  |  | Cash Flow Statement |  | 2020-06-23 14:14 | 2020-06-24 14:14 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 6.6 |  | Financial Ratios |  |  | 2020-06-24 14:14 | 2020-06-25 14:14 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
This document has been created with the help of https://ganttpro.com online service
You are free to use the document for your purposes with no limitations. To edit it, please, create a copy or use https://ganttpro.com