## Social Media Marketing
Create professional Gantt charts in GanttPRO in a few clicks
Social Media Marketing | [8 empty] | 2020-05-12 13:30
Color | WBS Number |  |  | Task name / Title | Assigned to | Planned start date | Planned end date | Deadline | Progress (%) | Duration (hours) | Estimated hours | Time log (minutes) | Status | Priority | Task description | Cost | Actual cost
| 1 | ANALYSIS AND STRATEGY |  |  |  | 2020-05-13 13:30 | 2020-05-19 13:30 |  | 0 | 36 | 0 | 0 |  |  |  | 0 | 0
| 1.1 |  | COMPANY DEFINED |  |  | 2020-05-13 13:30 | 2020-05-14 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 1.2 |  | YOUR MISSION |  |  | 2020-05-14 13:30 | 2020-05-15 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 1.3 |  | YOUR VISION |  |  | 2020-05-15 13:30 | 2020-05-18 13:30 |  | 0 | 10 | 0 | 0 | Open | Medium |  | 0 | 0
| 1.4 |  | TARGET AUDIENCE |  |  | 2020-05-16 13:30 | 2020-05-17 13:30 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 1.5 |  | YOUR MESSAGE |  |  | 2020-05-17 13:30 | 2020-05-18 13:30 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 1.6 |  | STRENGTHS DEFINED |  |  | 2020-05-18 13:30 | 2020-05-19 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 1.7 |  | WEAKNESSES DEFINED |  |  | 2020-05-19 13:30 | 2020-05-19 13:30 |  | 0 | 4 | 0 | 0 | Open | Medium |  | 0 | 0
| 2 | SOCIAL MEDIA MARKETING (BUDGET) |  |  |  | 2020-05-21 13:30 | 2020-06-01 13:30 |  | 0 | 56 | 0 | 0 |  |  |  | 0 | 0
| 2.1 |  | HUMAN RESOURCES - COST |  |  | 2020-05-21 13:30 | 2020-05-22 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.2 |  | ADVERTISING |  |  | 2020-05-22 13:30 | 2020-05-23 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.3 |  | PROMOTIONS |  |  | 2020-05-23 13:30 | 2020-05-24 13:30 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.4 |  | AGENCY FEES / RETAINER |  |  | 2020-05-24 13:30 | 2020-05-25 13:30 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.5 |  | HARDWARE |  |  | 2020-05-25 13:30 | 2020-05-26 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.6 |  | CONTENT CREATION |  |  | 2020-05-26 13:30 | 2020-05-27 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.7 |  | CONTENT MANAGEMENT |  |  | 2020-05-27 13:30 | 2020-05-28 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.8 |  | LICENSED CONTENT |  |  | 2020-05-28 13:30 | 2020-05-29 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.9 |  | SOFTWARE LICENSES |  |  | 2020-05-29 13:30 | 2020-05-30 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.10 |  | GRAPHIC DESIGN |  |  | 2020-05-30 13:30 | 2020-05-31 13:30 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 2.11 |  | VIDEO PRODUCTION |  |  | 2020-05-31 13:30 | 2020-06-01 13:30 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 3 | COMPETITIVE ANALYSIS |  |  |  | 2020-06-02 13:30 | 2020-06-08 13:30 |  | 0 | 32 | 0 | 0 |  |  |  | 0 | 0
| 3.1 |  | YOUR COMPANY'S COMPETITIVE EDGE |  |  | 2020-06-02 13:30 | 2020-06-03 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 3.2 |  | COMPETITION DEFINED |  |  | 2020-06-03 13:30 | 2020-06-04 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 3.3 |  | COMPETITION STRENGTHS |  |  | 2020-06-04 13:30 | 2020-06-05 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 3.4 |  | WHAT YOUR COMPANY CAN DO DIFFERENTLY |  |  | 2020-06-05 13:30 | 2020-06-06 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 3.5 |  | POTENTIAL ROADBLOCKS |  |  | 2020-06-06 13:30 | 2020-06-07 13:30 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 3.6 |  | BENEFITS |  |  | 2020-06-07 13:30 | 2020-06-08 13:30 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 4 | PLAN BUILDING |  |  |  | 2020-06-09 13:30 | 2020-06-17 13:30 |  | 0 | 48 | 0 | 0 |  |  |  | 0 | 0
| 4.1 |  | JOURNALISTS |  |  | 2020-06-09 13:30 | 2020-06-10 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.2 |  | BLOGGERS |  |  | 2020-06-10 13:30 | 2020-06-11 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.3 |  | SOCIAL MEDIA INFLUENCERS |  |  | 2020-06-11 13:30 | 2020-06-12 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.4 |  | SOCIAL MEDIA INTERACTORS |  |  | 2020-06-12 13:30 | 2020-06-13 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.5 |  | PEERS AND PARTNERS |  |  | 2020-06-13 13:30 | 2020-06-14 13:30 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.6 |  | CROSS PROMOTIONS |  |  | 2020-06-14 13:30 | 2020-06-15 13:30 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.7 |  | OTHER |  |  | 2020-06-15 13:30 | 2020-06-16 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 4.8 |  | OTHER |  |  | 2020-06-16 13:30 | 2020-06-17 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5 | SOCIAL MEDIA AUDIT |  |  |  | 2020-06-19 13:30 | 2020-11-25 13:30 |  | 0 | 904 | 0 | 0 |  |  |  | 0 | 0
| 5.1 |  | FACEBOOK |  |  | 2020-06-19 13:30 | 2020-07-04 13:30 |  | 0 | 88 | 0 | 0 |  |  |  | 0 | 0
| 5.1.1 |  |  | LINK |  | 2020-06-19 13:30 | 2020-06-20 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.1.2 |  |  | PROFILE NAME |  | 2020-06-20 13:30 | 2020-06-21 13:30 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.1.3 |  |  | FOLLOWERS |  | 2020-06-21 13:30 | 2020-06-22 13:30 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.1.4 |  |  | DATE OF LAST ACTIVITY |  | 2020-06-22 13:30 | 2020-06-23 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.1.5 |  |  | FREQUENCY OF POSTS |  | 2020-06-23 13:30 | 2020-06-24 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.1.6 |  |  | MONTLY REFERRAL TRAFFIC |  | 2020-06-24 13:30 | 2020-06-25 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.1.7 |  |  | % OF CHANGE (LAST YEAR) |  | 2020-06-25 13:30 | 2020-06-26 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.1.8 |  |  | % OF CHANGE (LAST MONTH) |  | 2020-06-26 13:30 | 2020-06-27 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.1.9 |  |  | CLICKS PER POST |  | 2020-06-27 13:30 | 2020-06-28 13:30 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.1.10 |  |  | CLICKS PER POST (LAST MONTH) |  | 2020-06-28 13:30 | 2020-06-29 13:30 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.1.11 |  |  | CLICKS PER POST CHANGE |  | 2020-06-29 13:30 | 2020-06-30 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.1.12 |  |  | FACEBOOK REACH |  | 2020-06-30 13:30 | 2020-07-01 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.1.13 |  |  | FOLLOWERS (TODAY) |  | 2020-07-01 13:30 | 2020-07-02 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.1.14 |  |  | FOLLOWERS (LAST MONTH) |  | 2020-07-02 13:30 | 2020-07-03 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.1.15 |  |  | FOLLOWERS CHANGE |  | 2020-07-03 13:30 | 2020-07-04 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.2 |  | INSTAGRAM |  |  | 2020-07-05 13:30 | 2020-07-20 13:30 |  | 0 | 80 | 0 | 0 |  |  |  | 0 | 0
| 5.2.1 |  |  | LINK |  | 2020-07-05 13:30 | 2020-07-06 13:30 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.2.2 |  |  | PROFILE NAME |  | 2020-07-06 13:30 | 2020-07-07 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.2.3 |  |  | FOLLOWERS |  | 2020-07-07 13:30 | 2020-07-08 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.2.4 |  |  | DATE OF LAST ACTIVITY |  | 2020-07-08 13:30 | 2020-07-09 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.2.5 |  |  | FREQUENCY OF POSTS |  | 2020-07-09 13:30 | 2020-07-10 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.2.6 |  |  | MONTLY REFERRAL TRAFFIC |  | 2020-07-10 13:30 | 2020-07-11 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.2.7 |  |  | % OF CHANGE (LAST YEAR) |  | 2020-07-11 13:30 | 2020-07-12 13:30 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.2.8 |  |  | % OF CHANGE (LAST MONTH) |  | 2020-07-12 13:30 | 2020-07-13 13:30 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.2.9 |  |  | CLICKS PER POST |  | 2020-07-13 13:30 | 2020-07-14 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.2.10 |  |  | CLICKS PER POST (LAST MONTH) |  | 2020-07-14 13:30 | 2020-07-15 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.2.11 |  |  | CLICKS PER POST CHANGE |  | 2020-07-15 13:30 | 2020-07-16 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.2.12 |  |  | FACEBOOK REACH |  | 2020-07-16 13:30 | 2020-07-17 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.2.13 |  |  | FOLLOWERS (TODAY) |  | 2020-07-17 13:30 | 2020-07-18 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.2.14 |  |  | FOLLOWERS (LAST MONTH) |  | 2020-07-18 13:30 | 2020-07-19 13:30 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.2.15 |  |  | FOLLOWERS CHANGE |  | 2020-07-19 13:30 | 2020-07-20 13:30 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.3 |  | TWITTER |  |  | 2020-07-21 13:30 | 2020-08-05 13:30 |  | 0 | 88 | 0 | 0 |  |  |  | 0 | 0
| 5.3.1 |  |  | LINK |  | 2020-07-21 13:30 | 2020-07-22 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.3.2 |  |  | PROFILE NAME |  | 2020-07-22 13:30 | 2020-07-23 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.3.3 |  |  | FOLLOWERS |  | 2020-07-23 13:30 | 2020-07-24 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.3.4 |  |  | DATE OF LAST ACTIVITY |  | 2020-07-24 13:30 | 2020-07-25 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.3.5 |  |  | FREQUENCY OF POSTS |  | 2020-07-25 13:30 | 2020-07-26 13:30 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.3.6 |  |  | MONTLY REFERRAL TRAFFIC |  | 2020-07-26 13:30 | 2020-07-27 13:30 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.3.7 |  |  | % OF CHANGE (LAST YEAR) |  | 2020-07-27 13:30 | 2020-07-28 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.3.8 |  |  | % OF CHANGE (LAST MONTH) |  | 2020-07-28 13:30 | 2020-07-29 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.3.9 |  |  | CLICKS PER POST |  | 2020-07-29 13:30 | 2020-07-30 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.3.10 |  |  | CLICKS PER POST (LAST MONTH) |  | 2020-07-30 13:30 | 2020-07-31 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.3.11 |  |  | CLICKS PER POST CHANGE |  | 2020-07-31 13:30 | 2020-08-01 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.3.12 |  |  | FACEBOOK REACH |  | 2020-08-01 13:30 | 2020-08-02 13:30 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.3.13 |  |  | FOLLOWERS (TODAY) |  | 2020-08-02 13:30 | 2020-08-03 13:30 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.3.14 |  |  | FOLLOWERS (LAST MONTH) |  | 2020-08-03 13:30 | 2020-08-04 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.3.15 |  |  | FOLLOWERS CHANGE |  | 2020-08-04 13:30 | 2020-08-05 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.4 |  | LINKED-IN |  |  | 2020-08-06 13:30 | 2020-08-21 13:30 |  | 0 | 88 | 0 | 0 |  |  |  | 0 | 0
| 5.4.1 |  |  | LINK |  | 2020-08-06 13:30 | 2020-08-07 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.4.2 |  |  | PROFILE NAME |  | 2020-08-07 13:30 | 2020-08-08 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.4.3 |  |  | FOLLOWERS |  | 2020-08-08 13:30 | 2020-08-09 13:30 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.4.4 |  |  | DATE OF LAST ACTIVITY |  | 2020-08-09 13:30 | 2020-08-10 13:30 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.4.5 |  |  | FREQUENCY OF POSTS |  | 2020-08-10 13:30 | 2020-08-11 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.4.6 |  |  | MONTLY REFERRAL TRAFFIC |  | 2020-08-11 13:30 | 2020-08-12 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.4.7 |  |  | % OF CHANGE (LAST YEAR) |  | 2020-08-12 13:30 | 2020-08-13 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.4.8 |  |  | % OF CHANGE (LAST MONTH) |  | 2020-08-13 13:30 | 2020-08-14 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.4.9 |  |  | CLICKS PER POST |  | 2020-08-14 13:30 | 2020-08-15 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.4.10 |  |  | CLICKS PER POST (LAST MONTH) |  | 2020-08-15 13:30 | 2020-08-16 13:30 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.4.11 |  |  | CLICKS PER POST CHANGE |  | 2020-08-16 13:30 | 2020-08-17 13:30 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.4.12 |  |  | FACEBOOK REACH |  | 2020-08-17 13:30 | 2020-08-18 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.4.13 |  |  | FOLLOWERS (TODAY) |  | 2020-08-18 13:30 | 2020-08-19 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.4.14 |  |  | FOLLOWERS (LAST MONTH) |  | 2020-08-19 13:30 | 2020-08-20 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.4.15 |  |  | FOLLOWERS CHANGE |  | 2020-08-20 13:30 | 2020-08-21 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.5 |  | GOOGLE+ |  |  | 2020-08-22 13:30 | 2020-09-06 13:30 |  | 0 | 80 | 0 | 0 |  |  |  | 0 | 0
| 5.5.1 |  |  | LINK |  | 2020-08-22 13:30 | 2020-08-23 13:30 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.5.2 |  |  | PROFILE NAME |  | 2020-08-23 13:30 | 2020-08-24 13:30 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.5.3 |  |  | FOLLOWERS |  | 2020-08-24 13:30 | 2020-08-25 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.5.4 |  |  | DATE OF LAST ACTIVITY |  | 2020-08-25 13:30 | 2020-08-26 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.5.5 |  |  | FREQUENCY OF POSTS |  | 2020-08-26 13:30 | 2020-08-27 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.5.6 |  |  | MONTLY REFERRAL TRAFFIC |  | 2020-08-27 13:30 | 2020-08-28 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.5.7 |  |  | % OF CHANGE (LAST YEAR) |  | 2020-08-28 13:30 | 2020-08-29 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.5.8 |  |  | % OF CHANGE (LAST MONTH) |  | 2020-08-29 13:30 | 2020-08-30 13:30 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.5.9 |  |  | CLICKS PER POST |  | 2020-08-30 13:30 | 2020-08-31 13:30 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.5.10 |  |  | CLICKS PER POST (LAST MONTH) |  | 2020-08-31 13:30 | 2020-09-01 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.5.11 |  |  | CLICKS PER POST CHANGE |  | 2020-09-01 13:30 | 2020-09-02 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.5.12 |  |  | FACEBOOK REACH |  | 2020-09-02 13:30 | 2020-09-03 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.5.13 |  |  | FOLLOWERS (TODAY) |  | 2020-09-03 13:30 | 2020-09-04 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.5.14 |  |  | FOLLOWERS (LAST MONTH) |  | 2020-09-04 13:30 | 2020-09-05 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.5.15 |  |  | FOLLOWERS CHANGE |  | 2020-09-05 13:30 | 2020-09-06 13:30 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.6 |  | SNAPCHAT |  |  | 2020-09-07 13:30 | 2020-09-22 13:30 |  | 0 | 88 | 0 | 0 |  |  |  | 0 | 0
| 5.6.1 |  |  | LINK |  | 2020-09-07 13:30 | 2020-09-08 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.6.2 |  |  | PROFILE NAME |  | 2020-09-08 13:30 | 2020-09-09 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.6.3 |  |  | FOLLOWERS |  | 2020-09-09 13:30 | 2020-09-10 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.6.4 |  |  | DATE OF LAST ACTIVITY |  | 2020-09-10 13:30 | 2020-09-11 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.6.5 |  |  | FREQUENCY OF POSTS |  | 2020-09-11 13:30 | 2020-09-12 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.6.6 |  |  | MONTLY REFERRAL TRAFFIC |  | 2020-09-12 13:30 | 2020-09-13 13:30 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.6.7 |  |  | % OF CHANGE (LAST YEAR) |  | 2020-09-13 13:30 | 2020-09-14 13:30 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.6.8 |  |  | % OF CHANGE (LAST MONTH) |  | 2020-09-14 13:30 | 2020-09-15 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.6.9 |  |  | CLICKS PER POST |  | 2020-09-15 13:30 | 2020-09-16 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.6.10 |  |  | CLICKS PER POST (LAST MONTH) |  | 2020-09-16 13:30 | 2020-09-17 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.6.11 |  |  | CLICKS PER POST CHANGE |  | 2020-09-17 13:30 | 2020-09-18 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.6.12 |  |  | FACEBOOK REACH |  | 2020-09-18 13:30 | 2020-09-19 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.6.13 |  |  | FOLLOWERS (TODAY) |  | 2020-09-19 13:30 | 2020-09-20 13:30 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.6.14 |  |  | FOLLOWERS (LAST MONTH) |  | 2020-09-20 13:30 | 2020-09-21 13:30 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.6.15 |  |  | FOLLOWERS CHANGE |  | 2020-09-21 13:30 | 2020-09-22 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.7 |  | PINTEREST |  |  | 2020-09-23 13:30 | 2020-10-08 13:30 |  | 0 | 88 | 0 | 0 |  |  |  | 0 | 0
| 5.7.1 |  |  | LINK |  | 2020-09-23 13:30 | 2020-09-24 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.7.2 |  |  | PROFILE NAME |  | 2020-09-24 13:30 | 2020-09-25 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.7.3 |  |  | FOLLOWERS |  | 2020-09-25 13:30 | 2020-09-26 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.7.4 |  |  | DATE OF LAST ACTIVITY |  | 2020-09-26 13:30 | 2020-09-27 13:30 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.7.5 |  |  | FREQUENCY OF POSTS |  | 2020-09-27 13:30 | 2020-09-28 13:30 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.7.6 |  |  | MONTLY REFERRAL TRAFFIC |  | 2020-09-28 13:30 | 2020-09-29 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.7.7 |  |  | % OF CHANGE (LAST YEAR) |  | 2020-09-29 13:30 | 2020-09-30 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.7.8 |  |  | % OF CHANGE (LAST MONTH) |  | 2020-09-30 13:30 | 2020-10-01 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.7.9 |  |  | CLICKS PER POST |  | 2020-10-01 13:30 | 2020-10-02 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.7.10 |  |  | CLICKS PER POST (LAST MONTH) |  | 2020-10-02 13:30 | 2020-10-03 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.7.11 |  |  | CLICKS PER POST CHANGE |  | 2020-10-03 13:30 | 2020-10-04 13:30 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.7.12 |  |  | FACEBOOK REACH |  | 2020-10-04 13:30 | 2020-10-05 13:30 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.7.13 |  |  | FOLLOWERS (TODAY) |  | 2020-10-05 13:30 | 2020-10-06 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.7.14 |  |  | FOLLOWERS (LAST MONTH) |  | 2020-10-06 13:30 | 2020-10-07 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.7.15 |  |  | FOLLOWERS CHANGE |  | 2020-10-07 13:30 | 2020-10-08 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.8 |  | TUMBLR |  |  | 2020-10-09 13:30 | 2020-10-24 13:30 |  | 0 | 88 | 0 | 0 |  |  |  | 0 | 0
| 5.8.1 |  |  | LINK |  | 2020-10-09 13:30 | 2020-10-10 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.8.2 |  |  | PROFILE NAME |  | 2020-10-10 13:30 | 2020-10-11 13:30 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.8.3 |  |  | FOLLOWERS |  | 2020-10-11 13:30 | 2020-10-12 13:30 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.8.4 |  |  | DATE OF LAST ACTIVITY |  | 2020-10-12 13:30 | 2020-10-13 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.8.5 |  |  | FREQUENCY OF POSTS |  | 2020-10-13 13:30 | 2020-10-14 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.8.6 |  |  | MONTLY REFERRAL TRAFFIC |  | 2020-10-14 13:30 | 2020-10-15 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.8.7 |  |  | % OF CHANGE (LAST YEAR) |  | 2020-10-15 13:30 | 2020-10-16 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.8.8 |  |  | % OF CHANGE (LAST MONTH) |  | 2020-10-16 13:30 | 2020-10-17 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.8.9 |  |  | CLICKS PER POST |  | 2020-10-17 13:30 | 2020-10-18 13:30 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.8.10 |  |  | CLICKS PER POST (LAST MONTH) |  | 2020-10-18 13:30 | 2020-10-19 13:30 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.8.11 |  |  | CLICKS PER POST CHANGE |  | 2020-10-19 13:30 | 2020-10-20 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.8.12 |  |  | FACEBOOK REACH |  | 2020-10-20 13:30 | 2020-10-21 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.8.13 |  |  | FOLLOWERS (TODAY) |  | 2020-10-21 13:30 | 2020-10-22 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.8.14 |  |  | FOLLOWERS (LAST MONTH) |  | 2020-10-22 13:30 | 2020-10-23 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.8.15 |  |  | FOLLOWERS CHANGE |  | 2020-10-23 13:30 | 2020-10-24 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.9 |  | YOUTUBE |  |  | 2020-10-25 13:30 | 2020-11-09 13:30 |  | 0 | 80 | 0 | 0 |  |  |  | 0 | 0
| 5.9.1 |  |  | LINK |  | 2020-10-25 13:30 | 2020-10-26 13:30 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.9.2 |  |  | PROFILE NAME |  | 2020-10-26 13:30 | 2020-10-27 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.9.3 |  |  | FOLLOWERS |  | 2020-10-27 13:30 | 2020-10-28 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.9.4 |  |  | DATE OF LAST ACTIVITY |  | 2020-10-28 13:30 | 2020-10-29 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.9.5 |  |  | FREQUENCY OF POSTS |  | 2020-10-29 13:30 | 2020-10-30 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.9.6 |  |  | MONTLY REFERRAL TRAFFIC |  | 2020-10-30 13:30 | 2020-10-31 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.9.7 |  |  | % OF CHANGE (LAST YEAR) |  | 2020-10-31 13:30 | 2020-11-01 13:30 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.9.8 |  |  | % OF CHANGE (LAST MONTH) |  | 2020-11-01 13:30 | 2020-11-02 13:30 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.9.9 |  |  | CLICKS PER POST |  | 2020-11-02 13:30 | 2020-11-03 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.9.10 |  |  | CLICKS PER POST (LAST MONTH) |  | 2020-11-03 13:30 | 2020-11-04 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.9.11 |  |  | CLICKS PER POST CHANGE |  | 2020-11-04 13:30 | 2020-11-05 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.9.12 |  |  | FACEBOOK REACH |  | 2020-11-05 13:30 | 2020-11-06 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.9.13 |  |  | FOLLOWERS (TODAY) |  | 2020-11-06 13:30 | 2020-11-07 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.9.14 |  |  | FOLLOWERS (LAST MONTH) |  | 2020-11-07 13:30 | 2020-11-08 13:30 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.9.15 |  |  | FOLLOWERS CHANGE |  | 2020-11-08 13:30 | 2020-11-09 13:30 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.10 |  | OTHER |  |  | 2020-11-10 13:30 | 2020-11-25 13:30 |  | 0 | 88 | 0 | 0 |  |  |  | 0 | 0
| 5.10.1 |  |  | LINK |  | 2020-11-10 13:30 | 2020-11-11 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.10.2 |  |  | PROFILE NAME |  | 2020-11-11 13:30 | 2020-11-12 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.10.3 |  |  | FOLLOWERS |  | 2020-11-12 13:30 | 2020-11-13 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.10.4 |  |  | DATE OF LAST ACTIVITY |  | 2020-11-13 13:30 | 2020-11-14 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.10.5 |  |  | FREQUENCY OF POSTS |  | 2020-11-14 13:30 | 2020-11-15 13:30 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.10.6 |  |  | MONTLY REFERRAL TRAFFIC |  | 2020-11-15 13:30 | 2020-11-16 13:30 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.10.7 |  |  | % OF CHANGE (LAST YEAR) |  | 2020-11-16 13:30 | 2020-11-17 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.10.8 |  |  | % OF CHANGE (LAST MONTH) |  | 2020-11-17 13:30 | 2020-11-18 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.10.9 |  |  | CLICKS PER POST |  | 2020-11-18 13:30 | 2020-11-19 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.10.10 |  |  | CLICKS PER POST (LAST MONTH) |  | 2020-11-19 13:30 | 2020-11-20 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.10.11 |  |  | CLICKS PER POST CHANGE |  | 2020-11-20 13:30 | 2020-11-21 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.10.12 |  |  | FACEBOOK REACH |  | 2020-11-21 13:30 | 2020-11-22 13:30 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.10.13 |  |  | FOLLOWERS (TODAY) |  | 2020-11-22 13:30 | 2020-11-23 13:30 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.10.14 |  |  | FOLLOWERS (LAST MONTH) |  | 2020-11-23 13:30 | 2020-11-24 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.10.15 |  |  | FOLLOWERS CHANGE |  | 2020-11-24 13:30 | 2020-11-25 13:30 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
This document has been created with the help of https://ganttpro.com online service
You are free to use the document for your purposes with no limitations. To edit it, please, create a copy or use https://ganttpro.com