## Strategic Retail Planning
Create professional Gantt charts in GanttPRO in a few clicks
Strategic Retail Planning | [8 empty] | 2022-07-25 13:20
Color | WBS Number |  |  | Task name / Title | Assigned to | Planned start date | Planned end date | Deadline | Progress (%) | Duration (hours) | Estimated hours | Time log (minutes) | Status | Priority | Task description | Predecessor | Cost | Actual cost
| 1 | Make a Plan |  |  |  | 2022-07-28 13:20 | 2022-08-01 13:20 |  | 0 | 40 | 0 | 0 |  |  |  |  | 0 | 0
| 1.1 |  | Growth & Income |  |  | 2022-07-28 13:20 | 2022-07-30 13:20 |  | 0 | 24 | 0 | 0 | Open | Medium |  |  | 0 | 0
| 1.2 |  | Strengths & Weaknesses |  |  | 2022-07-28 13:20 | 2022-07-30 13:20 |  | 0 | 24 | 0 | 0 | Open | Medium |  | 1.1 | 0 | 0
| 1.3 |  | Goals |  |  | 2022-07-28 13:20 | 2022-08-01 13:20 |  | 0 | 40 | 0 | 0 | Open | Medium |  | 1.2 | 0 | 0
| 2 | Decisions |  |  |  | 2022-08-04 13:20 | 2022-08-15 13:20 |  | 0 | 80 | 0 | 0 |  |  |  | 1 | 0 | 0
| 2.1 |  | Franchises |  |  | 2022-08-11 13:20 | 2022-08-12 13:20 |  | 0 | 16 | 0 | 0 | Open | Medium |  |  | 0 | 0
| 2.2 |  | Launching Your Own Business |  |  | 2022-08-11 13:20 | 2022-08-15 13:20 |  | 0 | 40 | 0 | 0 | Open | Medium |  |  | 0 | 0
| 2.3 |  | Professional Advisor |  |  | 2022-08-04 13:20 | 2022-08-15 13:20 |  | 0 | 80 | 0 | 0 | Open | Medium |  |  | 0 | 0
| 3 | Location |  |  |  | 2022-08-11 13:20 | 2022-08-22 13:20 |  | 0 | 80 | 0 | 0 |  |  |  | 2 | 0 | 0
| 3.1 |  | Homebased Retailer |  |  | 2022-08-11 13:20 | 2022-08-15 13:20 |  | 0 | 40 | 0 | 0 | Open | Medium |  |  | 0 | 0
| 3.2 |  | Merchants Associations |  |  | 2022-08-18 13:20 | 2022-08-22 13:20 |  | 0 | 40 | 0 | 0 | Open | Medium |  | 3.1 | 0 | 0
| 3.3 |  | Landlords |  |  | 2022-08-18 13:20 | 2022-08-22 13:20 |  | 0 | 40 | 0 | 0 | Open | Medium |  | 3.2 | 0 | 0
| 4 | Legal & Finance Issues |  |  |  | 2022-08-11 13:20 | 2022-08-15 13:20 |  | 0 | 40 | 0 | 0 |  |  |  | 3 | 0 | 0
| 4.1 |  | Common Legal Issues |  |  | 2022-08-11 13:20 | 2022-08-15 13:20 |  | 0 | 40 | 0 | 0 | Open | Medium |  |  | 0 | 0
| 4.2 |  | Current Issues in Finance |  |  | 2022-08-11 13:20 | 2022-08-15 13:20 |  | 0 | 40 | 0 | 0 | Open | Medium |  |  | 0 | 0
| 5 | Operations |  |  |  | 2022-08-11 13:20 | 2022-08-15 13:20 |  | 0 | 40 | 0 | 0 |  |  |  | 4 | 0 | 0
| 5.1 |  | Security Policies |  |  | 2022-08-11 13:20 | 2022-08-15 13:20 |  | 0 | 40 | 0 | 0 | Open | Medium |  |  | 0 | 0
| 5.2 |  | Credit Policies |  |  | 2022-08-11 13:20 | 2022-08-15 13:20 |  | 0 | 40 | 0 | 0 | Open | Medium |  | 5.1 | 0 | 0
| 6 | Equipment |  |  |  | 2022-08-11 13:20 | 2022-08-15 13:20 |  | 0 | 40 | 0 | 0 |  |  |  | 5 | 0 | 0
| 6.1 |  | Office Equipment |  |  | 2022-08-11 13:20 | 2022-08-15 13:20 |  | 0 | 40 | 0 | 0 | Open | Medium |  |  | 0 | 0
| 6.2 |  | Sales Equipment |  |  | 2022-08-11 13:20 | 2022-08-15 13:20 |  | 0 | 40 | 0 | 0 | Open | Medium |  |  | 0 | 0
| 7 | Pricing |  |  |  | 2022-08-11 13:20 | 2022-08-22 13:20 |  | 0 | 80 | 0 | 0 |  |  |  | 5 | 0 | 0
| 7.1 |  | Pricing Principles |  |  | 2022-08-11 13:20 | 2022-08-15 13:20 |  | 0 | 40 | 0 | 0 | Open | Medium |  |  | 0 | 0
| 7.2 |  | Approve |  |  | 2022-08-18 13:20 | 2022-08-18 13:20 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 7.1 | 0 | 0
| 7.3 |  | Discounts |  |  | 2022-08-18 13:20 | 2022-08-22 13:20 |  | 0 | 40 | 0 | 0 |  |  |  | 7.2 | 0 | 0
| 7.3.1 |  |  | Quantity Discounts |  | 2022-08-18 13:20 | 2022-08-22 13:20 |  | 0 | 40 | 0 | 0 | Open | Medium |  |  | 0 | 0
| 7.3.2 |  |  | Trade/Organization Disounts |  | 2022-08-18 13:20 | 2022-08-22 13:20 |  | 0 | 40 | 0 | 0 | Open | Medium |  |  | 0 | 0
| 7.3.3 |  |  | Pre-Season Discounts |  | 2022-08-18 13:20 | 2022-08-22 13:20 |  | 0 | 40 | 0 | 0 | Open | Medium |  |  | 0 | 0
| 7.3.4 |  |  | Voucher Discounts |  | 2022-08-18 13:20 | 2022-08-22 13:20 |  | 0 | 40 | 0 | 0 | Open | Medium |  |  | 0 | 0
| 8 | Human Resources |  |  |  | 2022-07-28 13:20 | 2022-08-08 13:20 |  | 0 | 80 | 0 | 0 |  |  |  |  | 0 | 0
| 8.1 |  | Hiring |  |  | 2022-07-28 13:20 | 2022-08-01 13:20 |  | 0 | 40 | 0 | 0 | Open | Medium |  |  | 0 | 0
| 8.2 |  | Manual & Other Materials |  |  | 2022-07-28 13:20 | 2022-08-01 13:20 |  | 0 | 40 | 0 | 0 | Open | Medium |  | 8.1 | 0 | 0
| 8.3 |  | Training |  |  | 2022-08-04 13:20 | 2022-08-08 13:20 |  | 0 | 40 | 0 | 0 | Open | Medium |  | 8.2 | 0 | 0
| 9 | Marketing |  |  |  | 2022-07-28 13:20 | 2022-08-22 13:20 |  | 0 | 160 | 0 | 0 |  |  |  |  | 0 | 0
| 9.1 |  | Promotion Planning |  |  | 2022-07-28 13:20 | 2022-08-01 13:20 |  | 0 | 40 | 0 | 0 | Open | Medium |  |  | 0 | 0
| 9.2 |  | Advertising |  |  | 2022-08-04 13:20 | 2022-08-06 13:20 |  | 0 | 24 | 0 | 0 | Open | Medium |  | 9.1 | 0 | 0
| 9.3 |  | Website |  |  | 2022-08-04 13:20 | 2022-08-06 13:20 |  | 0 | 24 | 0 | 0 | Open | Medium |  | 9.2 | 0 | 0
| 9.4 |  | Special Pricing |  |  | 2022-08-18 13:20 | 2022-08-22 13:20 |  | 0 | 40 | 0 | 0 | Open | Medium |  | 7.3 | 0 | 0
| 9.5 |  | PR |  |  | 2022-08-04 13:20 | 2022-08-06 13:20 |  | 0 | 24 | 0 | 0 | Open | Medium |  | 9.1 | 0 | 0
| 10 | Customer Services |  |  |  | 2022-07-28 13:20 | 2022-08-15 13:20 |  | 0 | 120 | 0 | 0 |  |  |  | 9 | 0 | 0
| 10.1 |  | Customer Relationship |  |  | 2022-07-28 13:20 | 2022-08-01 13:20 |  | 0 | 40 | 0 | 0 | Open | Medium |  |  | 0 | 0
| 10.2 |  | Work with Satisfied Customers |  |  | 2022-08-04 13:20 | 2022-08-08 13:20 |  | 0 | 40 | 0 | 0 | Open | Medium |  | 10.1 | 0 | 0
| 10.3 |  | Handle Unhappy Customers |  |  | 2022-08-11 13:20 | 2022-08-15 13:20 |  | 0 | 40 | 0 | 0 | Open | Medium |  | 10.2 | 0 | 0
| 11 | Risk Management |  |  |  | 2022-07-28 13:20 | 2022-08-15 13:20 |  | 0 | 120 | 0 | 0 |  |  |  |  | 0 | 0
| 11.1 |  | Insurance |  |  | 2022-07-28 13:20 | 2022-08-01 13:20 |  | 0 | 40 | 0 | 0 | Open | Medium |  |  | 0 | 0
| 11.2 |  | Law |  |  | 2022-07-28 13:20 | 2022-08-01 13:20 |  | 0 | 40 | 0 | 0 | Open | Medium |  |  | 0 | 0
| 11.3 |  | Product-Related Issues |  |  | 2022-07-28 13:20 | 2022-08-01 13:20 |  | 0 | 40 | 0 | 0 | Open | Medium |  |  | 0 | 0
| 11.4 |  | Customer-Related Issues |  |  | 2022-08-04 13:20 | 2022-08-08 13:20 |  | 0 | 40 | 0 | 0 | Open | Medium |  | 11.3 | 0 | 0
| 11.5 |  | Employee-Related Issues |  |  | 2022-08-11 13:20 | 2022-08-15 13:20 |  | 0 | 40 | 0 | 0 | Open | Medium |  | 11.4 | 0 | 0
This document has been created with the help of https://ganttpro.com online service
You are free to use the document for your purposes with no limitations. To edit it, please, create a copy or use https://ganttpro.com