## Web Design Project Plan
Create professional Gantt charts in GanttPRO in a few clicks
Web Design Project Plan | [8 empty] | 2020-06-11 13:38
Color | WBS Number |  |  | Task name / Title | Assigned to | Planned start date | Planned end date | Deadline | Progress (%) | Duration (hours) | Estimated hours | Time log (minutes) | Status | Priority | Task description | Cost | Actual cost
| 1 | Research for Main Layout |  |  |  | 2020-06-14 13:38 | 2020-06-25 13:38 |  | 0 | 79 | 0 | 0 |  |  |  | 0 | 0
| 1.1 |  | Collect Client's Vision & Goals |  |  | 2020-06-14 13:38 | 2020-06-15 13:38 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 1.2 |  | Request Client Moodboard |  |  | 2020-06-16 13:38 | 2020-06-16 13:38 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 1.3 |  | Review Brandmarks of Client's Products |  |  | 2020-06-17 13:38 | 2020-06-18 13:38 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 1.4 |  | Research Competitor Brands |  |  | 2020-06-21 13:38 | 2020-06-21 13:38 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 1.5 |  | Present Results of Research to Client |  |  | 2020-06-22 13:38 | 2020-06-22 13:38 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 1.6 |  | Concept Generation |  |  | 2020-06-23 13:38 | 2020-06-25 13:38 |  | 0 | 23 | 0 | 0 |  |  |  | 0 | 0
| 1.6.1 |  |  | Clarify Brand Strategy & Positioning |  | 2020-06-23 13:38 | 2020-06-23 13:38 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 1.6.2 |  |  | Client Feedback |  | 2020-06-24 13:38 | 2020-06-24 13:38 |  | 0 | 4 | 0 | 0 | Open | Medium |  | 0 | 0
| 1.6.3 |  |  | Draft Creative Brief |  | 2020-06-24 13:38 | 2020-06-24 13:38 |  | 0 | 4 | 0 | 0 | Open | Medium |  | 0 | 0
| 1.6.4 |  |  | Gain Client Approval of Creative Brief |  | 2020-06-25 13:38 | 2020-06-25 13:38 |  | 0 | 7 | 0 | 0 | Open | Medium |  | 0 | 0
| 1.6.5 |  |  | Concept Approve |  | 2020-06-25 13:38 | 2020-06-25 13:38 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 2 | Color & Graphics |  |  |  | 2020-06-21 13:38 | 2020-06-25 13:38 |  | 0 | 32 | 0 | 0 |  |  |  | 0 | 0
| 2.1 |  | Color & Graphics |  |  | 2020-06-21 13:38 | 2020-06-25 13:38 |  | 0 | 32 | 0 | 0 | Open | Medium |  | 0 | 0
| 3 | Content Presentation |  |  |  | 2020-06-21 13:38 | 2020-06-25 13:38 |  | 0 | 32 | 0 | 0 |  |  |  | 0 | 0
| 3.1 |  | Common Fonts |  |  | 2020-06-21 13:38 | 2020-06-25 13:38 |  | 0 | 32 | 0 | 0 | Open | Medium |  | 0 | 0
| 3.2 |  | Font Sizes, Font Colors |  |  | 2020-06-21 13:38 | 2020-06-25 13:38 |  | 0 | 32 | 0 | 0 | Open | Medium |  | 0 | 0
| 4 | Multimedia |  |  |  | 2020-06-21 13:38 | 2020-06-25 13:38 |  | 0 | 32 | 0 | 0 |  |  |  | 0 | 0
| 4.1 |  | Multimedia |  |  | 2020-06-21 13:38 | 2020-06-25 13:38 |  | 0 | 32 | 0 | 0 | Open | Medium |  | 0 | 0
| 5 | Functionality |  |  |  | 2020-06-15 13:38 | 2020-06-21 13:38 |  | 0 | 32 | 0 | 0 |  |  |  | 0 | 0
| 5.1 |  | External Hyperlinks |  |  | 2020-06-15 13:38 | 2020-06-15 13:38 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.2 |  | Forms Functionality |  |  | 2020-06-16 13:38 | 2020-06-17 13:38 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.3 |  | JavaScript Errors |  |  | 2020-06-18 13:38 | 2020-06-18 13:38 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 5.4 |  | Functionality Approve |  |  | 2020-06-21 13:38 | 2020-06-21 13:38 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0
| 6 | Prototype 1 |  |  |  | 2020-06-14 13:38 | 2020-06-15 13:38 |  | 0 | 16 | 0 | 0 |  |  |  | 0 | 0
| 6.1 |  | Prototype 1 |  |  | 2020-06-14 13:38 | 2020-06-15 13:38 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 7 | Prototype 2 |  |  |  | 2020-06-14 13:38 | 2020-06-15 13:38 |  | 0 | 16 | 0 | 0 |  |  |  | 0 | 0
| 7.1 |  | Prototype 2 |  |  | 2020-06-14 13:38 | 2020-06-15 13:38 |  | 0 | 16 | 0 | 0 | Open | Medium |  | 0 | 0
| 8 | Browser Compatibility |  |  |  | 2020-06-16 13:38 | 2020-06-21 13:38 |  | 0 | 32 | 0 | 0 |  |  |  | 0 | 0
| 8.1 |  | Test in IE |  |  | 2020-06-16 13:38 | 2020-06-16 13:38 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 8.2 |  | Test in Firefox |  |  | 2020-06-17 13:38 | 2020-06-17 13:38 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 8.3 |  | Test in Chrome |  |  | 2020-06-18 13:38 | 2020-06-18 13:38 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 8.4 |  | Test in Safari |  |  | 2020-06-21 13:38 | 2020-06-21 13:38 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 9 | Accessibility |  |  |  | 2020-06-16 13:38 | 2020-06-16 13:38 |  | 0 | 8 | 0 | 0 |  |  |  | 0 | 0
| 9.1 |  | Accessibility |  |  | 2020-06-16 13:38 | 2020-06-16 13:38 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
| 10 | Finalizing & Bug Reports |  |  |  | 2020-06-16 13:38 | 2020-06-16 13:38 |  | 0 | 8 | 0 | 0 |  |  |  | 0 | 0
| 10.1 |  | Finalizing & Bug Reports |  |  | 2020-06-16 13:38 | 2020-06-16 13:38 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0
This document has been created with the help of https://ganttpro.com online service
You are free to use the document for your purposes with no limitations. To edit it, please, create a copy or use https://ganttpro.com